## Sheet1
Dissertation Project Mangement Chart
| October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  | April |  |  |  | May
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Monday | October Week 2: PREP WEEK (Home); November Week 3: PREP WEEK; December Week 4: CHRISTMAS; Febuary Week 1: PRESENTATION; Febuary Week 2: READING; Febuary Week 3: FINISH READING; Febuary Week 4: DRAFTING + CHECK; March Week 2: DRAFTING + CHECK; March Week 4: FINAL DRAFT; April Week 1: EASTER BREAK; April Week 3: FINAL CHECKS AND PRINTING; May Week 2: PREP WEEK
Tuesday | Febuary Week 1: READING
Wednesday | October Week 3: Library Work (Go Wales); November Week 4: Library Work (Go Wales); January Week 1: Readress Plan and Start On Presentation
Thursday
Friday | October Week 1: PLAN DUE; May Week 1: DIS. DUE
Saturday | October Week 3: Reading For Dissertation; November Week 4: Reading For Dissertation; January Week 1: Work on Upcoming Presentation
Sunday | bar: October Week 2 to January Week 4; Febuary Week 3; March Week 4 to April Week 4; May Week 2
Key:
Dissertation Deadline
No Work on Dissertation
In Block
Work on Dissertation
Set Dissertation Goal
Home for Holidays
Flexible Days
Please scroll over for details
Note on U7: "Finish Reading" = All planned / prepared reading that can be done in advance. Reading whilst drafting may also be required.
Note on V7: Aiming to have "Introduction" and "Analysis of Ancient Text" completed. Aiming to have begun "Analysis of Modern Texts"
Note on X7: Aiming to have completed "Analysis of Modern Texts" and "Comparion of Characterisation's".
Note on Z7: Goal: To have made any necessary adjustments to previous drafts and to have added a finished conclusion. This final draft will need to be checked by the relevent people and edited as needed.
Note on AA7: During the Easter break, whilst at home, I will make sure to continue the editorial process when possible.
Note on E12: Aiming to read article's / chapter's at the weekend. Whilst in Block this might not always be possible. Set as an Aim rather than Goal to allow a degree of flexibility.
Note on J12: Aiming to read article's / chapter's at the weekend. Whilst in Block this might not always be possible. Set as an Aim rather than Goal to allow a degree of flexibility.
Note on C23: Nothing specifically planned for these days. Whatever work is needed can be done here (for Block or Dissertation).
Note on B24: User: