## Cash Flow Forecast
| Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
| 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22
Project Outline / Objectives
Feasibility Study
Development of Project Brief
BIM Execution Plan (BEP) (BIM)
Setup of Common Data Environment (CDE) (BIM)
Site Analysis
Cost Estimates
Outline Project Programme
Client Presentation
Information Requirements Documentation (BIM)
Plan Model Coordination meeting (BIM)
Define LOD requirements for different stages (BIM)
Cost estimate for Project
Technical Design development
Model Co-ordination review (every Thursday) (BIM)
Application for Planning Permission
Monthly Model Federation Review (every 4 weeks) (BIM)
Health & Safety Development
Clash Detection: Architectural vs Structural (BIM)
Clash Detection: MEP vs Architectural/Structural (BIM)
Detailed technical drawings
Asset Classification (BIM)
Finalise Specification
Asset Data Population (BIM)
Tender Documents
Building Regulations
Asset Register Development (BIM)
BIM kiosk setup and training (BIM)
RFI system implementation (BIM)
Site Setup | Month 7: 185320.3632
Ground Remediation | Month 8: 185320.3632
Borehole Drilling and Ground Testing | Month 9: 185320.3632
Excavation for Flood Prevention | Month 10: 185320.3632
Flood Prevention Measures (Drainage etc.) | Month 11: 185320.3632
Sewer and Water Supply Installation | Month 11: 185320.3632
Foundation Works
Pile Foundation Installation | Month 12: 590631.42
Pile Cap Installation | Month 13: 62976
Foundation Curing and Preparation | Month 13: 146072.32
Superstructure Construction
Ground Floor Columns and Beams | Month 13: 1006393.688
Ground Floor Slab Installation | Month 13: 1006393.688; Month 14: 202933.1486
First Floor Columns and Beams | Month 14: 1006393.688
First Floor Slab Installation | Month 13: 202933.1486; Month 14: 202933.1486; Month 15: 1006393.688
Second Floor Columns and Beams | Month 13: 202933.1486; Month 16: 1006393.688
Second Floor Slab Installation | Month 14: 202933.1486; Month 16: 202933.1486; Month 17: 1006393.688
Roof Columns and Beams | Month 13: 202933.1486; Month 17: 1006393.688
Roof Slab Installation | Month 13: 202933.1486; Month 14: 202933.1486; Month 15: 202933.1486; Month 18: 1006393.688
Roof structure | Month 19: 202933.1486
Hydrotherapy Suite Installation | Month 19: 123147.072
Wellness Suite Installation | Month 19: 123147.072
External and Internal Works | Month 19: 64619.52; Month 20: 221818.88; Month 21: 221818.88
External Timber Panel Installation | Month 20: 221818.88; Month 21: 221818.88
Electrical and Plumbing Installations | Month 20: 202933.1486; Month 21: 221818.88
HVAC Installation | Month 20: 202933.1486; Month 21: 221818.88
Ground Floor Fit-Out (Café) | Month 20: 202933.1486
First Floor Fit-Out (Gym) | Month 20: 202933.1486
Second Floor Fit-Out (Studio) | Month 20: 202933.1486
Roof Fit-Out (Wellness/Hydrotherapy) | Month 22: 202933.1486
Final Testing and Commissioning | Month 22: 202933.1486
RIBA Stage 6
Handover
| 0 | 0 | 0 | 0 | 0 | 0 | 185320.3632 | 185320.3632 | 185320.3632 | 185320.3632 | 370640.7264 | 590631.42 | 3033568.2905 | 1818126.2825 | 1209326.8366 | 1209326.8366 | 2012787.376 | 1006393.688 | 513846.8126 | 1458303.5032 | 887275.52 | 405866.2973 |  | 15257375.0427
Cumulative Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 185320.3632 | 370640.7264 | 555961.0897 | 741281.4529 | 1111922.1793 | 1702553.5993 | 4736121.8898 | 6554248.1724 | 7763575.009 | 8972901.8456 | 10985689.2216 | 11992082.9096 | 12505929.7223 | 13964233.2254 | 14851508.7454 | 15257375.0427
[23 empty] | Project Cost | 15257375.0427
[23 empty] | Check | 0