## Front
Jayne Pierson School of Fashion, Art & Design
NRM1 Estimate Cost Plan
Company: Alpha Designs
Project Reference: 6023
Dated:20/04/2024

## Status
NRM1 Feasibility Cost Plan
Monday 06/02/2023
Document Status
Revision | Date | Status | Prepared by | Checked by | Authorised by
DISCLAIMER
This document and its contents have been prepared and are intended solely for [Ace Capital Projects Ltd] information and use in relation to [Jayne Pierson School of Fashion, Art & Design]
Faithful+Gould assumes no responsibility to any other party in respect of or arising out of or in connection with this document and/or its contents.
COPYRIGHT
The copyright of this document is vested in Faithful+Gould. This document may not be reproduced in whole or in part without their express written permission.

## Information Used
Information Used & Assumptions
1 | Information Used
All measures have been under taken using the software app Quickscale
2 | General Assumptions;
External Works is excluded unless specifically identified within the cost plan.
External wall build up specified by client.
Costs are based upon the information as provided.
We have assumed a project bank account will be required for this scheme.
We have assumed that the area of works will be decanted for the project. No allowance is made for throughways or dealing with building occupants.
The exact nature of specification for internal doors, screens, folding partitions and finishes is assumed.
All costs are provisional awaiting design development.
All base costs are based on Q42024
3 | General Notes and Exclusions;
All included costs are subject to variation following design development.
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Works will be undertaken in a single phase.
Local Authority Fees
Building Regulation fees
Acquisition & associated legal

## Summary Original
Project details: | Jayne Pierson, School of Fashion, Art & Design |  |  |  | Arts Council Contribution @15% | 2942249.7976
[5 empty] | Jayne Pierson Contribution @5% | 980749.9325
Description: | Phase 2 of Port Talbot College
Building Works Cost
Based on GIFA of: 3041m2
| Group Element | Element Type | Total | £/m2
| Group element 0 | FACILITATING WORKS | 1861500 | 612.1342
| Group element 1 | SUBSTRUCTURE | 964885.6935 | 317.2922
| Group element 2 | SUPERSTRUCTURE | 2699457 | 887.6873
| Group element 3 | INTENAL FINISHES | 528711.96 | 173.8612
| Group element 4 | FITTINGS AND FURNISHINGS | 980000 | 322.2624
| Group element 5 | SERVICES | 2273241.947 | 747.5311
| Group element 8 | EXTERNAL WORKS | 418824.2857 | 137.7258
| Group element 9 | MAIN CONTRACTORS PRELIMINARIES | 3162938.3755 | 1040.0981
Works cost estimate (sub total A) |  |  | 12889559.2617 | 4238.5923
| Current TPI | 1.24
| Forecasted 2024 Q1 TPI | 2.22
|  |  | 23076469.0008 | 7588.4476
| Wales Location Factor | 0.85
|  |  | 19614998.6507 | 6450.1804
Project Constraints-Provisional sums
Demolition and site clearence |  |  | 100000 | 32.8839
Building Serveys |  |  | 50000 | 16.442
Knotweed treatment |  |  | 30000 | 9.8652
Land surveys |  |  | 5000 | 1.6442
Tower Crane |  |  | 130000 | 42.7491
Traffic management |  |  | 23400 | 7.6948
External services-overhead cable removal |  |  | 80000 | 26.3071
|  |  | 355640 | 116.9484
Project design team fees and other development costs (sub total B)
0HP | 12 % of the overall build cost |  | 1167194.5063 | 383.8193
Waste Costs | 10% of the overall build cost |  | 972662.0886 | 319.8494
Maintinance Costs | 5% of the overall build cost |  | 48633.1044 | 15.9925
Whole Life Costing | 10% of the overall cost |  | 972662.0886 | 319.8494
|  |  | 2686979.0198 | 883.584
Base cost estimate A + B (sub total C) |  |  | 22657617.6705 | 7450.7128
Group element 13
| Design Contingency | Risk allowance @ 2.5% | 566440.4418 | 481474.3755
| Construction Risk | Risk allowance @ 2.5% | 566440.4418 | 481474.3755
| Employers Change Risk | Risk allowance @ 2.50% | 566440.4418 | 481474.3755
| Other Mis. Risk | Risk allowance @ 2.5% | 566440.4418 | 481474.3755
Total Risk allowances (sub total D) |  |  | 2265761.7671 | 1637012.8767
Total Construction Cost (C + D) |  |  | 24923379.4376 | 1644463.5895

## NRM1 CP template
Feasibility Cost Plan
NRM 1 phaseologies
|  | Estimate Cost Plan | Jayne Peirson, School of Fashion, Art and Design
|  |  | Forecasted 2024 Q1 TPI |  |  | 2.22
|  |  | Wales Location Factor |  |  | 0.85
Ref. |  | Element | Timesing | Quantity |  | Unit | Rate | Sub-Total | Group-Total
[7 empty] | £ | £ | £
|  | GIFA |  |  | 3041 | m2
0 |  | FACILITATING WORKS | [6 empty] | 1861500
|  | Preliminaries |  |  | 3041 | GIFA
|  | to include managment Cost, site establishment, site supervision & Contingency |  |  |  |  | 500 | 1520500
Temporary Works
|  | Provisional Sum |  |  | 88 | wks | 2000 | 176000
278 Works
|  | Access Road to site |  |  | 50 | m | 1500 | 75000
|  | Services |  |  |  | m
|  | Mains Electrical and Gas Services |  |  | 200 |  | 300 | 60000
|  | Water mains & Domestic cold water system |  |  | 200 |  | 150 | 30000
1 | 1 | SUBSTRUCTURE | [6 empty] | 964885.6935
1.1 |  | Foundations
|  | 'Excavation to form levels |  |  | item |  | 40000 | 40000
|  | Excavate and disposal to formation level |  |  | item |  | 50000 | 50000
|  | Plain strip foundations to ground-floor external walls, including concrete, brickwork, DPC etc |  |  | 1013.6667 | m2 | 300 | 304100
|  | Plain strip foundations to ground-floor internal walls, including concrete, brickwork, DPC etc |  |  | 180 | m | 270 | 48600
|  | Ground-floor slab; assumed 225 mm deep beam and block floor; structural screed; damp-proof membrane; insulation |  |  | 3041 | m2 | 150 | 456150
|  | Allowance for groundfloor steel work for curtain wall system |  |  |  | item | 66035.6935 | 66035.6935 | To front Elevation
2 |  | SUPERSTRUCTURE | [6 empty] | 2699457
2.1 |  | Frame
|  | Structural timber frame |  |  | 750 | m2 | 140 | 105000
|  | Cavity wall; facing brick outer skin; insulation; plasterboard on stud inner skin; emulsion (U-value = 0.30 W/m2K) machine-made facings; PC £550.00/1000 |  |  | 600 | m2 | 210 | 126000
|  | Cavity wall construction, timber cladding system, insulation, 100 mm medium-density load-bearing blockwork inner leaf |  |  | 1640 | m2 | 330 | 541200
2.2 |  | Upper Floors
|  | 200 mm in situ reinforced concrete upper floors |  |  | 1747 | m2 | 115 | 200905
2.3 |  | Roof
Landscaped roofs Polyester-based elastomeric bitumen waterproofing and vapour equalization layer, copper lined bitumen membrane root barrier and waterproofing layer, separation and slip layers, protection layer, 50 mm thick drainage board, filter fleece, insulation board, Sedum vegetation blanket
|  | extensive (low maintenance – herbs, grasses, mosses and drought tolerant succulents such as Sedum) |  |  | 3041 | m2 | 200 | 608200
|  | 2.3.5 Rooflights/Patent Glazing and Glazed Roofs Rooflights individual polycarbonate rooflights; rectangular; fixed light |  |  | 120 | m2 | 60 | 7200
|  | Extra over allowance for green roof coverings to podium roof |  |  |  | item | 50000 | 50000
2.5 |  | Stairs & Ramps
|  | Internal steel staircase and balustrade with concrete finish for main staircase. |  |  |  | item | 34000 | 34000
[6 empty] | item | 2650 | 2650
|  | Staircase; high quality finishes; stainless steel and glass balustrades; plastered and decorated soffit 3.00 m rise; dogleg |  |  | 4 | nr | 40570.5 | 162282
|  | plus or minus for each 300 mm variation in storey height |  |  | 4 | nr | 2500 | 10000
2.6 |  | Windows & External Doors
2.61 |  | Windows
|  | Curtain walling with powder coated aluminium frame |  |  | 300 | m2 | 800 | 240000
|  | Aluminium triple glazed windows |  |  | 550 | m2 | 400 | 220000
2.62 |  | External Doors
|  | Aluminium external double doorsets |  |  | 9 | nr | 2700 | 24300
|  | 'Allowance for canopies to entrances |  |  | 1 | nr | 11500 | 11500
2.7 |  | Internal Walls & External Walls
2.71 |  | Sound reducing board and timber stud partitions; generally 2 layers of board each side; various levels of fire and sound insulations; part glazed as appropriate: |  |  | 2881 | m2 | 80 | 230480 | Deduction for external walls, included in 2.1 Frame
2.71.2 |  | Allow for column boxing |  |  |  | item | 48000 | 48000
|  | Allowance for fire protection through penetrations |  |  |  | item | 23000 | 23000
2.8 |  | Internal Doors and Screens
2.8.1 |  | Internal Doors The following rates include for the supply and hang of doors, complete with all frames, architrave, typical medium standard ironmongery set and appropriate finish
Fire doors Standard fire doors; cellular core; softwood lining; softwood architrave; aluminuim ironmongery (lockable, self-closure); painting or polishing;
|  | single leaf; Oak veneered; 30 min fire resistance; polished |  |  | 11 | item | 610 | 6710
|  | double leaf; Oak veneered; 30 min fire resistance; polished |  |  | 34 | item | 1400 | 47600
|  | 'maintenance/plant room door; lockable; fire-rated |  |  | 1 | item | 430 | 430
3 |  | INTENAL FINISHES | [6 empty] | 528711.96
|  | Finish to walls; Vinyl matt emulsion to all floors. |  |  |  | m2
|  | Painting to plasterboard surfaces, 1 mist coat and 2 top coats |  |  | 4212 | m2 | 12.01 | 50586.12
3.2 |  | Floor Finishes
|  | Entrance mats and matwells |  |  | 2 | nr | 6446.92 | 12893.84 | pro rata
|  | Self-levelling screed |  |  | 3041 | m2 | 11 | 33451
|  | Vinyl sheet flooring |  |  | 2441 | m2 | 41 | 100081
|  | Heavy duty vinyl to circulation areas, including |  |  | 600 | m2 | 46 | 27600
3.3 |  | Ceilings
3.3.1 |  | Suspended perforated metal tiled ceiling |  |  | 3041 | m2 | 100 | 304100
4 |  | FITTINGS AND FURNISHINGS | [6 empty] | 980000
4.1 |  | General fittings, furnishings and equipment
4.1.1 |  | Allowance for miscellaneous fixtures and fittings, reception desk, kitchenettes, copy stations, whiteboards etc |  |  |  | item | 200000 | 200000 | Prov Sum
|  | studio/workshop – less than 500 seats( Theatre) |  |  |  | item | 50000 | 50000 | Prov Sum
|  | Specialist Installations- light Sculpture |  |  |  | item | 100000 | 100000 | Prov Sum
4.1.2 |  | Blinds |  |  |  | item | 30000 | 30000 | prov Sum
4.1.3 |  | Audio visual installation, to lecture theatre, meeting rooms, communal spaces |  |  |  | item | 100000 | 100000 | prov Sum
4.1.4 |  | Allowance for signage, statutory, directional and external building signage |  |  |  | item | 300000 | 300000 | prov Sum
|  | Works of Art |  |  |  | item | 30000 | 30000 | prov sum
4.1.5 |  | Non mechanical and electrical equipment. |  |  |  | item | 100000 | 100000 | prov Sum
|  | Specialist mechanical and electrical equipment- workshops, kilns etc |  |  |  | item | 50000 | 50000 | prov sum
4.1.6 |  | Internal planting |  |  |  | item | 20000 | 20000 | prov Sum
5 |  | SERVICES | [6 empty] | 2273241.947
5.1 |  | Sanitary installations
5.1..1 |  | WC sanitary ware and cubicles performing arts building (medium specification) |  |  | 90 | m2 | 21.5 | 1935
Hand dryers
|  | Disabled WC suite including all sanitary and fittings |  |  | 3 | nr | 440 | 1320
|  | Equipment for shower rooms; including disabled person equipment |  |  | 3 | nr | 2500 | 7500
|  | LTHW underfloor heating |  |  | 3041 | m2 | 43 | 130763
5.2 |  | Services Equipment
5.2.1 |  | Waste, soil and vent installation; uPVC pipework and fittings |  |  | 3041 | m2 | 25 | 76025
|  | Hot and cold water supply to WCs |  |  | 9 | nr | 825 | 7425
5.3 |  | Disposal Installations
|  | Rainwater disposal installation including gullies and downpipes |  |  | 3041 | m2 | 3 | 9123
|  | Rainwater installation |  |  | 3041 | m2 | 4 | 12164
5.4 |  | Water installations
5.4.1 |  | Incoming mains and domestic cold water system included in facilitating works
5.5 |  | Heat source
5.5.1 |  | Air handling units, chillers; ductwork, pipework, insulation |  |  | 3041 | m2 | 75 | 228075
|  | Toilet extract ventilation |  |  |  | item | 7602.5 | 7602.5
|  | Cooling and ventilation installations to common areas |  |  |  | item | 10136.6667 | 10136.6667 | pro rata
|  | Ground source heat pump installation, including boreholes, pipework and all associated plant |  |  |  | item | 204576.3636 | 204576.3636 | Pro rata
5.6 |  | Space Heating and air conditioning
5.6.1. |  | Chilled water system including air cooled chillers, plantroom installation, distribution pipework, fan coil units and chilled beams |  |  | 3041 | m2 | 120 | 364920
|  | DX cooling to IT rooms |  |  |  | item | 29142.9167 | 29142.9167 | pro rata
5.7 |  | Ventilation Installations
5.7.1 |  | Ventilation extraction to toilet areas |  |  |  | item | 8017.1818 | 8017.1818 | pro rata
5.8 |  | Electrical installations
Mains incoming included in facilitating works
|  | Photovoltaic installation including inverters |  |  |  | item | 48379.5455 | 48379.5455 | pro rata
|  | Power & Data distribution Installations |  |  | 3041 | m2 | 45 | 136845
|  | Allowance for external lighting |  |  |  | item | £40000,00 | £40000,00
5.1 |  | Lift and conveyor installations
5.10.1 |  | Passenger lift |  |  | 2 | nr | 145000 | 290000
5.11 |  | Fire and lighting protection
5.11.1 |  | Dry riser installation |  |  |  | item | 6358.4545 | 6358.4545 | pro rata
|  | Lightning protection |  |  | 3041 | m2 | 2 | 6082
5.12 |  | Communications, Security and Control Systems
5.12.1 |  | Fire alarm and detection system |  |  | 3041 | m2 | 23 | 69943
|  | Data installation, category 6 wiring |  |  | 3041 | m2 | 35 | 106435
|  | Allowance for disabled induction loops, disabled refuge and alarm system |  |  |  | item | 4837.9545 | 4837.9545 | Pro rata
|  | Security system; access control |  |  |  | item | 40085.9091 | 40085.9091 | pro rata
|  | Security system; intruder alarm system |  |  | 3041 | m2 | 4 | 12164
|  | Security system; CCTV system |  |  |  | item | 6358.4545 | 6358.4545 | pro rata
|  | Building management system |  |  | 3041 | m2 | 130 | 395330
5.13 |  | Specialist installations
5.13.1 |  | Allowance for process chilled water system, complete with distribution pipework |  |  | 3041 | m2 | 17 | 51697
8 |  | EXTERNAL WORKS | [6 empty] | 418824.2857
8.1 |  | Hard and soft landscaping | [6 empty] | Prov Sum
|  | Grassed/planted areas |  |  | 50 | m2 | 11 | 550
|  | Car parking and access road |  |  | 150 | m2 | 50 | 7500
|  | Standard kerbs |  |  | 300 | m2 | 24 | 7200
|  | Road markings |  |  | 50 | Item | 1911.4857 | 95574.2857 | pro rata
|  | Paving to pedestrian areas |  |  | 1000 |  | 39 | 39000
|  | Stainless steel bollards |  |  | 50 |  | 280 | 14000
|  | Perimeter fencing 2.4 m high |  |  | 100 |  | 50 | 5000
8.3.2 |  | 8.3.2 External Plantin |  |  |  | item | 50000 | 50000 | Prov sum
Trees
|  | Contingency fund |  |  |  | item |  | 200000
9 |  | MAIN CONTRACTOR'S PRELIMINARIES | [6 empty] | 9726620.8862
|  | Testing and commissioning |  |  | item |  | 1786.5875 | 1786.5875 | 1786.5875
0HP
|  | 12 % of the overall build cost |  |  | 12 | % |  | 1167194.5063
|  | Waste Costs |  |  | 10 | % |  | 972662.0886
10% of the overall build cost
Maintinance Costs
|  | 5% of the overall build cost |  |  | 5 | % |  | 48633.1044
Whole Life Costing
|  | 10% of the overall cost |  |  | 10 | % |  | 972662.0886
3162938.3755
[8 empty] | Total to 'Summary | 12889559.2617

## Forecast
Forecast Cash Flow
*Excludes Maintanence and LLC costing
*5% rentention not included, to be added
|  | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 |  | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2025
Item Description | Total Amount Due | Jan-March | April-June | July-Sept | Oct-Dec |  | Jan-March | April-June | July-Sept | Oct-Dec | Total
FACILITATING WORKS | 1861500 | 465375 | 465375 | 465375 | 116343.75 |  | 58171.875 | 29085.9375 | 261773.44 |  | 1861500.0025
SUBSTRUCTURE | 964885.6935 | 321628.5645 | 643257.129 | 0 | 0 |  | 0 | 0 | 0 |  | 964885.6935
SUPERSTRUCTURE | 2699457 | 0 | 0 | 674864.25 | 1349728.5 |  | 674864.25 | 0 | 0 |  | 2699457
INTENAL FINISHES | 528711.96 | 0 | 0 | 0 | 66088.995 |  | 88118.66 | 132177.99 | 242326.315 |  | 528711.96
FITTINGS AND FURNISHINGS | 980000 | 0 | 0 | 0 | 122500 |  | 163333.3333 | 490000 | 204166.6667 |  | 980000
SERVICES | 2273241.947 | 284155.2434 | 378873.6578 | 0 | 0 |  | 568310.4867 | 1041902.559 |  |  | 2273241.947
EXTERNAL WORKS | 418824.2857 |  | 0 | 0 | 0 |  | 209412.1429 | 69804.0476 | 139608.0952 |  | 418824.2857
MAIN CONTRACTORS PRELIMINARIES | 3162938.3755 | 451848.3394 | 451848.3394 | 451848.3394 | 451848.3394 | 64549.7628 | 451848.3394 | 451848.3394 | 451848.3394 | 451848.3394 | 3162938.3755
PROJECT CONSTRAINTS | 355640 | 50805.7143 | 50805.7143 | 50805.7143 | 50805.7143 |  | 50805.7143 | 50805.7143 | 50805.7143 |  | 355640
RISK ALLOWANCE | 2265761.7671 | 323680.2524 | 323680.2524 | 323680.2524 | 323680.2524 |  | 323680.2524 | 323680.2524 | 323680.2524 |  | 2265761.7671
0HP | 1167194.5063 | 166742.0723 | 166742.0723 | 166742.0723 | 166742.0723 |  | 166742.0723 | 166742.0723 | 166742.0723 |  | 1167194.5063
WASTE COST | 972662.0886 | 138951.7269 | 138951.7269 | 138951.7269 | 138951.7269 |  | 138951.7269 | 138951.7269 | 138951.7269 |  | 972662.0886
| 17650817.6237 | 2203186.9132 | 2619533.8922 | 2272267.3554 | 2786689.3504 | 64549.7628 | 2894238.8533 | 2894998.6395 | 1979902.6223 | 451848.3394 | 17650817.6262
Monthly Contributions
Arts Council Contribution @15% | 2647622.6436 | 330478.037 | 392930.0838 | 340840.1033 | 418003.4026 | 9682.4644 | 434135.828 | 434249.7959 | 296985.3933 | 67777.2509 | 2647622.6439
Jayne Pierson Contribution @5% | 882540.8812 | 110159.3457 | 130976.6946 | 113613.3678 | 139334.4675 | 3227.4881 | 144711.9427 | 144749.932 | 98995.1311 | 22592.417 | 882540.8813
Total Monthly Payments | 14120654.099 | 1762549.5306 | 2095627.1138 | 1817813.8843 | 2229351.4803 | 51639.8102 | 2315391.0826 | 2315998.9116 | 1583922.0978 | 361478.6715 | 14120654.101
Monthly Estimated Interim Payments | Totals | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments | x4 Monthly Payments
Clients Contribution Estimated Interim Payments | 17650817.6237 | 550796.7283 | 654883.4731 | 568066.8388 | 696672.3376 | 16137.4407 | 723559.7133 | 723749.6599 | 494975.6556 | 112962.0848 | 4412704.4066
Arts Council Contribution @15% | 2647622.6436 | 82619.5092 | 98232.521 | 85210.0258 | 104500.8506 | 2420.6161 | 108533.957 | 108562.449 | 74246.3483 | 16944.3127 | 661905.661
Jayne Pierson Contribution @5% | 882540.8812 | 27539.8364 | 32744.1737 | 28403.3419 | 34833.6169 | 806.872 | 36177.9857 | 36187.483 | 24748.7828 | 5648.1042 | 220635.2203
| 21180981.1485 | 660956.074 | 785860.1677 | 681680.2066 | 836006.8051 | 19364.9288 | 868271.656 | 868499.5919 | 593970.7867 | 135554.5018 | 5295245.2879
5% | 10590.4906 | 330.478 | 392.9301 | 340.8401 | 418.0034 | 9.6825 | 434.1358 | 434.2498 | 296.9854 | 67.7773 | 2647.6226
Minus 5% Retention | 21170390.6579 | 660625.5959 | 785467.2376 | 681339.3665 | 835588.8017 | 19355.2464 | 867837.5202 | 868065.3421 | 593673.8013 | 135486.7246 | 5292597.6652

## Material Costing Comparisons
| OPTION 1 (Concept Design) |  |  |  | OPTION 2 |  |  |  | OPTION 3
Item | Material Description | Qty/m2 | Cost/ unit | Total | Material Description | Qty | Cost/ unit | Total | Material Description | Qty | Cost/ unit | Total
FOUNDATION | Strip Foundations with200mm concrete slab | 4021 | 300 | 1206300 | Piled foundations; RC ground bearing slab 200mm | 4021 | 490 | 1970290 | Concrete pad foundations | 4021 | 500 | 2010500
FRAME | Timber | 2240 | 140 | 313600 | Steel frame | 2240 | 490 | 1097600 | Concrete frame 300 mm × 600 mm | 2240 | 235 | 526400
INTERNAL WALLS | Timber Stud Partion | 2881 | 80 | 230480 | Metal stud partion | 2881 | 85 | 244885 | Concrete partitions Reinforced concrete walls; C25 strength150mm thick | 2881 | 200 | 576200
ROOF | Landscaped DPM | 4021 | 200 | 804200 | Kalzip embossed aluminium standing seam roof | 4021 | 100 | 402100 | Reinforced concrete roof slab; 300 mm thick | 4021 | 180 | 723780
|  |  | Total | 2554580 |  |  |  | 3714875 |  |  |  | 3836880