Kirsty Cook | 2203229 | Deborah Jenkins | BMTP5021

Live Music Event | The Bunkhouse, Swansea | Stone Deaf, Coda, The False Idles

Introduction

The event was a ‘Live Music Event’. The definition of an event is ‘an occurrence that has a time element, two or more participants and is planned with a clear definition of what is going to happen’ (Dolasinski 2021). It was a night filled of Indie Rock local bands. Stone Deaf, Coda and The False Idles. The night consisted of two, 30-minute performances from Coda and The False Idles and 45 minutes from Stone Deaf.

Aims and Objectives

There are three main aims that was covered and that we wanted to achieve while putting on a live event. These included:

Entertainment: to provide an enjoyable experience for everyone who came to support. By picking acts to suit the type of audience that The Bunkhouse help promote. The Bunkhouse was the venue that got picked as it’s well known in Swansea and the owner Jordan McGuire had many connections to help in the search of finding bands to play. The capacity of the Bunkhouse is 235 people. The Bunkhouse also has a solid social media presence and high-quality sound and production values that helped to keep everything as professional as possible.

Promotion of artists: to make sure everything was well promoted for the chance to sell the greatest number of tickets possible to maximise our profits and provide a platform for up-and-coming artists to gain exposure and gives people an opportunity to network.

Environmentally sustainable: We as a group decided to minimise the events environmental footprint by not printing out posters and using QR codes instead of physical tickets.

Market Research/Plan

We first got in contact with Jordan McGuire from bunkhouse to discuss the event. The meeting was Friday the 9th of February 2024, and we asked these questions:

- Whether security was provided?

- What the cut off point for play music in the establishment

- Bartender and Tech people whether they were provided?

Market Research was essential for understanding the target audience, these things include, looking at different competitors in the field, looking at the demand a live event has not only in general but in Swansea.

Once we defined our objectives. We had to understand the audience demographics and pick bands that would link well with the type of vibe we were going for. This was indie rock. We researched venues and look at different bands. We knew our target audience was 18–30-year-olds. We shocked to discover that we also had people aged 40-60 there too, however, when speaking to them we soon discovered that some of them where family members of the bands and locals that are there every week.

Advertising Poster

When deciding ticket prices, we needed to be cheap enough that people would attend by also enough money to give money to the bands. With Jordan’s guidance we set on £5 online and £6 on the door. Next, we had to decide on what date we wanted to do it. We knew for definite that we wanted to do it on a Wednesday with that being student night it would draw a lot of attention to our event.

Running order

The running order of the night was:

- 5pm- Bands arriving, setting up and soundcheck

- 6pm- Doors opening and the bar being open for ‘welcome drinks’

- 8pm-8:30 The False Idles

- 8:45pm-9:15 CODA

- 9:30- end Stone Deaf

Gantt Chart

| Task names | Who was Involved | Start date | Final date to complete task | Completed? |
| --- | --- | --- | --- | --- |
| Book a venue | Grace, Kirsty, Sav, Ben | 29/1/24 | 9/2/24 | Complete |
| Marketing | Sav and Grace | 12/2/24 | 26/02/24 | Complete |
| Planning | Grace, Sav, Kirsty, Ben | 29/1/24 | 1/03/24 | Complete |
| Finances | ALL | 30/1/24 | 9/2/24 | Complete |
| Team Communications | Grace, Kirsty, Ben, Sav | 29/1/24 | 20/03/24 | Complete |
| Posting on social media | Kirsty and Grace | 29/1/24 | 20/3/24 | Complete |
| Follow up | Grace, Sav, Kirsty, Ben | 29/1/24 | 20/03/24 | Complete |

Risk Management Plan

| Event Name: | Live music event, STONE DEAF, CODA, THE FALSE IDLES | Date: | 20/03/24 | Venue: | Bunkhouse Swansea |
| --- | --- | --- | --- | --- | --- |

| (1) Activity / Area of Concern ie: what is taking place as part of the event? | (2) Hazards Identified ie: what can cause harm? | (3) Persons at Risk ie: who could be harmed by the hazard? | (4) Current Risk Factor (high, medium or low) ie: determine the level of risk | (5) Actions to be Taken to Minimize each Risk ie: what action can you take to lower the level of risk | (6) New Risk Factor (high, medium or low) ie: risk factor after action taken to minimise the risk |
| --- | --- | --- | --- | --- | --- |
| Live music event in a small venue | Crowd Management | -Public Venue staff (including security) -Performers Neighbouring residents and businesses | Crowd Management: Medium | -Implement and communicate venue capacity limits -Ensure clear and unobstructed exit routes -Regularly inspect and maintain flooring to prevent slips | Crowed management: Low |
| Emergency evacuation procedure | Fire; Terrorist attack; Storm | -Members of the public -staff members | High | -Assembly point will be to evacuate into the street through the multiple fire exits. -Information boards for public use such as fire exit signs and lighting -Emergency services will be informed in case of an incident by a member of staff on duty | Emergency evacuation procedure: Medium |
| First Aid | -Minor injuries -Heat stroke, -general accidents -Major incidents | -Public Venue staff (including security) -Performers Neighbouring residents and businesses | Medium | -Provide adequate First Aid cover. Number of qualified First Aiders to be present for the event=2 | First aid: Low |
| Electrical Equipment | Electrocution -Death -Shock and Burns | -Attendees (patrons) -Venue staff Performers Neighbouring residents and businesses | Electrical Equipment: Medium | -Regularly inspect and maintain all electrical systems -Provide staff training on identifying and reporting electrical issues | Electrical Equipment: Low |
| Toilet Provision | Not enough toilets | Members of the public | Low | -Ensure enough toilets present at site for numbers attending -Use public toilets on site. | Not enough toilets: Low |
| Noice Levels | Annoyance to locals in the area | -Attendees (patrons) Venue staff -Performers Neighbouring residents and businesses | Noise Levels: Medium | - Implement noise level monitoring and control measures -Install soundproofing measures within the venue -Finish live music at 11pm following guidelines. | Noise level-Low |
| Risk of fire | Burn or smoke injuries | -Members of the public especially people with disabilities -Staff Event participants Contractors | Medium | - Fire Detection and Suppression: - Emergency Preparedness: - Smoking Policies: - Lighting and Visibility: - Communication and Contacts - Regular Procedure Review: | Risk of fire: Low |
| Security | -Alcohol -18 years plus -tickets are mandatory | -Attendees (patrons) - Venue staff (including security) -Performers -Neighbouring residents and businesses | Medium | -Employ trained security personnel - Implement a comprehensive security plan - Monitor and control alcohol consumption to reduce the likelihood of altercations -Security cameras in place | Security levels: Low |
| Alcohol Service | -Glass bottles -Unresponsible use of alcohol -Licensing of products -Security measures -Capacity levels | -Attendees (patrons) -Venue staff (including bartenders) -Neighbouring residents and businesses | Alcohol Service: Medium | - Enforce responsible alcohol service policies - Train staff to identify and manage intoxicated patrons - Implement ID checks and limit the sale of alcohol to appropriate hours | Alcohol service: Low |
| Litter | Litter or other debris generated by event | (Complaints from) Members of the public Parks Division staff | Medium | -Ensure that a litter pick is pre-arranged and undertaken by the venue -Clean the venue during the event to keep a good level of hygiene | Litter levels: Low |
| Crowd management | Pinch points; Over-crowding; Potential conflict re-entry to event | -Members of the public -Senior citizens -disabled people | High | -PA system in place. -Appropriate number of identifiable staff on site, with radio system. Staff to be fully briefed prior to event. -Limit to ticket sales | Medium |
| Cash collectors | Risk of theft / injury to cash collectors | Competitors / members of the public | Medium | -All cash collection points are well known by security in case of a theft or incident -Members of staff will report an issue to the police immediately -Security cameras are in place -Staff are fully trained | Low |

I hereby confirm that I will fully comply with this Event Risk Assessment and agree to obtain all the necessary permission and licences required.

Name of person completing Risk Assessment (printed)

Ben Williams, Kirsty Cook, Grace Davies, Savannah Kitching

Organisation: University of Wales Trinity Saint Davids.

Signature: Ben WIlliams, Kirsty Cook, Grace Davies, Savannah Kitching

Date: 04/03/2024

Problems that occurred:

The event was a success. According to (Nordahl-Pedersen 2023) factors that contribute to a successful event project is having “common goals, good information, communication and interaction among project members” which we did have. However, there were a few problems that occurred. Firstly, The False Idles didn't have their amplifier. So, after asking around we concluded that we would ask on of the other bands. They were nice enough to lend there's to the band. Secondly, all the drink that were purchased at the venue were in plastic cups. However, towards the end of the set's drinks all the plastic cups were being used so glasses were being used and there ended up being smashed, so we had to clear that up. There was an incident with a local man that comes in every weekend however, when he has a bit too much to drink, he gets a bit rowdy. So, we had to keep an eye on them and if things go out of hand, we had to make security aware and lastly, we had trouble with one of the bands smoking weed in the green room so had to escort them outside.

Financial

With deciding to sell our tickets for £5 each we sold 54 tickets, and, on the door, we increase or sales by £1 and sold 21 tickets. With a grand total of 75 tickets sold we made a profit of £396. With our outgoing being free this was an opportunity for local bands, however all the money we made from this was given to the bands and we spilt as followed.

The False Idles: £100

CODA: £100

Stone Deaf: £196

We decided to give stone deaf more as they were the headline act and they played for the longest out of them all.

We also offered all bands a rider too. This is where they get to choose things they want in their green room. On this rider where things like water, beer and ice. A rider is important as it ‘helps when communicating with event organisers and if you can facilitate what the artists might need it will bring out their best performance for you’ (Music Gateway 2023) However, we had a slight problem were some of the members of The False Idles were underage so couldn't be served this.

Pictures from the event

Bibliography

Dolaskinski, MJ (2021) Defining the Field of Events. [Journals] Available at: https://journals.sagepub.com/doi/abs/10.1177/1096348020978266 (Accessed 22 March 2024)

Music Gateway (2023) What are artist riders and why do you need them? Available at: https://www.musicgateway.com/blog/music-industry/what-are-artist-rider-and-why-do-you-need-them (Accessed 21 March 2024)

Nordahl-Pedersen (2023) What factors contributes to a success in an events project? [Article] Available at: https://www.sciencedirect.com/science/article/pii/S1877050923005070 (Accessed 20 March 2024)