## Critical resources
Task Name | Work | Duration | Start | Finish
Baseline 06.01 | 119,728 hrs | 550 days | Mon 16/09/24 | Fri 23/10/26
SA1 Development | 119,728 hrs | 550 days | Mon 16/09/24 | Fri 23/10/26
Milestones | 0 hrs | 550 days | Mon 16/09/24 | Fri 23/10/26
Site resources for project duration | 17,600 hrs | 550 days | Mon 16/09/24 | Fri 23/10/26
Site preparation | 2,064 hrs | 71 days | Mon 16/09/24 | Mon 23/12/24
Clear site | 160 hrs | 10 days | Mon 16/09/24 | Fri 27/09/24
r Groundworker 1 | 80 hrs |  | Mon 16/09/24 | Fri 27/09/24
r Groundworker 2 | 80 hrs |  | Mon 16/09/24 | Fri 27/09/24
p Excavator 1 per day | 1 |  | Mon 16/09/24 | Fri 27/09/24
p Excavator 2 per day | 1 |  | Mon 16/09/24 | Fri 27/09/24
Install Site fencing | 120 hrs | 5 days | Mon 30/09/24 | Fri 04/10/24
r Groundworker 1 | 40 hrs |  | Mon 30/09/24 | Fri 04/10/24
r Groundworker 2 | 40 hrs |  | Mon 30/09/24 | Fri 04/10/24
r Groundworker 3 | 40 hrs |  | Mon 30/09/24 | Fri 04/10/24
Level site | 640 hrs | 20 days | Mon 07/10/24 | Fri 01/11/24
r Groundworker 1 | 160 hrs |  | Mon 07/10/24 | Fri 01/11/24
r Groundworker 2 | 160 hrs |  | Mon 07/10/24 | Fri 01/11/24
r Groundworker 3 | 160 hrs |  | Mon 07/10/24 | Fri 01/11/24
r Groundworker 4 | 160 hrs |  | Mon 07/10/24 | Fri 01/11/24
p Excavator 1 per day | 1 |  | Mon 07/10/24 | Fri 01/11/24
p Excavator 2 per day | 1 |  | Mon 07/10/24 | Fri 01/11/24
p Dumper truck 3t day | 1 |  | Mon 07/10/24 | Fri 01/11/24
Install plinths for cabins | 48 hrs | 2 days | Mon 04/11/24 | Tue 05/11/24
r Groundworker 1 | 16 hrs |  | Mon 04/11/24 | Tue 05/11/24
r Groundworker 2 | 16 hrs |  | Mon 04/11/24 | Tue 05/11/24
r Carpenter 1 | 16 hrs |  | Mon 04/11/24 | Tue 05/11/24
p Excavator 1 per day | 1 |  | Mon 04/11/24 | Tue 05/11/24
p Excavator 2 per day | 1 |  | Mon 04/11/24 | Tue 05/11/24
p Dumper truck 3t day | 1 |  | Mon 04/11/24 | Tue 05/11/24
m Concrete m3 | 5 |  | Mon 04/11/24 | Tue 05/11/24
m Timber Pine m2 | 3 |  | Mon 04/11/24 | Tue 05/11/24
Install generator and temporary utilities | 40 hrs | 1 day | Wed 06/11/24 | Wed 06/11/24
r Electrician 1 | 8 hrs |  | Wed 06/11/24 | Wed 06/11/24
r Groundworker 1 | 8 hrs |  | Wed 06/11/24 | Wed 06/11/24
r Groundworker 2 | 8 hrs |  | Wed 06/11/24 | Wed 06/11/24
r Groundworker 3 | 8 hrs |  | Wed 06/11/24 | Wed 06/11/24
r Groundworker 4 | 8 hrs |  | Wed 06/11/24 | Wed 06/11/24
p Excavator 1 per day | 1 |  | Wed 06/11/24 | Wed 06/11/24
p Excavator 2 per day | 1 |  | Wed 06/11/24 | Wed 06/11/24
p Hiab 35t day | 1 |  | Wed 06/11/24 | Wed 06/11/24
p Dumper truck 3t day | 1 |  | Wed 06/11/24 | Wed 06/11/24
Install site skips | 32 hrs | 1 day | Mon 11/11/24 | Mon 11/11/24
r Groundworker 1 | 8 hrs |  | Mon 11/11/24 | Mon 11/11/24
r Groundworker 2 | 8 hrs |  | Mon 11/11/24 | Mon 11/11/24
r Groundworker 3 | 8 hrs |  | Mon 11/11/24 | Mon 11/11/24
r Groundworker 4 | 8 hrs |  | Mon 11/11/24 | Mon 11/11/24
p Hiab 35t day | 1 |  | Mon 11/11/24 | Mon 11/11/24
Complete CFA piling for all buildings | 960 hrs | 30 days | Tue 12/11/24 | Mon 23/12/24
r Groundworker 1 | 240 hrs |  | Tue 12/11/24 | Mon 23/12/24
r Groundworker 2 | 240 hrs |  | Tue 12/11/24 | Mon 23/12/24
r Groundworker 3 | 240 hrs |  | Tue 12/11/24 | Mon 23/12/24
r Groundworker 4 | 240 hrs |  | Tue 12/11/24 | Mon 23/12/24
p CFA Piling rig | 1 |  | Tue 12/11/24 | Mon 23/12/24
m Concrete m3 | 20 |  | Tue 12/11/24 | Mon 23/12/24
Site clearance after construction | 168 hrs | 8 days | Wed 14/10/26 | Fri 23/10/26
Remove welfare facilities | 16 hrs | 1 day | Wed 14/10/26 | Wed 14/10/26
r Groundworker 1 | 8 hrs |  | Wed 14/10/26 | Wed 14/10/26
r Groundworker 2 | 8 hrs |  | Wed 14/10/26 | Wed 14/10/26
p Excavator 1 per day | 1 |  | Wed 14/10/26 | Wed 14/10/26
p Excavator 2 per day | 1 |  | Wed 14/10/26 | Wed 14/10/26
p Hiab 35t day | 1 |  | Wed 14/10/26 | Wed 14/10/26
p Dumper truck 3t day | 1 |  | Wed 14/10/26 | Wed 14/10/26
Remove site office | 16 hrs | 1 day | Wed 14/10/26 | Wed 14/10/26
r Groundworker 3 | 8 hrs |  | Wed 14/10/26 | Wed 14/10/26
r Groundworker 4 | 8 hrs |  | Wed 14/10/26 | Wed 14/10/26
p Hiab 35t day | 1 |  | Wed 14/10/26 | Wed 14/10/26
Remove generator and temporary utilities | 24 hrs | 1 day | Wed 14/10/26 | Wed 14/10/26
r Electrician 1 | 8 hrs |  | Wed 14/10/26 | Wed 14/10/26
r Groundworker 5 | 8 hrs |  | Wed 14/10/26 | Wed 14/10/26
r Groundworker 6 | 8 hrs |  | Wed 14/10/26 | Wed 14/10/26
p Excavator 1 per day | 1 |  | Wed 14/10/26 | Wed 14/10/26
p Excavator 2 per day | 1 |  | Wed 14/10/26 | Wed 14/10/26
p Hiab 35t day | 1 |  | Wed 14/10/26 | Wed 14/10/26
p Dumper truck 3t day | 1 |  | Wed 14/10/26 | Wed 14/10/26
Remove temporary plinths | 16 hrs | 1 day | Thu 15/10/26 | Thu 15/10/26
r Groundworker 1 | 8 hrs |  | Thu 15/10/26 | Thu 15/10/26
r Groundworker 2 | 8 hrs |  | Thu 15/10/26 | Thu 15/10/26
p Excavator 1 per day | 1 |  | Thu 15/10/26 | Thu 15/10/26
p Excavator 2 per day | 1 |  | Thu 15/10/26 | Thu 15/10/26
p Dumper truck 3t day | 1 |  | Thu 15/10/26 | Thu 15/10/26
Remove hoarding | 48 hrs | 3 days | Fri 16/10/26 | Tue 20/10/26
r Groundworker 1 | 24 hrs |  | Fri 16/10/26 | Tue 20/10/26
r Groundworker 2 | 24 hrs |  | Fri 16/10/26 | Tue 20/10/26
p Dumper truck 3t day | 1 |  | Fri 16/10/26 | Tue 20/10/26
Remove skips | 16 hrs | 1 day | Wed 21/10/26 | Wed 21/10/26
r Groundworker 1 | 8 hrs |  | Wed 21/10/26 | Wed 21/10/26
r Groundworker 2 | 8 hrs |  | Wed 21/10/26 | Wed 21/10/26
p Hiab 35t day | 1 |  | Wed 21/10/26 | Wed 21/10/26
Landscape facilities area | 32 hrs | 2 days | Thu 22/10/26 | Fri 23/10/26
r Landscaper 1 | 16 hrs |  | Thu 22/10/26 | Fri 23/10/26
r Landscaper 2 | 16 hrs |  | Thu 22/10/26 | Fri 23/10/26
Plots 500 to 508 3 storey x 9 units type 49 | 26,200 hrs | 264 days | Tue 24/12/24 | Fri 26/12/25
500 to 508 Foundations, substructures & structural floors | 5,008 hrs | 143 days | Tue 24/12/24 | Thu 10/07/25
Drainage | 304 hrs | 19 days | Tue 24/12/24 | Fri 17/01/25
Excavate trenches for 500 to 508 | 112 hrs | 7 days | Tue 24/12/24 | Wed 01/01/25
r Groundworker 7 | 56 hrs |  | Tue 24/12/24 | Wed 01/01/25
r Groundworker 8 | 56 hrs |  | Tue 24/12/24 | Wed 01/01/25
p Excavator 1 per day | 7 |  | Tue 24/12/24 | Wed 01/01/25
p Dumper truck 3t day | 7 |  | Tue 24/12/24 | Wed 01/01/25
Lay pipes for 500 to 508 | 112 hrs | 7 days | Thu 02/01/25 | Fri 10/01/25
r Groundworker 7 | 56 hrs |  | Thu 02/01/25 | Fri 10/01/25
r Groundworker 8 | 56 hrs |  | Thu 02/01/25 | Fri 10/01/25
p Telehandler 18m per day | 1 |  | Thu 02/01/25 | Fri 10/01/25
m Drainage materials 10mtr | 10 |  | Thu 02/01/25 | Fri 10/01/25
Backfill trenches 500 to 508 | 80 hrs | 5 days | Mon 13/01/25 | Fri 17/01/25
r Groundworker 7 | 40 hrs |  | Mon 13/01/25 | Fri 17/01/25
r Groundworker 8 | 40 hrs |  | Mon 13/01/25 | Fri 17/01/25
p Excavator 1 per day | 5 |  | Mon 13/01/25 | Fri 17/01/25
p Dumper truck 3t day | 5 |  | Mon 13/01/25 | Fri 17/01/25
Utilities | 1,048 hrs | 59 days | Mon 20/01/25 | Thu 10/04/25
Excavate trenches for cables | 80 hrs | 5 days | Mon 20/01/25 | Fri 24/01/25
r Groundworker 7 | 40 hrs |  | Mon 20/01/25 | Fri 24/01/25
r Groundworker 8 | 40 hrs |  | Mon 20/01/25 | Fri 24/01/25
p Excavator 2 per day | 5 |  | Mon 20/01/25 | Fri 24/01/25
p Dumper truck 3t day | 5 |  | Mon 20/01/25 | Fri 24/01/25
Ground FLR Concrete slab | 696 hrs | 73 days | Mon 20/01/25 | Wed 30/04/25
Lay hardcore base | 96 hrs | 6 days | Mon 20/01/25 | Wed 29/01/25
r Groundworker 1 | 24 hrs |  | Mon 27/01/25 | Wed 29/01/25
r Groundworker 2 | 24 hrs |  | Mon 27/01/25 | Wed 29/01/25
r Groundworker 3 | 24 hrs |  | Mon 27/01/25 | Wed 29/01/25
r Groundworker 4 | 24 hrs |  | Mon 20/01/25 | Wed 22/01/25
p Excavator 1 per day | 6 |  | Mon 20/01/25 | Wed 29/01/25
p roller per day | 6 |  | Mon 20/01/25 | Wed 29/01/25
p Dumper truck 3t day | 6 |  | Mon 20/01/25 | Wed 29/01/25
m Type 1 m3 | 30 |  | Mon 20/01/25 | Wed 29/01/25
Install DPM | 64 hrs | 4 days | Thu 30/01/25 | Fri 14/02/25
r Groundworker 1 | 16 hrs |  | Thu 30/01/25 | Fri 31/01/25
r Groundworker 2 | 16 hrs |  | Thu 13/02/25 | Fri 14/02/25
r Groundworker 3 | 16 hrs |  | Thu 13/02/25 | Fri 14/02/25
r Groundworker 4 | 16 hrs |  | Thu 30/01/25 | Fri 31/01/25
p Telehandler 18m per day | 4 |  | Thu 30/01/25 | Fri 14/02/25
Install Insulation slab | 128 hrs | 4 days | Mon 17/02/25 | Thu 20/02/25
r Groundworker 1 | 32 hrs |  | Mon 17/02/25 | Thu 20/02/25
r Insulation supervisor 1 | 32 hrs |  | Mon 17/02/25 | Thu 20/02/25
r Insulator 1 | 32 hrs |  | Mon 17/02/25 | Thu 20/02/25
r Insulator 2 | 32 hrs |  | Mon 17/02/25 | Thu 20/02/25
p Telehandler 18m per day | 4 |  | Mon 17/02/25 | Thu 20/02/25
m Insulation raft m2 | 30 |  | Mon 17/02/25 | Thu 20/02/25
make and install steel reinforcement cages | 160 hrs | 8 days | Fri 21/02/25 | Thu 06/03/25
r Groundworker 1 | 40 hrs |  | Fri 21/02/25 | Thu 06/03/25
r Groundworker 2 | 40 hrs |  | Fri 21/02/25 | Thu 27/02/25
r Groundworker 3 | 40 hrs |  | Fri 21/02/25 | Thu 27/02/25
r Groundworker 4 | 40 hrs |  | Fri 21/02/25 | Thu 27/02/25
p Telehandler 18m per day | 8 |  | Fri 21/02/25 | Thu 06/03/25
m Rebar T | 100 |  | Fri 21/02/25 | Thu 06/03/25
Construct formwork | 80 hrs | 5 days | Fri 07/03/25 | Thu 13/03/25
r Carpenter 1 | 40 hrs |  | Fri 07/03/25 | Thu 13/03/25
r Carpenter 2 | 40 hrs |  | Fri 07/03/25 | Thu 13/03/25
p Telehandler 18m per day | 1 |  | Fri 07/03/25 | Thu 13/03/25
m Timber Pine m2 | 10 |  | Fri 07/03/25 | Thu 13/03/25
Pour concrete slab 500 to 508 | 32 hrs | 1 day | Fri 14/03/25 | Fri 14/03/25
r Groundworker 1 | 8 hrs |  | Fri 14/03/25 | Fri 14/03/25
r Groundworker 2 | 8 hrs |  | Fri 14/03/25 | Fri 14/03/25
r Groundworker 3 | 8 hrs |  | Fri 14/03/25 | Fri 14/03/25
r Groundworker 4 | 8 hrs |  | Fri 14/03/25 | Fri 14/03/25
m Concrete m3 | 30 |  | Fri 14/03/25 | Fri 14/03/25
Staircase & Stairwell 2 | 560 hrs | 20 days | Tue 25/03/25 | Mon 21/04/25
Erect Ground FLR stairwell 2 scaffolding | 40 hrs | 1 day | Tue 25/03/25 | Tue 25/03/25
r Scaffolding supervisor 1 | 8 hrs |  | Tue 25/03/25 | Tue 25/03/25
r Scaffolder 1 | 8 hrs |  | Tue 25/03/25 | Tue 25/03/25
r Scaffolder 2 | 8 hrs |  | Tue 25/03/25 | Tue 25/03/25
r Scaffolder 3 | 8 hrs |  | Tue 25/03/25 | Tue 25/03/25
r scaffolder 4 | 8 hrs |  | Tue 25/03/25 | Tue 25/03/25
p Scaffolding m2 | 15 |  | Tue 25/03/25 | Tue 25/03/25
Construct Ground FLR Breeze block Stairwell 2 | 120 hrs | 3 days | Fri 28/03/25 | Tue 01/04/25
r Bricklayer supervisor 1 | 24 hrs |  | Fri 28/03/25 | Tue 01/04/25
r Bricklayer supervisor 3 | 24 hrs |  | Fri 28/03/25 | Tue 01/04/25
r Bricklayer 2 | 24 hrs |  | Fri 28/03/25 | Tue 01/04/25
r Bricklayer 3 | 24 hrs |  | Fri 28/03/25 | Tue 01/04/25
r Bricklayer 4 | 24 hrs |  | Fri 28/03/25 | Tue 01/04/25
m Blocks m2 | 40 |  | Fri 28/03/25 | Tue 01/04/25
Erect First FLR scaffolding | 40 hrs | 1 day | Wed 02/04/25 | Wed 02/04/25
r Scaffolding supervisor 1 | 8 hrs |  | Wed 02/04/25 | Wed 02/04/25
r Scaffolder 1 | 8 hrs |  | Wed 02/04/25 | Wed 02/04/25
r Scaffolder 2 | 8 hrs |  | Wed 02/04/25 | Wed 02/04/25
r Scaffolder 3 | 8 hrs |  | Wed 02/04/25 | Wed 02/04/25
r scaffolder 4 | 8 hrs |  | Wed 02/04/25 | Wed 02/04/25
p Scaffolding m2 | 15 |  | Wed 02/04/25 | Wed 02/04/25
Construct First FLR Breeze block Stairwell 2 | 120 hrs | 3 days | Mon 07/04/25 | Wed 09/04/25
r Bricklayer supervisor 1 | 24 hrs |  | Mon 07/04/25 | Wed 09/04/25
r Bricklayer supervisor 3 | 24 hrs |  | Mon 07/04/25 | Wed 09/04/25
r Bricklayer 2 | 24 hrs |  | Mon 07/04/25 | Wed 09/04/25
r Bricklayer 3 | 24 hrs |  | Mon 07/04/25 | Wed 09/04/25
r Bricklayer 4 | 24 hrs |  | Mon 07/04/25 | Wed 09/04/25
m Blocks m2 | 40 |  | Mon 07/04/25 | Wed 09/04/25
Erect Second FLR scaffolding | 40 hrs | 1 day | Thu 10/04/25 | Thu 10/04/25
r Scaffolding supervisor 1 | 8 hrs |  | Thu 10/04/25 | Thu 10/04/25
r Scaffolder 1 | 8 hrs |  | Thu 10/04/25 | Thu 10/04/25
r Scaffolder 2 | 8 hrs |  | Thu 10/04/25 | Thu 10/04/25
r Scaffolder 3 | 8 hrs |  | Thu 10/04/25 | Thu 10/04/25
r scaffolder 4 | 8 hrs |  | Thu 10/04/25 | Thu 10/04/25
p Scaffolding m2 | 15 |  | Thu 10/04/25 | Thu 10/04/25
Construct Second FLR Breeze block stairwell 2 | 120 hrs | 3 days | Tue 15/04/25 | Thu 17/04/25
r Bricklayer supervisor 1 | 24 hrs |  | Tue 15/04/25 | Thu 17/04/25
r Bricklayer supervisor 3 | 24 hrs |  | Tue 15/04/25 | Thu 17/04/25
r Bricklayer 2 | 24 hrs |  | Tue 15/04/25 | Thu 17/04/25
r Bricklayer 3 | 24 hrs |  | Tue 15/04/25 | Thu 17/04/25
r Bricklayer 4 | 24 hrs |  | Tue 15/04/25 | Thu 17/04/25
m Blocks m2 | 40 |  | Tue 15/04/25 | Thu 17/04/25
Dismantle all stairwell 2 scaffolding | 80 hrs | 2 days | Fri 18/04/25 | Mon 21/04/25
r Scaffolding supervisor 1 | 16 hrs |  | Fri 18/04/25 | Mon 21/04/25
r Scaffolder 1 | 16 hrs |  | Fri 18/04/25 | Mon 21/04/25
r Scaffolder 2 | 16 hrs |  | Fri 18/04/25 | Mon 21/04/25
r Scaffolder 3 | 16 hrs |  | Fri 18/04/25 | Mon 21/04/25
r scaffolder 4 | 16 hrs |  | Fri 18/04/25 | Mon 21/04/25
First FLR Structural FLR | 920 hrs | 29 days | Tue 22/04/25 | Fri 30/05/25
Erect scaffold access | 160 hrs | 4 days | Tue 22/04/25 | Fri 25/04/25
r Scaffolding supervisor 1 | 32 hrs |  | Tue 22/04/25 | Fri 25/04/25
r Scaffolder 1 | 32 hrs |  | Tue 22/04/25 | Fri 25/04/25
r Scaffolder 2 | 32 hrs |  | Tue 22/04/25 | Fri 25/04/25
r Scaffolder 3 | 32 hrs |  | Tue 22/04/25 | Fri 25/04/25
r scaffolder 4 | 32 hrs |  | Tue 22/04/25 | Fri 25/04/25
p Scaffolding m2 | 100 |  | Tue 22/04/25 | Fri 25/04/25
Install pre cast concrete beams | 256 hrs | 8 days | Mon 28/04/25 | Wed 07/05/25
r Concrete contract supervisor 1 | 64 hrs |  | Mon 28/04/25 | Wed 07/05/25
r Concrete contract operative 1 | 64 hrs |  | Mon 28/04/25 | Wed 07/05/25
r Concrete contract operative 2 | 64 hrs |  | Mon 28/04/25 | Wed 07/05/25
r Concrete contract operative 3 | 64 hrs |  | Mon 28/04/25 | Wed 07/05/25
p Hiab 35t day | 8 |  | Mon 28/04/25 | Wed 07/05/25
p Crane 100t per day | 8 |  | Mon 28/04/25 | Wed 07/05/25
m Concrete m3 | 50 |  | Mon 28/04/25 | Wed 07/05/25
Install concrete pre tension blocks | 256 hrs | 8 days | Thu 08/05/25 | Mon 19/05/25
r Concrete contract supervisor 1 | 64 hrs |  | Thu 08/05/25 | Mon 19/05/25
r Concrete contract operative 1 | 64 hrs |  | Thu 08/05/25 | Mon 19/05/25
r Concrete contract operative 2 | 64 hrs |  | Thu 08/05/25 | Mon 19/05/25
r Concrete contract operative 3 | 64 hrs |  | Thu 08/05/25 | Mon 19/05/25
p Hiab 35t day | 8 |  | Thu 08/05/25 | Mon 19/05/25
p Crane 100t per day | 8 |  | Thu 08/05/25 | Mon 19/05/25
m Concrete m3 | 50 |  | Thu 08/05/25 | Mon 19/05/25
Dismantle scaffolding access | 120 hrs | 3 days | Tue 20/05/25 | Thu 22/05/25
r Scaffolding supervisor 1 | 24 hrs |  | Tue 20/05/25 | Thu 22/05/25
r Scaffolder 1 | 24 hrs |  | Tue 20/05/25 | Thu 22/05/25
r Scaffolder 2 | 24 hrs |  | Tue 20/05/25 | Thu 22/05/25
r Scaffolder 3 | 24 hrs |  | Tue 20/05/25 | Thu 22/05/25
r scaffolder 4 | 24 hrs |  | Tue 20/05/25 | Thu 22/05/25
Grout gaps | 64 hrs | 2 days | Fri 23/05/25 | Mon 26/05/25
r Concrete contract supervisor 1 | 16 hrs |  | Fri 23/05/25 | Mon 26/05/25
r Concrete contract operative 1 | 16 hrs |  | Fri 23/05/25 | Mon 26/05/25
r Concrete contract operative 2 | 16 hrs |  | Fri 23/05/25 | Mon 26/05/25
r Concrete contract operative 3 | 16 hrs |  | Fri 23/05/25 | Mon 26/05/25
m Concrete m3 | 3 |  | Fri 23/05/25 | Mon 26/05/25
Screed FLR | 64 hrs | 4 days | Tue 27/05/25 | Fri 30/05/25
r Screed operative 1 | 32 hrs |  | Tue 27/05/25 | Fri 30/05/25
r Screed operative 2 | 32 hrs |  | Tue 27/05/25 | Fri 30/05/25
m Screed m2 | 5 |  | Tue 27/05/25 | Fri 30/05/25
Second FLR Structural FLR | 920 hrs | 29 days | Mon 02/06/25 | Thu 10/07/25
Erect scaffold access | 160 hrs | 4 days | Mon 02/06/25 | Thu 05/06/25
r Scaffolding supervisor 1 | 32 hrs |  | Mon 02/06/25 | Thu 05/06/25
r Scaffolder 1 | 32 hrs |  | Mon 02/06/25 | Thu 05/06/25
r Scaffolder 2 | 32 hrs |  | Mon 02/06/25 | Thu 05/06/25
r Scaffolder 3 | 32 hrs |  | Mon 02/06/25 | Thu 05/06/25
r scaffolder 4 | 32 hrs |  | Mon 02/06/25 | Thu 05/06/25
p Scaffolding m2 | 1 |  | Mon 02/06/25 | Thu 05/06/25
Install pre cast concrete beams | 256 hrs | 8 days | Fri 06/06/25 | Tue 17/06/25
r Concrete contract supervisor 1 | 64 hrs |  | Fri 06/06/25 | Tue 17/06/25
r Concrete contract operative 1 | 64 hrs |  | Fri 06/06/25 | Tue 17/06/25
r Concrete contract operative 2 | 64 hrs |  | Fri 06/06/25 | Tue 17/06/25
r Concrete contract operative 3 | 64 hrs |  | Fri 06/06/25 | Tue 17/06/25
p Hiab 35t day | 8 |  | Fri 06/06/25 | Tue 17/06/25
p Crane 100t per day | 8 |  | Fri 06/06/25 | Tue 17/06/25
m Concrete m3 | 50 |  | Fri 06/06/25 | Tue 17/06/25
Install concrete pre tension blocks | 256 hrs | 8 days | Wed 18/06/25 | Fri 27/06/25
r Concrete contract supervisor 1 | 64 hrs |  | Wed 18/06/25 | Fri 27/06/25
r Concrete contract operative 1 | 64 hrs |  | Wed 18/06/25 | Fri 27/06/25
r Concrete contract operative 2 | 64 hrs |  | Wed 18/06/25 | Fri 27/06/25
r Concrete contract operative 3 | 64 hrs |  | Wed 18/06/25 | Fri 27/06/25
p Hiab 35t day | 8 |  | Wed 18/06/25 | Fri 27/06/25
p Crane 100t per day | 8 |  | Wed 18/06/25 | Fri 27/06/25
m Concrete m3 | 50 |  | Wed 18/06/25 | Fri 27/06/25
Dismantle scaffolding access | 120 hrs | 3 days | Mon 30/06/25 | Wed 02/07/25
r Scaffolding supervisor 1 | 24 hrs |  | Mon 30/06/25 | Wed 02/07/25
r Scaffolder 1 | 24 hrs |  | Mon 30/06/25 | Wed 02/07/25
r Scaffolder 2 | 24 hrs |  | Mon 30/06/25 | Wed 02/07/25
r Scaffolder 3 | 24 hrs |  | Mon 30/06/25 | Wed 02/07/25
r scaffolder 4 | 24 hrs |  | Mon 30/06/25 | Wed 02/07/25
Grout gaps | 64 hrs | 2 days | Thu 03/07/25 | Fri 04/07/25
r Concrete contract supervisor 1 | 16 hrs |  | Thu 03/07/25 | Fri 04/07/25
r Concrete contract operative 1 | 16 hrs |  | Thu 03/07/25 | Fri 04/07/25
r Concrete contract operative 2 | 16 hrs |  | Thu 03/07/25 | Fri 04/07/25
r Concrete contract operative 3 | 16 hrs |  | Thu 03/07/25 | Fri 04/07/25
m Concrete m3 | 3 |  | Thu 03/07/25 | Fri 04/07/25
Screed FLR | 64 hrs | 4 days | Mon 07/07/25 | Thu 10/07/25
r Screed operative 1 | 32 hrs |  | Mon 07/07/25 | Thu 10/07/25
r Screed operative 2 | 32 hrs |  | Mon 07/07/25 | Thu 10/07/25
m Screed m2 | 5 |  | Mon 07/07/25 | Thu 10/07/25
500 to 508 Walls & Interiors | 20,624 hrs | 172 days | Thu 01/05/25 | Fri 26/12/25
Interior walls & Interiors | 16,920 hrs | 172 days | Thu 01/05/25 | Fri 26/12/25
Interior Second FLR | 5,856 hrs | 121 days | Fri 11/07/25 | Fri 26/12/25
Build interior SF Partition block walls | 1,520 hrs | 38 days | Fri 11/07/25 | Tue 02/09/25
r Bricklayer supervisor 2 | 304 hrs |  | Fri 11/07/25 | Tue 02/09/25
r Bricklayer 5 | 304 hrs |  | Fri 11/07/25 | Tue 02/09/25
r Bricklayer 6 | 304 hrs |  | Fri 11/07/25 | Tue 02/09/25
r Bricklayer 7 | 304 hrs |  | Fri 11/07/25 | Tue 02/09/25
r Bricklayer 8 | 304 hrs |  | Fri 11/07/25 | Tue 02/09/25
p Hiab 35t day | 1 |  | Fri 11/07/25 | Thu 07/08/25
m Blocks m2 | 200 |  | Fri 11/07/25 | Tue 02/09/25
Second FLR First fix electrical | 600 hrs | 15 days | Wed 03/09/25 | Tue 23/09/25
r Electrical supervisor 2 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Electrician 5 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Electrician 6 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Electrician 7 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Electrician 8 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
Second Flr First fix Plumbing | 600 hrs | 15 days | Wed 03/09/25 | Tue 23/09/25
r Plumbing supervisor 2 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Plumber 5 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Plumber 6 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Plumber 7 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Plumber 8 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
Second FLR First fix Carpentry | 600 hrs | 15 days | Wed 03/09/25 | Tue 23/09/25
r Carpenter supervisor 2 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Carpenter 5 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Carpenter 6 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Carpenter 7 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
r Carpenter 8 | 120 hrs |  | Wed 03/09/25 | Tue 23/09/25
Second floor Plasterboard ceiling | 200 hrs | 5 days | Wed 24/09/25 | Tue 30/09/25
r Plasterer supervisor 2 | 40 hrs |  | Wed 24/09/25 | Tue 30/09/25
r Plasterer 5 | 40 hrs |  | Wed 24/09/25 | Tue 30/09/25
r Plasterer 6 | 40 hrs |  | Wed 24/09/25 | Tue 30/09/25
r Plasterer 7 | 40 hrs |  | Wed 24/09/25 | Tue 30/09/25
r Plasterer 8 | 40 hrs |  | Wed 24/09/25 | Tue 30/09/25
m Plaster m2 | 100 |  | Wed 24/09/25 | Tue 30/09/25
Second floor complete plastering | 320 hrs | 8 days | Wed 01/10/25 | Fri 10/10/25
r Plasterer supervisor 2 | 64 hrs |  | Wed 01/10/25 | Fri 10/10/25
r Plasterer 5 | 64 hrs |  | Wed 01/10/25 | Fri 10/10/25
r Plasterer 6 | 64 hrs |  | Wed 01/10/25 | Fri 10/10/25
r Plasterer 7 | 64 hrs |  | Wed 01/10/25 | Fri 10/10/25
r Plasterer 8 | 64 hrs |  | Wed 01/10/25 | Fri 10/10/25
m Plaster m2 | 200 |  | Wed 01/10/25 | Fri 10/10/25
First floor Install Kitchens | 528 hrs | 7 days | Mon 13/10/25 | Tue 28/10/25
r Electrical supervisor 2 | 48 hrs |  | Mon 13/10/25 | Tue 28/10/25
r Electrician 5 | 48 hrs |  | Mon 13/10/25 | Tue 28/10/25
r Electrician 6 | 48 hrs |  | Mon 13/10/25 | Tue 28/10/25
r Electrician 7 | 48 hrs |  | Mon 13/10/25 | Tue 28/10/25
r Electrician 8 | 48 hrs |  | Mon 13/10/25 | Tue 28/10/25
r Plumber 5 | 48 hrs |  | Mon 13/10/25 | Tue 28/10/25
r Carpenter supervisor 2 | 48 hrs |  | Mon 13/10/25 | Mon 20/10/25
r Carpenter 5 | 48 hrs |  | Mon 13/10/25 | Mon 20/10/25
r Carpenter 6 | 48 hrs |  | Mon 13/10/25 | Mon 20/10/25
r Carpenter 7 | 48 hrs |  | Mon 13/10/25 | Mon 20/10/25
r Carpenter 8 | 48 hrs |  | Mon 13/10/25 | Mon 20/10/25
m Kitchen per residence | 3 |  | Mon 13/10/25 | Tue 28/10/25
m Plumbing fittings per residence | 3 |  | Mon 13/10/25 | Tue 28/10/25
First floor Install Bathrooms | 480 hrs | 16 days | Wed 29/10/25 | Wed 19/11/25
r Electrical supervisor 2 | 48 hrs |  | Wed 05/11/25 | Wed 12/11/25
r Electrician 5 | 48 hrs |  | Wed 05/11/25 | Wed 12/11/25
r Electrician 6 | 48 hrs |  | Wed 05/11/25 | Wed 12/11/25
r Electrician 7 | 48 hrs |  | Wed 05/11/25 | Wed 12/11/25
r Electrician 8 | 48 hrs |  | Wed 05/11/25 | Wed 12/11/25
r Plumbing supervisor 2 | 48 hrs |  | Wed 29/10/25 | Wed 05/11/25
r Plumber 5 | 48 hrs |  | Wed 12/11/25 | Wed 19/11/25
r Plumber 6 | 48 hrs |  | Wed 29/10/25 | Wed 05/11/25
r Plumber 7 | 48 hrs |  | Wed 29/10/25 | Wed 05/11/25
r Plumber 8 | 48 hrs |  | Wed 29/10/25 | Wed 05/11/25
m Bahroom per residence | 3 |  | Wed 29/10/25 | Wed 19/11/25
First floor second fix electrical | 200 hrs | 5 days | Thu 27/11/25 | Wed 03/12/25
r Electrical supervisor 2 | 40 hrs |  | Thu 27/11/25 | Wed 03/12/25
r Electrician 5 | 40 hrs |  | Thu 27/11/25 | Wed 03/12/25
r Electrician 6 | 40 hrs |  | Thu 27/11/25 | Wed 03/12/25
r Electrician 7 | 40 hrs |  | Thu 27/11/25 | Wed 03/12/25
r Electrician 8 | 40 hrs |  | Thu 27/11/25 | Wed 03/12/25
m Electrical fittings per residence | 3 |  | Thu 27/11/25 | Wed 03/12/25
First floor second fix Plumbing | 200 hrs | 10 days | Thu 20/11/25 | Wed 03/12/25
r Plumbing supervisor 2 | 40 hrs |  | Thu 20/11/25 | Wed 26/11/25
r Plumber 5 | 40 hrs |  | Thu 27/11/25 | Wed 03/12/25
r Plumber 6 | 40 hrs |  | Thu 20/11/25 | Wed 26/11/25
r Plumber 7 | 40 hrs |  | Thu 20/11/25 | Wed 26/11/25
r Plumber 8 | 40 hrs |  | Thu 20/11/25 | Wed 26/11/25
m Plumbing fittings per residence | 3 |  | Thu 20/11/25 | Wed 03/12/25
First floor Complete tiling | 144 hrs | 6 days | Mon 08/12/25 | Mon 15/12/25
r Tile fitter supervisor 2 | 48 hrs |  | Mon 08/12/25 | Mon 15/12/25
r Tile fitter 3 | 48 hrs |  | Mon 08/12/25 | Mon 15/12/25
r Tile fitter 4 | 48 hrs |  | Mon 08/12/25 | Mon 15/12/25
m Flooring tiles m2 | 10 |  | Mon 08/12/25 | Mon 15/12/25
m Tiles m2 | 10 |  | Mon 08/12/25 | Mon 15/12/25
First Floor Complete decorating | 144 hrs | 6 days | Tue 16/12/25 | Tue 23/12/25
r Decorater supervisor 2 | 48 hrs |  | Tue 16/12/25 | Tue 23/12/25
r Decorater 3 | 48 hrs |  | Tue 16/12/25 | Tue 23/12/25
r Decorater 4 | 48 hrs |  | Tue 16/12/25 | Tue 23/12/25
m finishings per m2 | 100 |  | Tue 16/12/25 | Tue 23/12/25
First floor fit carpets and floor coverings | 120 hrs | 3 days | Wed 24/12/25 | Fri 26/12/25
r Carpenter supervisor 2 | 24 hrs |  | Wed 24/12/25 | Fri 26/12/25
r Carpet fitter 5 | 24 hrs |  | Wed 24/12/25 | Fri 26/12/25
r Carpet fitter 6 | 24 hrs |  | Wed 24/12/25 | Fri 26/12/25
r Carpet fitter 7 | 24 hrs |  | Wed 24/12/25 | Fri 26/12/25
r Carpet fitter 8 | 24 hrs |  | Wed 24/12/25 | Fri 26/12/25
m Flooring carpet M2 | 50 |  | Wed 24/12/25 | Fri 26/12/25
m Flooring vinyl m2 | 50 |  | Wed 24/12/25 | Fri 26/12/25
Plots 500 to 508 construction complete | 0 hrs | 0 days | Fri 26/12/25 | Fri 26/12/25
Plots 500 to 508 construction complete | 0 hrs | 0 days | Fri 26/12/25 | Fri 26/12/25
Plots 600 to 605 3 storey x 6 units type 42 | 25,032 hrs | 393 days | Fri 11/04/25 | Tue 13/10/26
600 to 605 Foundations, substructures & structural floors | 4,784 hrs | 272 days | Fri 11/04/25 | Mon 27/04/26
Ground FLR Concrete slab | 424 hrs | 40 days | Mon 29/12/25 | Fri 20/02/26
Lay hardcore base | 64 hrs | 2 days | Mon 29/12/25 | Tue 30/12/25
r Groundworker 1 | 16 hrs |  | Mon 29/12/25 | Tue 30/12/25
r Groundworker 2 | 16 hrs |  | Mon 29/12/25 | Tue 30/12/25
r Groundworker 3 | 16 hrs |  | Mon 29/12/25 | Tue 30/12/25
r Groundworker 4 | 16 hrs |  | Mon 29/12/25 | Tue 30/12/25
p Excavator 1 per day | 2 |  | Mon 29/12/25 | Tue 30/12/25
p roller per day | 2 |  | Mon 29/12/25 | Tue 30/12/25
p Dumper truck 3t day | 2 |  | Mon 29/12/25 | Tue 30/12/25
m Type 1 m3 | 30 |  | Mon 29/12/25 | Tue 30/12/25
Install DPM | 32 hrs | 1 day | Wed 31/12/25 | Wed 31/12/25
r Groundworker 1 | 8 hrs |  | Wed 31/12/25 | Wed 31/12/25
r Groundworker 2 | 8 hrs |  | Wed 31/12/25 | Wed 31/12/25
r Groundworker 3 | 8 hrs |  | Wed 31/12/25 | Wed 31/12/25
r Groundworker 4 | 8 hrs |  | Wed 31/12/25 | Wed 31/12/25
p Telehandler 18m per day | 1 |  | Wed 31/12/25 | Wed 31/12/25
Install Insulation slab | 64 hrs | 2 days | Thu 01/01/26 | Fri 02/01/26
r Groundworker 1 | 16 hrs |  | Thu 01/01/26 | Fri 02/01/26
r Insulation supervisor 1 | 16 hrs |  | Thu 01/01/26 | Fri 02/01/26
r Insulator 1 | 16 hrs |  | Thu 01/01/26 | Fri 02/01/26
r Insulator 2 | 16 hrs |  | Thu 01/01/26 | Fri 02/01/26
p Telehandler 18m per day | 2 |  | Thu 01/01/26 | Fri 02/01/26
m Insulation raft m2 | 30 |  | Thu 01/01/26 | Fri 02/01/26
make and install steel reinforcement cages | 96 hrs | 5 days | Thu 01/01/26 | Wed 07/01/26
r Groundworker 1 | 24 hrs |  | Mon 05/01/26 | Wed 07/01/26
r Groundworker 2 | 24 hrs |  | Thu 01/01/26 | Mon 05/01/26
r Groundworker 3 | 24 hrs |  | Thu 01/01/26 | Mon 05/01/26
r Groundworker 4 | 24 hrs |  | Thu 01/01/26 | Mon 05/01/26
p Telehandler 18m per day | 5 |  | Thu 01/01/26 | Wed 07/01/26
m Rebar T | 100 |  | Thu 01/01/26 | Wed 07/01/26
Construct formwork | 48 hrs | 3 days | Mon 05/01/26 | Wed 07/01/26
r Carpenter 1 | 24 hrs |  | Mon 05/01/26 | Wed 07/01/26
r Carpenter 2 | 24 hrs |  | Mon 05/01/26 | Wed 07/01/26
p Telehandler 18m per day | 1 |  | Mon 05/01/26 | Wed 07/01/26
m Timber Pine m2 | 10 |  | Mon 05/01/26 | Wed 07/01/26
Pour concrete slab 500 to 508 | 32 hrs | 1 day | Thu 08/01/26 | Thu 08/01/26
r Groundworker 1 | 8 hrs |  | Thu 08/01/26 | Thu 08/01/26
r Groundworker 2 | 8 hrs |  | Thu 08/01/26 | Thu 08/01/26
r Groundworker 3 | 8 hrs |  | Thu 08/01/26 | Thu 08/01/26
r Groundworker 4 | 8 hrs |  | Thu 08/01/26 | Thu 08/01/26
m Concrete m3 | 30 |  | Thu 08/01/26 | Thu 08/01/26
Staircase & Stairwell | 560 hrs | 14 days | Fri 16/01/26 | Wed 04/02/26
Erect Ground FLR stairwell 1 scaffolding | 40 hrs | 1 day | Fri 16/01/26 | Fri 16/01/26
r Scaffolding supervisor 1 | 8 hrs |  | Fri 16/01/26 | Fri 16/01/26
r Scaffolder 1 | 8 hrs |  | Fri 16/01/26 | Fri 16/01/26
r Scaffolder 2 | 8 hrs |  | Fri 16/01/26 | Fri 16/01/26
r Scaffolder 3 | 8 hrs |  | Fri 16/01/26 | Fri 16/01/26
r scaffolder 4 | 8 hrs |  | Fri 16/01/26 | Fri 16/01/26
p Scaffolding m2 | 15 |  | Fri 16/01/26 | Fri 16/01/26
Construct Ground FLR Breeze block Stairwell 1 | 120 hrs | 3 days | Mon 19/01/26 | Wed 21/01/26
r Bricklayer supervisor 1 | 24 hrs |  | Mon 19/01/26 | Wed 21/01/26
r Bricklayer supervisor 3 | 24 hrs |  | Mon 19/01/26 | Wed 21/01/26
r Bricklayer 2 | 24 hrs |  | Mon 19/01/26 | Wed 21/01/26
r Bricklayer 3 | 24 hrs |  | Mon 19/01/26 | Wed 21/01/26
r Bricklayer 4 | 24 hrs |  | Mon 19/01/26 | Wed 21/01/26
m Blocks m2 | 40 |  | Mon 19/01/26 | Wed 21/01/26
Erect First FLR scaffolding | 40 hrs | 1 day | Thu 22/01/26 | Thu 22/01/26
r Scaffolding supervisor 1 | 8 hrs |  | Thu 22/01/26 | Thu 22/01/26
r Scaffolder 1 | 8 hrs |  | Thu 22/01/26 | Thu 22/01/26
r Scaffolder 2 | 8 hrs |  | Thu 22/01/26 | Thu 22/01/26
r Scaffolder 3 | 8 hrs |  | Thu 22/01/26 | Thu 22/01/26
r scaffolder 4 | 8 hrs |  | Thu 22/01/26 | Thu 22/01/26
p Scaffolding m2 | 15 |  | Thu 22/01/26 | Thu 22/01/26
Construct First FLR Breeze block Stairwell 1 | 120 hrs | 3 days | Fri 23/01/26 | Tue 27/01/26
r Bricklayer supervisor 1 | 24 hrs |  | Fri 23/01/26 | Tue 27/01/26
r Bricklayer supervisor 3 | 24 hrs |  | Fri 23/01/26 | Tue 27/01/26
r Bricklayer 2 | 24 hrs |  | Fri 23/01/26 | Tue 27/01/26
r Bricklayer 3 | 24 hrs |  | Fri 23/01/26 | Tue 27/01/26
r Bricklayer 4 | 24 hrs |  | Fri 23/01/26 | Tue 27/01/26
m Blocks m2 | 40 |  | Fri 23/01/26 | Tue 27/01/26
Erect Second FLR scaffolding | 40 hrs | 1 day | Wed 28/01/26 | Wed 28/01/26
r Scaffolding supervisor 1 | 8 hrs |  | Wed 28/01/26 | Wed 28/01/26
r Scaffolder 1 | 8 hrs |  | Wed 28/01/26 | Wed 28/01/26
r Scaffolder 2 | 8 hrs |  | Wed 28/01/26 | Wed 28/01/26
r Scaffolder 3 | 8 hrs |  | Wed 28/01/26 | Wed 28/01/26
r scaffolder 4 | 8 hrs |  | Wed 28/01/26 | Wed 28/01/26
p Scaffolding m2 | 15 |  | Wed 28/01/26 | Wed 28/01/26
Construct Second FLR Breeze block stairwell 1 | 120 hrs | 3 days | Thu 29/01/26 | Mon 02/02/26
r Bricklayer supervisor 1 | 24 hrs |  | Thu 29/01/26 | Mon 02/02/26
r Bricklayer supervisor 3 | 24 hrs |  | Thu 29/01/26 | Mon 02/02/26
r Bricklayer 2 | 24 hrs |  | Thu 29/01/26 | Mon 02/02/26
r Bricklayer 3 | 24 hrs |  | Thu 29/01/26 | Mon 02/02/26
r Bricklayer 4 | 24 hrs |  | Thu 29/01/26 | Mon 02/02/26
m Blocks m2 | 40 |  | Thu 29/01/26 | Mon 02/02/26
Dismantle all stairwell 1 scaffolding | 80 hrs | 2 days | Tue 03/02/26 | Wed 04/02/26
r Scaffolding supervisor 1 | 16 hrs |  | Tue 03/02/26 | Wed 04/02/26
r Scaffolder 1 | 16 hrs |  | Tue 03/02/26 | Wed 04/02/26
r Scaffolder 2 | 16 hrs |  | Tue 03/02/26 | Wed 04/02/26
r Scaffolder 3 | 16 hrs |  | Tue 03/02/26 | Wed 04/02/26
r scaffolder 4 | 16 hrs |  | Tue 03/02/26 | Wed 04/02/26
First FLR Structural FLR | 920 hrs | 29 days | Thu 05/02/26 | Tue 17/03/26
Erect scaffold access | 160 hrs | 4 days | Thu 05/02/26 | Tue 10/02/26
r Scaffolding supervisor 1 | 32 hrs |  | Thu 05/02/26 | Tue 10/02/26
r Scaffolder 1 | 32 hrs |  | Thu 05/02/26 | Tue 10/02/26
r Scaffolder 2 | 32 hrs |  | Thu 05/02/26 | Tue 10/02/26
r Scaffolder 3 | 32 hrs |  | Thu 05/02/26 | Tue 10/02/26
r scaffolder 4 | 32 hrs |  | Thu 05/02/26 | Tue 10/02/26
p Scaffolding m2 | 1 |  | Thu 05/02/26 | Tue 10/02/26
Install pre cast concrete beams | 256 hrs | 8 days | Wed 11/02/26 | Fri 20/02/26
r Concrete contract supervisor 1 | 64 hrs |  | Wed 11/02/26 | Fri 20/02/26
r Concrete contract operative 1 | 64 hrs |  | Wed 11/02/26 | Fri 20/02/26
r Concrete contract operative 2 | 64 hrs |  | Wed 11/02/26 | Fri 20/02/26
r Concrete contract operative 3 | 64 hrs |  | Wed 11/02/26 | Fri 20/02/26
p Hiab 35t day | 8 |  | Wed 11/02/26 | Fri 20/02/26
p Crane 100t per day | 8 |  | Wed 11/02/26 | Fri 20/02/26
m Concrete m3 | 50 |  | Wed 11/02/26 | Fri 20/02/26
Install concrete pre tension blocks | 256 hrs | 8 days | Mon 23/02/26 | Wed 04/03/26
r Concrete contract supervisor 1 | 64 hrs |  | Mon 23/02/26 | Wed 04/03/26
r Concrete contract operative 1 | 64 hrs |  | Mon 23/02/26 | Wed 04/03/26
r Concrete contract operative 2 | 64 hrs |  | Mon 23/02/26 | Wed 04/03/26
r Concrete contract operative 3 | 64 hrs |  | Mon 23/02/26 | Wed 04/03/26
p Hiab 35t day | 8 |  | Mon 23/02/26 | Wed 04/03/26
p Crane 100t per day | 8 |  | Mon 23/02/26 | Wed 04/03/26
m Concrete m3 | 50 |  | Mon 23/02/26 | Wed 04/03/26
Dismantle scaffolding access | 120 hrs | 3 days | Thu 05/03/26 | Mon 09/03/26
r Scaffolding supervisor 1 | 24 hrs |  | Thu 05/03/26 | Mon 09/03/26
r Scaffolder 1 | 24 hrs |  | Thu 05/03/26 | Mon 09/03/26
r Scaffolder 2 | 24 hrs |  | Thu 05/03/26 | Mon 09/03/26
r Scaffolder 3 | 24 hrs |  | Thu 05/03/26 | Mon 09/03/26
r scaffolder 4 | 24 hrs |  | Thu 05/03/26 | Mon 09/03/26
Grout gaps | 64 hrs | 2 days | Tue 10/03/26 | Wed 11/03/26
r Concrete contract supervisor 1 | 16 hrs |  | Tue 10/03/26 | Wed 11/03/26
r Concrete contract operative 1 | 16 hrs |  | Tue 10/03/26 | Wed 11/03/26
r Concrete contract operative 2 | 16 hrs |  | Tue 10/03/26 | Wed 11/03/26
r Concrete contract operative 3 | 16 hrs |  | Tue 10/03/26 | Wed 11/03/26
m Concrete m3 | 3 |  | Tue 10/03/26 | Wed 11/03/26
Screed FLR | 64 hrs | 4 days | Thu 12/03/26 | Tue 17/03/26
r Screed operative 1 | 32 hrs |  | Thu 12/03/26 | Tue 17/03/26
r Screed operative 2 | 32 hrs |  | Thu 12/03/26 | Tue 17/03/26
m Screed m2 | 5 |  | Thu 12/03/26 | Tue 17/03/26
Second FLR Structural FLR | 920 hrs | 29 days | Wed 18/03/26 | Mon 27/04/26
Erect scaffold access | 160 hrs | 4 days | Wed 18/03/26 | Mon 23/03/26
r Scaffolding supervisor 1 | 32 hrs |  | Wed 18/03/26 | Mon 23/03/26
r Scaffolder 1 | 32 hrs |  | Wed 18/03/26 | Mon 23/03/26
r Scaffolder 2 | 32 hrs |  | Wed 18/03/26 | Mon 23/03/26
r Scaffolder 3 | 32 hrs |  | Wed 18/03/26 | Mon 23/03/26
r scaffolder 4 | 32 hrs |  | Wed 18/03/26 | Mon 23/03/26
p Scaffolding m2 | 1 |  | Wed 18/03/26 | Mon 23/03/26
Install pre cast concrete beams | 256 hrs | 8 days | Tue 24/03/26 | Thu 02/04/26
r Concrete contract supervisor 1 | 64 hrs |  | Tue 24/03/26 | Thu 02/04/26
r Concrete contract operative 1 | 64 hrs |  | Tue 24/03/26 | Thu 02/04/26
r Concrete contract operative 2 | 64 hrs |  | Tue 24/03/26 | Thu 02/04/26
r Concrete contract operative 3 | 64 hrs |  | Tue 24/03/26 | Thu 02/04/26
p Hiab 35t day | 8 |  | Tue 24/03/26 | Thu 02/04/26
p Crane 100t per day | 8 |  | Tue 24/03/26 | Thu 02/04/26
m Concrete m3 | 50 |  | Tue 24/03/26 | Thu 02/04/26
Install concrete pre tension blocks | 256 hrs | 8 days | Fri 03/04/26 | Tue 14/04/26
r Concrete contract supervisor 1 | 64 hrs |  | Fri 03/04/26 | Tue 14/04/26
r Concrete contract operative 1 | 64 hrs |  | Fri 03/04/26 | Tue 14/04/26
r Concrete contract operative 2 | 64 hrs |  | Fri 03/04/26 | Tue 14/04/26
r Concrete contract operative 3 | 64 hrs |  | Fri 03/04/26 | Tue 14/04/26
p Hiab 35t day | 8 |  | Fri 03/04/26 | Tue 14/04/26
p Crane 100t per day | 8 |  | Fri 03/04/26 | Tue 14/04/26
m Concrete m3 | 50 |  | Fri 03/04/26 | Tue 14/04/26
Dismantle scaffolding access | 120 hrs | 3 days | Wed 15/04/26 | Fri 17/04/26
r Scaffolding supervisor 1 | 24 hrs |  | Wed 15/04/26 | Fri 17/04/26
r Scaffolder 1 | 24 hrs |  | Wed 15/04/26 | Fri 17/04/26
r Scaffolder 2 | 24 hrs |  | Wed 15/04/26 | Fri 17/04/26
r Scaffolder 3 | 24 hrs |  | Wed 15/04/26 | Fri 17/04/26
r scaffolder 4 | 24 hrs |  | Wed 15/04/26 | Fri 17/04/26
Grout gaps | 64 hrs | 2 days | Mon 20/04/26 | Tue 21/04/26
r Concrete contract supervisor 1 | 16 hrs |  | Mon 20/04/26 | Tue 21/04/26
r Concrete contract operative 1 | 16 hrs |  | Mon 20/04/26 | Tue 21/04/26
r Concrete contract operative 2 | 16 hrs |  | Mon 20/04/26 | Tue 21/04/26
r Concrete contract operative 3 | 16 hrs |  | Mon 20/04/26 | Tue 21/04/26
m Concrete m3 | 3 |  | Mon 20/04/26 | Tue 21/04/26
Screed FLR | 64 hrs | 4 days | Wed 22/04/26 | Mon 27/04/26
r Screed operative 1 | 32 hrs |  | Wed 22/04/26 | Mon 27/04/26
r Screed operative 2 | 32 hrs |  | Wed 22/04/26 | Mon 27/04/26
m Screed m2 | 5 |  | Wed 22/04/26 | Mon 27/04/26
600 to 605 Walls & Interiors | 19,864 hrs | 167 days | Mon 23/02/26 | Tue 13/10/26
Interior walls & Interiors | 15,320 hrs | 167 days | Mon 23/02/26 | Tue 13/10/26
Interior First FLR | 3,912 hrs | 147 days | Mon 23/03/26 | Tue 13/10/26
Build interior FF Partition block walls | 680 hrs | 21 days | Mon 23/03/26 | Fri 12/06/26
r Bricklayer supervisor 2 | 136 hrs |  | Mon 23/03/26 | Fri 12/06/26
r Bricklayer 5 | 136 hrs |  | Mon 23/03/26 | Mon 25/05/26
r Bricklayer 6 | 136 hrs |  | Mon 23/03/26 | Mon 25/05/26
r Bricklayer 7 | 136 hrs |  | Mon 23/03/26 | Mon 25/05/26
r Bricklayer 8 | 136 hrs |  | Mon 23/03/26 | Mon 25/05/26
p Hiab 35t day | 1 |  | Mon 23/03/26 | Fri 10/04/26
m Blocks m2 | 200 |  | Mon 23/03/26 | Fri 12/06/26
First FLR First fix electrical | 400 hrs | 12 days | Thu 18/06/26 | Tue 21/07/26
r Electrical supervisor 2 | 80 hrs |  | Thu 18/06/26 | Mon 20/07/26
r Electrician 5 | 80 hrs |  | Fri 19/06/26 | Tue 21/07/26
r Electrician 6 | 80 hrs |  | Thu 18/06/26 | Mon 20/07/26
r Electrician 7 | 80 hrs |  | Thu 18/06/26 | Mon 20/07/26
r Electrician 8 | 80 hrs |  | Thu 18/06/26 | Mon 20/07/26
First floor Plasterboard ceiling | 160 hrs | 4 days | Wed 22/07/26 | Mon 27/07/26
r Plasterer supervisor 1 | 32 hrs |  | Wed 22/07/26 | Mon 27/07/26
r Plasterer 1 | 32 hrs |  | Wed 22/07/26 | Mon 27/07/26
r Plasterer 2 | 32 hrs |  | Wed 22/07/26 | Mon 27/07/26
r Plasterer 3 | 32 hrs |  | Wed 22/07/26 | Mon 27/07/26
r Plasterer 4 | 32 hrs |  | Wed 22/07/26 | Mon 27/07/26
m Plaster m2 | 100 |  | Wed 22/07/26 | Mon 27/07/26
First floor complete plastering | 240 hrs | 6 days | Tue 28/07/26 | Tue 04/08/26
r Plasterer supervisor 2 | 48 hrs |  | Tue 28/07/26 | Tue 04/08/26
r Plasterer 5 | 48 hrs |  | Tue 28/07/26 | Tue 04/08/26
r Plasterer 6 | 48 hrs |  | Tue 28/07/26 | Tue 04/08/26
r Plasterer 7 | 48 hrs |  | Tue 28/07/26 | Tue 04/08/26
r Plasterer 8 | 48 hrs |  | Tue 28/07/26 | Tue 04/08/26
m Plaster m2 | 200 |  | Tue 28/07/26 | Tue 04/08/26
First floor Install Kitchens | 440 hrs | 11 days | Wed 05/08/26 | Thu 27/08/26
r Electrical supervisor 2 | 40 hrs |  | Wed 05/08/26 | Tue 11/08/26
r Electrician 5 | 40 hrs |  | Wed 05/08/26 | Tue 11/08/26
r Electrician 6 | 40 hrs |  | Wed 05/08/26 | Tue 11/08/26
r Electrician 7 | 40 hrs |  | Wed 05/08/26 | Tue 11/08/26
r Electrician 8 | 40 hrs |  | Wed 05/08/26 | Tue 11/08/26
r Plumber 5 | 40 hrs |  | Wed 05/08/26 | Tue 11/08/26
r Carpenter supervisor 2 | 40 hrs |  | Wed 12/08/26 | Thu 27/08/26
r Carpenter 5 | 40 hrs |  | Wed 12/08/26 | Wed 26/08/26
r Carpenter 6 | 40 hrs |  | Wed 12/08/26 | Wed 26/08/26
r Carpenter 7 | 40 hrs |  | Wed 12/08/26 | Wed 26/08/26
r Carpenter 8 | 40 hrs |  | Wed 12/08/26 | Wed 26/08/26
m Kitchen per residence | 3 |  | Wed 05/08/26 | Thu 27/08/26
m Plumbing fittings per residence | 3 |  | Wed 05/08/26 | Thu 27/08/26
First floor Install Bathrooms | 400 hrs | 5 days | Fri 28/08/26 | Thu 03/09/26
r Electrical supervisor 2 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Electrician 5 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Electrician 6 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Electrician 7 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Electrician 8 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Plumbing supervisor 2 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Plumber 5 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Plumber 6 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Plumber 7 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
r Plumber 8 | 40 hrs |  | Fri 28/08/26 | Thu 03/09/26
m Bahroom per residence | 3 |  | Fri 28/08/26 | Thu 03/09/26
First floor second fix electrical | 160 hrs | 5 days | Fri 04/09/26 | Wed 16/09/26
r Electrical supervisor 2 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Electrician 5 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Electrician 6 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Electrician 7 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Electrician 8 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
m Electrical fittings per residence | 3 |  | Fri 04/09/26 | Wed 16/09/26
First floor second fix Plumbing | 160 hrs | 6 days | Fri 04/09/26 | Wed 16/09/26
r Plumbing supervisor 2 | 32 hrs |  | Fri 04/09/26 | Wed 09/09/26
r Plumber 5 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Plumber 6 | 32 hrs |  | Fri 04/09/26 | Wed 09/09/26
r Plumber 7 | 32 hrs |  | Fri 04/09/26 | Wed 09/09/26
r Plumber 8 | 32 hrs |  | Fri 04/09/26 | Wed 09/09/26
m Plumbing fittings per residence | 3 |  | Fri 04/09/26 | Wed 16/09/26
First floor second fix Carpentry | 160 hrs | 4 days | Fri 04/09/26 | Wed 16/09/26
r Carpenter supervisor 2 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Carpenter 5 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Carpenter 6 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Carpenter 7 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
r Carpenter 8 | 32 hrs |  | Fri 04/09/26 | Wed 16/09/26
m Timber Pine m2 | 10 |  | Fri 04/09/26 | Wed 16/09/26
First floor Complete tiling | 96 hrs | 4 days | Fri 25/09/26 | Wed 30/09/26
r Tile fitter supervisor 1 | 32 hrs |  | Fri 25/09/26 | Wed 30/09/26
r Tile fitter 1 | 32 hrs |  | Fri 25/09/26 | Wed 30/09/26
r Tile fitter 2 | 32 hrs |  | Fri 25/09/26 | Wed 30/09/26
m Flooring tiles m2 | 10 |  | Fri 25/09/26 | Wed 30/09/26
m Tiles m2 | 10 |  | Fri 25/09/26 | Wed 30/09/26
First Floor Complete decorating | 96 hrs | 6 days | Thu 01/10/26 | Thu 08/10/26
r Decorater 5 | 48 hrs |  | Thu 01/10/26 | Thu 08/10/26
r Decorater 6 | 48 hrs |  | Thu 01/10/26 | Thu 08/10/26
m finishings per m2 | 100 |  | Thu 01/10/26 | Thu 08/10/26
First floor fit carpets and floor coverings | 120 hrs | 3 days | Fri 09/10/26 | Tue 13/10/26
r Carpenter supervisor 2 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 5 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 6 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 7 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 8 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
m Flooring carpet M2 | 50 |  | Fri 09/10/26 | Tue 13/10/26
m Flooring vinyl m2 | 50 |  | Fri 09/10/26 | Tue 13/10/26
Interior Second FLR | 5,072 hrs | 120 days | Wed 29/04/26 | Tue 13/10/26
Build interior SF Partition block walls | 960 hrs | 24 days | Wed 29/04/26 | Wed 03/06/26
r Bricklayer supervisor 5 | 192 hrs |  | Wed 29/04/26 | Wed 03/06/26
r Bricklayer 17 | 192 hrs |  | Wed 29/04/26 | Wed 03/06/26
r Bricklayer 18 | 192 hrs |  | Wed 29/04/26 | Wed 03/06/26
r Bricklayer 19 | 192 hrs |  | Wed 29/04/26 | Wed 03/06/26
r Bricklayer 20 | 192 hrs |  | Wed 29/04/26 | Wed 03/06/26
p Hiab 35t day | 1 |  | Wed 29/04/26 | Tue 19/05/26
m Blocks m2 | 200 |  | Wed 29/04/26 | Wed 03/06/26
Second FLR First fix electrical | 760 hrs | 19 days | Thu 04/06/26 | Wed 01/07/26
r Electrical supervisor 3 | 152 hrs |  | Thu 04/06/26 | Wed 01/07/26
r Electrician 9 | 152 hrs |  | Thu 04/06/26 | Wed 01/07/26
r Electrician 10 | 152 hrs |  | Thu 04/06/26 | Wed 01/07/26
r Electrician 11 | 152 hrs |  | Thu 04/06/26 | Wed 01/07/26
r Electrician 12 | 152 hrs |  | Thu 04/06/26 | Wed 01/07/26
Second Flr First fix Plumbing | 680 hrs | 17 days | Thu 02/07/26 | Tue 28/07/26
r Plumbing supervisor 2 | 136 hrs |  | Thu 02/07/26 | Tue 28/07/26
r Plumber 5 | 136 hrs |  | Thu 02/07/26 | Tue 28/07/26
r Plumber 6 | 136 hrs |  | Thu 02/07/26 | Tue 28/07/26
r Plumber 7 | 136 hrs |  | Thu 02/07/26 | Tue 28/07/26
r Plumber 8 | 136 hrs |  | Thu 02/07/26 | Tue 28/07/26
Second FLR First fix Carpentry | 680 hrs | 17 days | Wed 29/07/26 | Mon 24/08/26
r Carpenter supervisor 3 | 136 hrs |  | Wed 29/07/26 | Mon 24/08/26
r Carpenter 9 | 136 hrs |  | Wed 29/07/26 | Mon 24/08/26
r Carpenter 10 | 136 hrs |  | Wed 29/07/26 | Mon 24/08/26
r Carpenter 11 | 136 hrs |  | Wed 29/07/26 | Mon 24/08/26
r Carpenter 12 | 136 hrs |  | Wed 29/07/26 | Mon 24/08/26
Second floor Plasterboard ceiling | 160 hrs | 4 days | Tue 25/08/26 | Fri 28/08/26
r Plasterer supervisor 1 | 32 hrs |  | Tue 25/08/26 | Fri 28/08/26
r Plasterer 1 | 32 hrs |  | Tue 25/08/26 | Fri 28/08/26
r Plasterer 2 | 32 hrs |  | Tue 25/08/26 | Fri 28/08/26
r Plasterer 3 | 32 hrs |  | Tue 25/08/26 | Fri 28/08/26
r Plasterer 4 | 32 hrs |  | Tue 25/08/26 | Fri 28/08/26
m Plaster m2 | 100 |  | Tue 25/08/26 | Fri 28/08/26
Second floor complete plastering | 240 hrs | 6 days | Mon 31/08/26 | Mon 07/09/26
r Plasterer supervisor 2 | 48 hrs |  | Mon 31/08/26 | Mon 07/09/26
r Plasterer 5 | 48 hrs |  | Mon 31/08/26 | Mon 07/09/26
r Plasterer 6 | 48 hrs |  | Mon 31/08/26 | Mon 07/09/26
r Plasterer 7 | 48 hrs |  | Mon 31/08/26 | Mon 07/09/26
r Plasterer 8 | 48 hrs |  | Mon 31/08/26 | Mon 07/09/26
m Plaster m2 | 200 |  | Mon 31/08/26 | Mon 07/09/26
First floor Install Kitchens | 440 hrs | 6 days | Tue 08/09/26 | Tue 15/09/26
r Electrical supervisor 2 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Electrician 5 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Electrician 6 | 40 hrs |  | Wed 09/09/26 | Tue 15/09/26
r Electrician 7 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Electrician 8 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Plumber 5 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Carpenter supervisor 2 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Carpenter 5 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Carpenter 6 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Carpenter 7 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
r Carpenter 8 | 40 hrs |  | Tue 08/09/26 | Mon 14/09/26
m Kitchen per residence | 3 |  | Tue 08/09/26 | Tue 15/09/26
m Plumbing fittings per residence | 3 |  | Tue 08/09/26 | Tue 15/09/26
First floor Install Bathrooms | 360 hrs | 5 days | Wed 16/09/26 | Tue 22/09/26
r Electrical supervisor 3 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Electrician 9 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Electrician 10 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Electrician 11 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Electrician 12 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Plumber 9 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Plumber 10 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Plumber 11 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
r Plumber 12 | 40 hrs |  | Wed 16/09/26 | Tue 22/09/26
m Bahroom per residence | 3 |  | Wed 16/09/26 | Tue 22/09/26
First floor second fix electrical | 160 hrs | 4 days | Wed 23/09/26 | Mon 28/09/26
r Electrical supervisor 2 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Electrician 5 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Electrician 6 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Electrician 7 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Electrician 8 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
m Electrical fittings per residence | 3 |  | Wed 23/09/26 | Mon 28/09/26
First floor second fix Plumbing | 160 hrs | 4 days | Wed 23/09/26 | Mon 28/09/26
r Plumbing supervisor 2 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Plumber 5 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Plumber 6 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Plumber 7 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Plumber 8 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
m Plumbing fittings per residence | 3 |  | Wed 23/09/26 | Mon 28/09/26
First floor second fix Carpentry | 160 hrs | 4 days | Wed 23/09/26 | Mon 28/09/26
r Carpenter supervisor 2 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Carpenter 5 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Carpenter 6 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Carpenter 7 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
r Carpenter 8 | 32 hrs |  | Wed 23/09/26 | Mon 28/09/26
m Timber Pine m2 | 10 |  | Wed 23/09/26 | Mon 28/09/26
First floor Complete tiling | 96 hrs | 4 days | Tue 29/09/26 | Fri 02/10/26
r Tile fitter supervisor 2 | 32 hrs |  | Tue 29/09/26 | Fri 02/10/26
r Tile fitter 3 | 32 hrs |  | Tue 29/09/26 | Fri 02/10/26
r Tile fitter 4 | 32 hrs |  | Tue 29/09/26 | Fri 02/10/26
m Flooring tiles m2 | 10 |  | Tue 29/09/26 | Fri 02/10/26
m Tiles m2 | 10 |  | Tue 29/09/26 | Fri 02/10/26
First Floor Complete decorating | 96 hrs | 4 days | Mon 05/10/26 | Thu 08/10/26
r Decorater supervisor 2 | 32 hrs |  | Mon 05/10/26 | Thu 08/10/26
r Decorater 3 | 32 hrs |  | Mon 05/10/26 | Thu 08/10/26
r Decorater 4 | 32 hrs |  | Mon 05/10/26 | Thu 08/10/26
m finishings per m2 | 100 |  | Mon 05/10/26 | Thu 08/10/26
First floor fit carpets and floor coverings | 120 hrs | 3 days | Fri 09/10/26 | Tue 13/10/26
r Carpenter supervisor 3 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 9 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 10 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 11 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
r Carpet fitter 12 | 24 hrs |  | Fri 09/10/26 | Tue 13/10/26
m Flooring carpet M2 | 50 |  | Fri 09/10/26 | Tue 13/10/26
m Flooring vinyl m2 | 50 |  | Fri 09/10/26 | Tue 13/10/26
Plots 600 to 605 construction complete | 0 hrs | 0 days | Tue 13/10/26 | Tue 13/10/26
Plots 600 to 605 construction complete | 0 hrs | 0 days | Tue 13/10/26 | Tue 13/10/26

## Critical path
Task Name | Start | Finish | Late Start | Late Finish | Free Slack | Total Slack | Critical
Baseline 06.01 | Mon 16/09/24 | Fri 23/10/26 | Mon 16/09/24 | Fri 23/10/26 | 0 days | 0 days | Yes
SA1 Development | Mon 16/09/24 | Fri 23/10/26 | Mon 16/09/24 | Fri 23/10/26 | 0 days | 0 days | Yes
Milestones | Mon 16/09/24 | Fri 23/10/26 | Mon 16/09/24 | Fri 23/10/26 | 0 days | 0 days | Yes
Site resources for project duration | Mon 16/09/24 | Fri 23/10/26 | Mon 16/09/24 | Fri 23/10/26 | 0 days | 0 days | Yes
Site preparation | Mon 16/09/24 | Mon 23/12/24 | Mon 16/09/24 | Mon 23/12/24 | 0 days | 0 days | Yes
Clear site | Mon 16/09/24 | Fri 27/09/24 | Mon 16/09/24 | Fri 27/09/24 | 0 days | 0 days | Yes
Install Site fencing | Mon 30/09/24 | Fri 04/10/24 | Mon 30/09/24 | Fri 04/10/24 | 0 days | 0 days | Yes
Level site | Mon 07/10/24 | Fri 01/11/24 | Mon 07/10/24 | Fri 01/11/24 | 0 days | 0 days | Yes
Install plinths for cabins | Mon 04/11/24 | Tue 05/11/24 | Mon 04/11/24 | Tue 05/11/24 | 0 days | 0 days | Yes
Install generator and temporary utilities | Wed 06/11/24 | Wed 06/11/24 | Wed 06/11/24 | Wed 06/11/24 | 0 days | 0 days | Yes
Install site skips | Mon 11/11/24 | Mon 11/11/24 | Mon 11/11/24 | Mon 11/11/24 | 0 days | 0 days | Yes
Complete CFA piling for all buildings | Tue 12/11/24 | Mon 23/12/24 | Tue 12/11/24 | Mon 23/12/24 | 0 days | 0 days | Yes
Site clearance after construction | Wed 14/10/26 | Fri 23/10/26 | Wed 14/10/26 | Fri 23/10/26 | 0 days | 0 days | Yes
Remove welfare facilities | Wed 14/10/26 | Wed 14/10/26 | Wed 14/10/26 | Wed 14/10/26 | 0 days | 0 days | Yes
Remove site office | Wed 14/10/26 | Wed 14/10/26 | Wed 14/10/26 | Wed 14/10/26 | 0 days | 0 days | Yes
Remove generator and temporary utilities | Wed 14/10/26 | Wed 14/10/26 | Wed 14/10/26 | Wed 14/10/26 | 0 days | 0 days | Yes
Remove temporary plinths | Thu 15/10/26 | Thu 15/10/26 | Thu 15/10/26 | Thu 15/10/26 | 0 days | 0 days | Yes
Remove hoarding | Fri 16/10/26 | Tue 20/10/26 | Fri 16/10/26 | Tue 20/10/26 | 0 days | 0 days | Yes
Remove skips | Wed 21/10/26 | Wed 21/10/26 | Wed 21/10/26 | Wed 21/10/26 | 0 days | 0 days | Yes
Landscape facilities area | Thu 22/10/26 | Fri 23/10/26 | Thu 22/10/26 | Fri 23/10/26 | 0 days | 0 days | Yes
Plots 500 to 508 3 storey x 9 units type 49 | Tue 24/12/24 | Fri 26/12/25 | Tue 24/12/24 | Mon 29/12/25 | 0 days | 0 days | Yes
500 to 508 Foundations, substructures & structural floors | Tue 24/12/24 | Thu 10/07/25 | Tue 24/12/24 | Fri 26/12/25 | 0 days | 0 days | Yes
Drainage | Tue 24/12/24 | Fri 17/01/25 | Tue 24/12/24 | Fri 17/01/25 | 0 days | 0 days | Yes
Excavate trenches for 500 to 508 | Tue 24/12/24 | Wed 01/01/25 | Tue 24/12/24 | Wed 01/01/25 | 0 days | 0 days | Yes
Lay pipes for 500 to 508 | Thu 02/01/25 | Fri 10/01/25 | Thu 02/01/25 | Fri 10/01/25 | 0 days | 0 days | Yes
Backfill trenches 500 to 508 | Mon 13/01/25 | Fri 17/01/25 | Mon 13/01/25 | Fri 17/01/25 | 0 days | 0 days | Yes
Utilities | Mon 20/01/25 | Thu 10/04/25 | Mon 20/01/25 | Fri 26/12/25 | 0 days | 0 days | Yes
Excavate trenches for cables | Mon 20/01/25 | Fri 24/01/25 | Mon 20/01/25 | Fri 24/01/25 | 0 days | 0 days | Yes
Ground FLR Concrete slab | Mon 20/01/25 | Wed 30/04/25 | Mon 20/01/25 | Fri 09/05/25 | 0 days | 0 days | Yes
Lay hardcore base | Mon 20/01/25 | Wed 29/01/25 | Mon 20/01/25 | Wed 29/01/25 | 0 days | 0 days | Yes
Install DPM | Thu 30/01/25 | Fri 14/02/25 | Thu 30/01/25 | Fri 14/02/25 | 0 days | 0 days | Yes
Install Insulation slab | Mon 17/02/25 | Thu 20/02/25 | Mon 17/02/25 | Thu 20/02/25 | 0 days | 0 days | Yes
make and install steel reinforcement cages | Fri 21/02/25 | Thu 06/03/25 | Fri 21/02/25 | Thu 06/03/25 | 0 days | 0 days | Yes
Construct formwork | Fri 07/03/25 | Thu 13/03/25 | Fri 07/03/25 | Thu 13/03/25 | 0 days | 0 days | Yes
Pour concrete slab 500 to 508 | Fri 14/03/25 | Fri 14/03/25 | Fri 14/03/25 | Fri 14/03/25 | 0 days | 0 days | Yes
Staircase & Stairwell 2 | Tue 25/03/25 | Mon 21/04/25 | Tue 25/03/25 | Mon 21/04/25 | 0 days | 0 days | Yes
Erect Ground FLR stairwell 2 scaffolding | Tue 25/03/25 | Tue 25/03/25 | Tue 25/03/25 | Tue 25/03/25 | 0 days | 0 days | Yes
Construct Ground FLR Breeze block Stairwell 2 | Fri 28/03/25 | Tue 01/04/25 | Fri 28/03/25 | Tue 01/04/25 | 0 days | 0 days | Yes
Erect First FLR scaffolding | Wed 02/04/25 | Wed 02/04/25 | Wed 02/04/25 | Wed 02/04/25 | 0 days | 0 days | Yes
Construct First FLR Breeze block Stairwell 2 | Mon 07/04/25 | Wed 09/04/25 | Mon 07/04/25 | Wed 09/04/25 | 0 days | 0 days | Yes
Erect Second FLR scaffolding | Thu 10/04/25 | Thu 10/04/25 | Thu 10/04/25 | Thu 10/04/25 | 0 days | 0 days | Yes
Construct Second FLR Breeze block stairwell 2 | Tue 15/04/25 | Thu 17/04/25 | Tue 15/04/25 | Thu 17/04/25 | 0 days | 0 days | Yes
Dismantle all stairwell 2 scaffolding | Fri 18/04/25 | Mon 21/04/25 | Fri 18/04/25 | Mon 21/04/25 | 0 days | 0 days | Yes
First FLR Structural FLR | Tue 22/04/25 | Fri 30/05/25 | Tue 22/04/25 | Fri 30/05/25 | 0 days | 0 days | Yes
Erect scaffold access | Tue 22/04/25 | Fri 25/04/25 | Tue 22/04/25 | Fri 25/04/25 | 0 days | 0 days | Yes
Install pre cast concrete beams | Mon 28/04/25 | Wed 07/05/25 | Mon 28/04/25 | Wed 07/05/25 | 0 days | 0 days | Yes
Install concrete pre tension blocks | Thu 08/05/25 | Mon 19/05/25 | Thu 08/05/25 | Mon 19/05/25 | 0 days | 0 days | Yes
Dismantle scaffolding access | Tue 20/05/25 | Thu 22/05/25 | Tue 20/05/25 | Thu 22/05/25 | 0 days | 0 days | Yes
Grout gaps | Fri 23/05/25 | Mon 26/05/25 | Fri 23/05/25 | Mon 26/05/25 | 0 days | 0 days | Yes
Screed FLR | Tue 27/05/25 | Fri 30/05/25 | Tue 27/05/25 | Fri 30/05/25 | 0 days | 0 days | Yes
Second FLR Structural FLR | Mon 02/06/25 | Thu 10/07/25 | Mon 02/06/25 | Thu 10/07/25 | 0 days | 0 days | Yes
Erect scaffold access | Mon 02/06/25 | Thu 05/06/25 | Mon 02/06/25 | Thu 05/06/25 | 0 days | 0 days | Yes
Install pre cast concrete beams | Fri 06/06/25 | Tue 17/06/25 | Fri 06/06/25 | Tue 17/06/25 | 0 days | 0 days | Yes
Install concrete pre tension blocks | Wed 18/06/25 | Fri 27/06/25 | Wed 18/06/25 | Fri 27/06/25 | 0 days | 0 days | Yes
Dismantle scaffolding access | Mon 30/06/25 | Wed 02/07/25 | Mon 30/06/25 | Wed 02/07/25 | 0 days | 0 days | Yes
Grout gaps | Thu 03/07/25 | Fri 04/07/25 | Thu 03/07/25 | Fri 04/07/25 | 0 days | 0 days | Yes
Screed FLR | Mon 07/07/25 | Thu 10/07/25 | Mon 07/07/25 | Thu 10/07/25 | 0 days | 0 days | Yes
500 to 508 Walls & Interiors | Thu 01/05/25 | Fri 26/12/25 | Mon 12/05/25 | Fri 26/12/25 | 0 days | 0 days | Yes
Interior walls & Interiors | Thu 01/05/25 | Fri 26/12/25 | Mon 23/06/25 | Fri 26/12/25 | 0 days | 0 days | Yes
Interior Second FLR | Fri 11/07/25 | Fri 26/12/25 | Fri 11/07/25 | Fri 26/12/25 | 0 days | 0 days | Yes
Build interior SF Partition block walls | Fri 11/07/25 | Tue 02/09/25 | Fri 11/07/25 | Tue 02/09/25 | 0 days | 0 days | Yes
Second FLR First fix electrical | Wed 03/09/25 | Tue 23/09/25 | Wed 03/09/25 | Tue 23/09/25 | 0 days | 0 days | Yes
Second Flr First fix Plumbing | Wed 03/09/25 | Tue 23/09/25 | Wed 03/09/25 | Tue 23/09/25 | 0 days | 0 days | Yes
Second FLR First fix Carpentry | Wed 03/09/25 | Tue 23/09/25 | Wed 03/09/25 | Tue 23/09/25 | 0 days | 0 days | Yes
Second floor Plasterboard ceiling | Wed 24/09/25 | Tue 30/09/25 | Wed 24/09/25 | Tue 30/09/25 | 0 days | 0 days | Yes
Second floor complete plastering | Wed 01/10/25 | Fri 10/10/25 | Wed 01/10/25 | Fri 10/10/25 | 0 days | 0 days | Yes
First floor Install Kitchens | Mon 13/10/25 | Tue 28/10/25 | Mon 13/10/25 | Tue 28/10/25 | 0 days | 0 days | Yes
First floor Install Bathrooms | Wed 29/10/25 | Wed 19/11/25 | Wed 29/10/25 | Wed 19/11/25 | 0 days | 0 days | Yes
First floor second fix electrical | Thu 27/11/25 | Wed 03/12/25 | Thu 27/11/25 | Wed 03/12/25 | 0 days | 0 days | Yes
First floor second fix Plumbing | Thu 20/11/25 | Wed 03/12/25 | Thu 20/11/25 | Wed 03/12/25 | 0 days | 0 days | Yes
First floor Complete tiling | Mon 08/12/25 | Mon 15/12/25 | Mon 08/12/25 | Mon 15/12/25 | 0 days | 0 days | Yes
First Floor Complete decorating | Tue 16/12/25 | Tue 23/12/25 | Tue 16/12/25 | Tue 23/12/25 | 0 days | 0 days | Yes
First floor fit carpets and floor coverings | Wed 24/12/25 | Fri 26/12/25 | Wed 24/12/25 | Fri 26/12/25 | 0 days | 0 days | Yes
Plots 500 to 508 construction complete | Fri 26/12/25 | Fri 26/12/25 | Mon 29/12/25 | Mon 29/12/25 | 0 days | 0 days | Yes
Plots 500 to 508 construction complete | Fri 26/12/25 | Fri 26/12/25 | Mon 29/12/25 | Mon 29/12/25 | 0 days | 0 days | Yes
Plots 600 to 605 3 storey x 6 units type 42 | Fri 11/04/25 | Tue 13/10/26 | Mon 29/12/25 | Wed 14/10/26 | 0 days | 0 days | Yes
600 to 605 Foundations, substructures & structural floors | Fri 11/04/25 | Mon 27/04/26 | Mon 29/12/25 | Tue 13/10/26 | 121 days | 121 days | No
Ground FLR Concrete slab | Mon 29/12/25 | Fri 20/02/26 | Mon 29/12/25 | Wed 25/02/26 | 0 days | 0 days | Yes
Lay hardcore base | Mon 29/12/25 | Tue 30/12/25 | Mon 29/12/25 | Tue 30/12/25 | 0 days | 0 days | Yes
Install DPM | Wed 31/12/25 | Wed 31/12/25 | Wed 31/12/25 | Wed 31/12/25 | 0 days | 0 days | Yes
Install Insulation slab | Thu 01/01/26 | Fri 02/01/26 | Thu 01/01/26 | Fri 02/01/26 | 0 days | 0 days | Yes
make and install steel reinforcement cages | Thu 01/01/26 | Wed 07/01/26 | Thu 01/01/26 | Wed 07/01/26 | 0 days | 0 days | Yes
Construct formwork | Mon 05/01/26 | Wed 07/01/26 | Mon 05/01/26 | Wed 07/01/26 | 0 days | 0 days | Yes
Pour concrete slab 500 to 508 | Thu 08/01/26 | Thu 08/01/26 | Thu 08/01/26 | Thu 08/01/26 | 0 days | 0 days | Yes
Staircase & Stairwell | Fri 16/01/26 | Wed 04/02/26 | Fri 16/01/26 | Wed 04/02/26 | 0 days | 0 days | Yes
Erect Ground FLR stairwell 1 scaffolding | Fri 16/01/26 | Fri 16/01/26 | Fri 16/01/26 | Fri 16/01/26 | 0 days | 0 days | Yes
Construct Ground FLR Breeze block Stairwell 1 | Mon 19/01/26 | Wed 21/01/26 | Mon 19/01/26 | Wed 21/01/26 | 0 days | 0 days | Yes
Erect First FLR scaffolding | Thu 22/01/26 | Thu 22/01/26 | Thu 22/01/26 | Thu 22/01/26 | 0 days | 0 days | Yes
Construct First FLR Breeze block Stairwell 1 | Fri 23/01/26 | Tue 27/01/26 | Fri 23/01/26 | Tue 27/01/26 | 0 days | 0 days | Yes
Erect Second FLR scaffolding | Wed 28/01/26 | Wed 28/01/26 | Wed 28/01/26 | Wed 28/01/26 | 0 days | 0 days | Yes
Construct Second FLR Breeze block stairwell 1 | Thu 29/01/26 | Mon 02/02/26 | Thu 29/01/26 | Mon 02/02/26 | 0 days | 0 days | Yes
Dismantle all stairwell 1 scaffolding | Tue 03/02/26 | Wed 04/02/26 | Tue 03/02/26 | Wed 04/02/26 | 0 days | 0 days | Yes
First FLR Structural FLR | Thu 05/02/26 | Tue 17/03/26 | Thu 05/02/26 | Tue 17/03/26 | 0 days | 0 days | Yes
Erect scaffold access | Thu 05/02/26 | Tue 10/02/26 | Thu 05/02/26 | Tue 10/02/26 | 0 days | 0 days | Yes
Install pre cast concrete beams | Wed 11/02/26 | Fri 20/02/26 | Wed 11/02/26 | Fri 20/02/26 | 0 days | 0 days | Yes
Install concrete pre tension blocks | Mon 23/02/26 | Wed 04/03/26 | Mon 23/02/26 | Wed 04/03/26 | 0 days | 0 days | Yes
Dismantle scaffolding access | Thu 05/03/26 | Mon 09/03/26 | Thu 05/03/26 | Mon 09/03/26 | 0 days | 0 days | Yes
Grout gaps | Tue 10/03/26 | Wed 11/03/26 | Tue 10/03/26 | Wed 11/03/26 | 0 days | 0 days | Yes
Screed FLR | Thu 12/03/26 | Tue 17/03/26 | Thu 12/03/26 | Tue 17/03/26 | 0 days | 0 days | Yes
Second FLR Structural FLR | Wed 18/03/26 | Mon 27/04/26 | Wed 18/03/26 | Mon 27/04/26 | 0 days | 0 days | Yes
Erect scaffold access | Wed 18/03/26 | Mon 23/03/26 | Wed 18/03/26 | Mon 23/03/26 | 0 days | 0 days | Yes
Install pre cast concrete beams | Tue 24/03/26 | Thu 02/04/26 | Tue 24/03/26 | Thu 02/04/26 | 0 days | 0 days | Yes
Install concrete pre tension blocks | Fri 03/04/26 | Tue 14/04/26 | Fri 03/04/26 | Tue 14/04/26 | 0 days | 0 days | Yes
Dismantle scaffolding access | Wed 15/04/26 | Fri 17/04/26 | Wed 15/04/26 | Fri 17/04/26 | 0 days | 0 days | Yes
Grout gaps | Mon 20/04/26 | Tue 21/04/26 | Mon 20/04/26 | Tue 21/04/26 | 0 days | 0 days | Yes
Screed FLR | Wed 22/04/26 | Mon 27/04/26 | Wed 22/04/26 | Mon 27/04/26 | 0 days | 0 days | Yes
600 to 605 Walls & Interiors | Mon 23/02/26 | Tue 13/10/26 | Thu 26/02/26 | Tue 13/10/26 | 0 days | 0 days | Yes
Interior walls & Interiors | Mon 23/02/26 | Tue 13/10/26 | Fri 06/03/26 | Tue 13/10/26 | 0 days | 0 days | Yes
Interior First FLR | Mon 23/03/26 | Tue 13/10/26 | Mon 23/03/26 | Tue 13/10/26 | 0 days | 0 days | Yes
Build interior FF Partition block walls | Mon 23/03/26 | Fri 12/06/26 | Mon 23/03/26 | Fri 12/06/26 | 0 days | 0 days | Yes
First FLR First fix electrical | Thu 18/06/26 | Tue 21/07/26 | Thu 18/06/26 | Tue 21/07/26 | 0 days | 0 days | Yes
First floor Plasterboard ceiling | Wed 22/07/26 | Mon 27/07/26 | Wed 22/07/26 | Mon 27/07/26 | 0 days | 0 days | Yes
First floor complete plastering | Tue 28/07/26 | Tue 04/08/26 | Tue 28/07/26 | Tue 04/08/26 | 0 days | 0 days | Yes
First floor Install Kitchens | Wed 05/08/26 | Thu 27/08/26 | Wed 05/08/26 | Thu 27/08/26 | 0 days | 0 days | Yes
First floor Install Bathrooms | Fri 28/08/26 | Thu 03/09/26 | Fri 28/08/26 | Thu 03/09/26 | 0 days | 0 days | Yes
First floor second fix electrical | Fri 04/09/26 | Wed 16/09/26 | Fri 04/09/26 | Wed 16/09/26 | 0 days | 0 days | Yes
First floor second fix Plumbing | Fri 04/09/26 | Wed 16/09/26 | Fri 04/09/26 | Wed 16/09/26 | 0 days | 0 days | Yes
First floor second fix Carpentry | Fri 04/09/26 | Wed 16/09/26 | Fri 04/09/26 | Wed 16/09/26 | 0 days | 0 days | Yes
First floor Complete tiling | Fri 25/09/26 | Wed 30/09/26 | Fri 25/09/26 | Wed 30/09/26 | 0 days | 0 days | Yes
First Floor Complete decorating | Thu 01/10/26 | Thu 08/10/26 | Thu 01/10/26 | Thu 08/10/26 | 0 days | 0 days | Yes
First floor fit carpets and floor coverings | Fri 09/10/26 | Tue 13/10/26 | Fri 09/10/26 | Tue 13/10/26 | 0 days | 0 days | Yes
Interior Second FLR | Wed 29/04/26 | Tue 13/10/26 | Wed 29/04/26 | Tue 13/10/26 | 0 days | 0 days | Yes
Build interior SF Partition block walls | Wed 29/04/26 | Wed 03/06/26 | Wed 29/04/26 | Wed 03/06/26 | 0 days | 0 days | Yes
Second FLR First fix electrical | Thu 04/06/26 | Wed 01/07/26 | Thu 04/06/26 | Wed 01/07/26 | 0 days | 0 days | Yes
Second Flr First fix Plumbing | Thu 02/07/26 | Tue 28/07/26 | Thu 02/07/26 | Tue 28/07/26 | 0 days | 0 days | Yes
Second FLR First fix Carpentry | Wed 29/07/26 | Mon 24/08/26 | Wed 29/07/26 | Mon 24/08/26 | 0 days | 0 days | Yes
Second floor Plasterboard ceiling | Tue 25/08/26 | Fri 28/08/26 | Tue 25/08/26 | Fri 28/08/26 | 0 days | 0 days | Yes
Second floor complete plastering | Mon 31/08/26 | Mon 07/09/26 | Mon 31/08/26 | Mon 07/09/26 | 0 days | 0 days | Yes
First floor Install Kitchens | Tue 08/09/26 | Tue 15/09/26 | Tue 08/09/26 | Tue 15/09/26 | 0 days | 0 days | Yes
First floor Install Bathrooms | Wed 16/09/26 | Tue 22/09/26 | Wed 16/09/26 | Tue 22/09/26 | 0 days | 0 days | Yes
First floor second fix electrical | Wed 23/09/26 | Mon 28/09/26 | Wed 23/09/26 | Mon 28/09/26 | 0 days | 0 days | Yes
First floor second fix Plumbing | Wed 23/09/26 | Mon 28/09/26 | Wed 23/09/26 | Mon 28/09/26 | 0 days | 0 days | Yes
First floor second fix Carpentry | Wed 23/09/26 | Mon 28/09/26 | Wed 23/09/26 | Mon 28/09/26 | 0 days | 0 days | Yes
First floor Complete tiling | Tue 29/09/26 | Fri 02/10/26 | Tue 29/09/26 | Fri 02/10/26 | 0 days | 0 days | Yes
First Floor Complete decorating | Mon 05/10/26 | Thu 08/10/26 | Mon 05/10/26 | Thu 08/10/26 | 0 days | 0 days | Yes
First floor fit carpets and floor coverings | Fri 09/10/26 | Tue 13/10/26 | Fri 09/10/26 | Tue 13/10/26 | 0 days | 0 days | Yes
Plots 600 to 605 construction complete | Tue 13/10/26 | Tue 13/10/26 | Wed 14/10/26 | Wed 14/10/26 | 0 days | 0 days | Yes
Plots 600 to 605 construction complete | Tue 13/10/26 | Tue 13/10/26 | Wed 14/10/26 | Wed 14/10/26 | 0 days | 0 days | Yes