| What | Why | Who | Where | When | Cost |
| --- | --- | --- | --- | --- | --- |
| Recommendation 1: Engage Therapies staff with being an active bystander. |  |  |  |  |  |
| Equip staff with the skills and techniques to be an active bystander through training (Active Bystander, 2022). Apply nudge theory to promote the use of active bystander techniques. | Educating staff can raise awareness and increase ability to have difficult conversations (Howard & Embree, 2020). Bystander training can prompt effective behaviours when witnessing incivility (Kuntz & Searle, 2023). Although meta-analyses have found that research is mixed on educating staff (Armstrong, 2018), active bystander training delivered to other staff was successful (HDdUHB, 2022). To ensure that habits are built staff should be subtly prompted to behave effectively (Kotter, 2023). Nudge theory can be applied to influence staff and encourage desired behaviours (Abbas, 2023). | HR, external provider, therapies staff HR | Training on Microsoft Teams platform as the organisation already owns this resource and it will avoid milage costs. In staff areas across sites and via Hapi notifications. | Train staff by 12/01/24 02/02/24 | Time Administration assistant:- - arrange and manage sessions (£12.45 x 7= £87.15) - create posters and print (£12.45 x 2 = £24.90). - schedule Hapi notifications (£12.45) Resources Active Bystander Training:- - hire active bystander training slots (6 sessions = £200) Posters - (100x £0.30 =£30) Total= £354.50 |
| Recommendation 2: Support line managers to effectively manage incivility. |  |  |  |  |  |
| Utilise webinars to ensure that managers are aware of resources available to support them with managing healthy working relationships and enabling healthy workplace cultures and develop their skills to manage incivility and conflict resolution. | To encourage active bystanders and reporting of incivility, leaders should be trained and supported on effectively managing incivility (Young, 2020). Leaders must role model being an active bystander (Kuntz & Searle, 2023) and foster a positive culture of trust (Paull, et al, 2020). | HR, Managers | Webinars conducted via Microsoft Teams for the above reasons. | 23/02/24 | Time OD Facilitator - Develop, promote and deliver webinar for managers (£21.80 x 37 = £806.60) Resources - Microsoft Teams is already in place Total= £806.60 |
| Recommendation 3: Hold focus groups with Therapies staff to listen to staff and glean further insight about how to support positive workplace culture. |  |  |  |  |  |
| Hold focus groups with therapies staff which aim to listen to staff experience in the workplace and support them to develop a positive workplace culture. | Staff that feel supported with instances of incivility are less affected by it (He et al, 2020). Culture is complex and the surface level is not a true reflection of the true culture (Schein, 1985). Listening to staff voice will engage staff with the process (Peters, 2022) and enable the organisation to better understand the culture and how best to support a positive culture (CIPD, 2012). | HR, Therapies staff | Face to face in each county. | Conduct on agreed dates through March 2024. | Time OD Facilitators - Develop, deliver and action sessions (£21.80 x 73 = £817.50) Resources - Hire of venues ( £120 x3 = £360) Total = £1177.50 |
| Benefits Analysis Whilst the total cost of this plan would be £2338.60, the benefits of outlaying this money include potential to increase productivity and improve employee experience, reduce turnover rates and improve patient care (Martin & Zadinsky, 2022). Which is significant for HDdUHB as it strives to reduce turnover and provide the best possible patient care (Gostling, 2020). Whilst costs differ for organisations, the consequences of incivility can cost organisations tens of thousands per staff member (Laschinger, 2014). Given the current cost saving measures in place (Morgan, 2022), the potential savings could support HDdUHB to make cost savings over time. |  |  |  |  |  |

It is proposed that HR continually monitor progress and obtain staff voice one year after implementation to evaluate and provide additional support where necessary (Kotter, 2023).

References

Abbas, T. (2023) Nudge theory in the workplace – influencing employees behaviour. Change Management Insight. Available at: https://changemanagementinsight.com/nudge-theory-in-the-workplace-influencing-employees-behaviour/ (Accessed: 9th October 2023).

Active Bystander (2022). How we can help you. The Active bystander training company. Available at: https://www.activebystander.co.uk/how-we-can-help-you/ (Accessed: 6th October 2023).

Armstrong, N. (2018) ‘Management of Nursing Workplace Incivility in the Health Care Settings: A Systematic Review’, Workplace Health & Safety, 66(8), pp. 403–410. Available at: https://doi.org/10.1177/2165079918771106. (Accessed: 6th October 2023).

CIPD. (2012) Leading culture change: employee engagement and public service transformation. CIPD. Available at: https://www.cipd.org/globalassets/media/knowledge/knowledge-hub/reports/leading-culture-change-employee-engagement-and-public-service-transformation_2012_tcm18-14116.pdf  (Accessed: 9th October 2023).

Gostling, L. (2020). ‘Workforce, Organisational Development and Education Strategy 2020-2030.’ Hywel Dda University Health Board. Unpublished.

He, Y, Walker, J, Payne, S, and Miner, K. (2020) ‘Explaining the negative impact of workplace incivility on work and non‐work outcomes: The roles of negative rumination and organizational support’, Stress and Health, 37(2), pp. 297–309. Available at: https://doi.org/10.1002/smi.2988. (Accessed: 5th October 2023).

Howard, M.S. and Embree, J.L. (2020) ‘Educational Intervention Improves Communication Abilities of Nurses Encountering Workplace Incivility’, The Journal of Continuing Education in Nursing, 51(3), pp. 138–144. Available at: https://doi.org/10.3928/00220124-20200216-09. (Accessed: 17th March 2023).

Hywel Dda University Health Board. (2022) Active bystander training. Hywel Dda University Health Board. Internal document. Unpublished.

Kotter, J. (2023) The 8 steps for leading change. Kotter. Available at: https://www.kotterinc.com/methodology/8-steps/  (Accessed: 5th October 2023).

Kuntz, J.C. and Searle, F. (2023) ‘Does Bystander Intervention Training Work? When Employee Intentions and Organisational Barriers Collide’, Journal of Interpersonal Violence, 38(3-4), pp. 2934–2956. Available at: https://doi.org/10.1177/08862605221104530. (Accessed: 6th October 2023).

Laschinger, H, Cummings G, Wong, G, Grau, A. (2014) ‘Resonant leadership and workplace empowerment: the value of positive organizational cultures in reducing workplace incivility’, Nursing economic, 32(1), pp. 5–15. Available at: https://www.proquest.com/docview/1508688469?parentSessionId=CkcU51Di%2FZ5u9UHU119RMbwkgbah4VwP%2Br7RSnuvVHQ%3D&pq-origsite=primo&accountid=130472  (Accessed: 10th October 2023).

Martin, L.D. and Zadinsky, J.K. (2022) ‘Frequency and outcomes of workplace incivility in healthcare: A scoping review of the literature’, Journal of nursing Management, 30(7), pp. 3496–3518. Available at: https://doi.org/10.1111/jonm.13783. (Accessed: 17th March 2023).

Morgan, E. (2022). Written statement: Escalation and intervention arrangements. Welsh Government. Available at: https://www.gov.wales/written-statement-escalation-and-intervention-arrangements-3  (Accessed: 4th October 2023).

Paull, M, Omari, M, D’Cruz, P, Cangarli, B.G. (2020) ‘Bystanders in workplace bullying: working university students’ perspectives on action versus inaction’, Asia Pacific journal of human resources, 58(3), pp. 313–334. Available at: https://doi.org/10.1111/1744-7941.12216. (Accessed: 6th October 2023).

Peters, R. (2022) Employee voice. CIPD. Available at: https://www.cipd.org/uk/knowledge/factsheets/voice-factsheet/  (Accessed: 9th October 2023).

Schein, E.H. (1985) Organizational culture and leadership. San Francisco: Jossey-Bass.

Young, J. (2020). ‘Workplace bullying: the role of the bystander.’ CIPD. Available at: https://www.cipd.org/uk/knowledge/bitesize-research/workplace-bullying-bystander/ (Accessed: 6th October 2023).