## Responsibility Charting

What is it and how can it help me? 

This is a simple tool that you can use it to make sure that everyone is clear about roles and responsibilities. It works well within teams, between teams, for strategic management and for project management settings.   

Responsibility charting will help you to:

- Clarify any confusion, assumptions and misunderstandings about ‘who does what'

- Make sure that someone is responsible for each task

- Identify who needs to be given communication about each task

- Prevent duplication of effort

It can unearth a range of issues, including gaps in responsibility, misunderstanding, miscommunication and areas where too many people are given responsibility for the same thing.

There are two ways that this tool can help you:

1. Ensuring clarity about who is responsible for what in an operational setting

A lack of clarity about who is responsible for what, in an operational setting, leads to wasting time and confusion.

2. Ensuring clarity about who is responsible for what in project or change management

How often are the same old things discussed and agreed but never taken forward? Achieving improvement will depend upon good project management: you will need to be clear who is responsible for what action.

When does it work best?

Use this tool during the initial planning stages and at any time that roles and responsibilities seem unclear

How to use it

Approach

In an operational setting you should develop responsibility charts based on how processes and associated tasks are carried out, not according to the status and authority of the people who are listed against the process. For example, even though a functional unit manager may have overall responsibility for the way the team operates, everyone has day-to-day responsibilities for tasks and decision making. You should be aiming to display ‘how things work' on the chart.

If there are underlying issues, within a team that make completing the chart difficult an experienced external facilitator may be best placed to help you.

In a project management setting, use this tool when forming project teams and delegating tasks. This means that you can use this as a reference point to check if things get done or don't happen.

Developing a responsibility chart

1. List activities or tasks 
List the activities in the matrix, these are the row headings.  For example:

- Developing budgets, allocating resources eg discharge planning

- Deciding when a patient is ready for discharge

- Getting take home medications ready

- Informing patient about what is happening

- Giving information to patients about who to contact if there is a problem

- Informing transport etc

2. List the people involved

List all the people involved in the process, they are the column headings. They will include:

- People directly involved in the process

- Managers and committees who apply controls on the process

- Other people who may impact the performance of the process

3. Identify each person's responsibility with respect to the activity

Working across each row, taking each activity in turn, discuss and identify each person's role and responsibility.

Beckhard and Harris (1977) described four roles:

(i) Responsibility - the responsibility to initiate action to ensure that activities/decisions are carried out. For example, it would be a department head's responsibility (R) to initiate preparation of the departmental budget or a significant change in academic direction.

(ii) Approval required or the right to veto (A-V) - the particular item must be reviewed by the particular role occupant; this person has the option of either vetoing or approving it.

(iii) Support (S) - providing personal or logistical support and resources for the particular item.

(iv) Inform (I) - must be informed and, by inference, cannot influence.

It is also useful to indicate if someone is not involved with a dash (-).

Beckhard and Harris's guidelines for making the technique more effective:

- Assign responsibility to only one person. That person initiates and then is responsible and accountable for that activity or task

- Avoid having too many people with an approval-veto function on any single item. This will slow down task completion or will negate it altogether

- If one person has approval-veto involvement on most decisions, that person could create a bottleneck which inhibits progress

- The support function is critical. A person with this role has to provide resources or produce something that is then used by the person responsible for the task. This support role and its specific demands must be clarified and clearly assigned

- - a person may want to exercise a veto on an item, but not really need it 
    - a person may not want to support responsibility on an item, but should take on that role. 
    - two people each want responsibility on a particular item, but only one can have it.

- At times the assignment of functions  to individuals becomes difficult and will require discussion. For example: See the illustration of a completed grid below

Examples

If a patient doesn't turn up for their appointment, who is responsible for what?

Before:

| Individual | Mani | Jo | Lou | Matt |
| --- | --- | --- | --- | --- |
| Decision / Role | Information Manager | Reception | Matron | Dr |
| Tell clinical staff that the patient hasn't turned up | - | Responsible | Informed | Informed |
| Find out why the patient didn't turn up | - | - | - | - |
| Decision to make another appointment (according to protocol) | - | - | - | Responsible |
| Send appointment letter | - | Responsible | - | - |
| Monitor the number of patients who don't turn up and why they don't turn up | Responsible | - | - | - |

In this example, no one is responsible for finding out why a patient didn't turn up. This is inefficient and may result in booking new appointments, which the patient will not attend yet again.

The doctor is responsible for deciding about making a new appointment, but is this always necessary? The information manager monitors the fact that the patient does not turn up, but is not responsible for feeding back patterns to the clinic.

Discussion may highlight these sorts of issues, identifying gaps in roles as well as opportunities for more efficient decision making. The final chart could look like this:

After:

| Name | Mani | Jo | Lou | Matt |
| --- | --- | --- | --- | --- |
| Role | Information Manager | Reception | Matron | Dr |
| Tell clinical staff that the patient hasn't turned up | - | Responsible | Informed | Informed |
| Find out why the patient didn't turn up | Informed | Responsible | Informed | Informed |
| Decision to make another appointment | - | Support | Responsible | Approval - veto |
| Send appointment letter | - | Responsible | - | - |
| Monitor the number of patients who don't turn up and why they don't turn up | Responsible | Support | Informed | Informed |