|  | Action/Strategy | Resources Needed | Person(s) Responsible | Success Criteria | Monitoring and evaluation | Start | Finish |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Creating a sense of Urgency | ## Have discussions with all stakeholders about the necessity of making speedy changes to the current way things are done, in an effort to create a sustainability culture at B.H.S | ## Human resources | ## Principal | ## 75% of stakeholders agree that there is an urgency to have a sustainability culture embedded at the school. | ## Observations ## Direct questioning Presentations, classrom debates | ## September 2023 | ## December 2023 |
| - Form a powerful Coalition | - Set up a Sustainability Teams - The sponsor: The minister of education, Sustainabible Department - The guiding team - The change team |  | Principal School Management Team | All the committes are set up and are in dialogue. | Observations, interviews, discussions | September 2023 | December 2023 |
| Create a vision for change | Work colloborately to formulate a vision for sustainability which aligns with the school’s motto |  | Coalition Teams All stakeholders | The vision aligns and matches the policies of the ministry of education and the laws of SVG | Checklist to ascertain that this vision is being seen, Posters, social media, daily announcements at assemblies |  |  |
| Communicate the vision | Communicate the vision to all stakeholders including the community in which the school operates |  | All stakeholders | The vision is seen and echoed in and around the Bethel High School | Open discussions, workshops, town hall meetings |  |  |
| Empower actions | Network with Known advocates of sustainability Get feedback from stakeholders about resistance to creating a sustainability culture at Bethel High School. Recognition Day for those who are working to implement this change Training and coaching of those who are in need |  | Principal, Sponsors Sustainability team | Atleast 20% of those resistant to creating a sustainability culture are no longer resistant. | Observations, discussions, Hard talks | January,2024 | January 2024 |
| Create short term wins | Best kept school garden competitions, Compost program Waste reduction compaigns Reduction of energy |  |  | 80% of students and teachers are enthusiastic and take part in the competitions and compaigns | Checklist obervations | January 2024 | Continious |
| Build on the change | Be the catalyst who empowes other schools to creating sustainability cultures |  |  | Other schools become aware of the need for sustainability and would look at us as pioneers for sustainability in schools. |  | September 2024 | Continious |
| Anchor changes | Embedding sustainability into the culture of teachers and students soo that it transcends into the community. outside the walls of the school Having the school be known as the first sustainability school in the nation. Curriculum which teaches sustainability, Challenge the nearby Technicl Institute to create a sustainability |  |  |  |  |  |  |

Executive Summary

Bethel High School is a secondary school found on the island of St. Vincent and the Grenadines. The school is headed by the government of the country through the Ministry of Education portfolio. There are  five hundred and eighty four (584) students and fifty four (54 )teachers at this educational institution.  The current situation at this educational instition does not reflect sustainability in practice or theory . Therefore, in an effort to lead a sustainability change, Bethel High School through its principal, will use Kotter’s 8 step model design  to create a  plan with anticpation of creating  and leading  a sustainability culture. The intended targets are stakeholders such teachers, students, parents and the Ministry of Education.

Introduction

McFarlane and Ogazon (2011) opined that there is a need for transformation in the modus operandi at educational institutions in order for sustainability to become a reality. This transformation will require stakeholders in education to realize that there must be a shift in the way things are done and take the necessary steps to champion sustainability.  Furthermore, Aung and Hallinger (2023) argued that sustainability leadership is crucial in addressing current environmental challenges and empowering the next generation to become responsible global citizens. High schools are therefore pivotal in nurturing sustainability practices and mindsets among students. This report outlines a comprehensive change plan to establish a sustainability culture at the Bethel High School, guided by Kotter’s 8 Steps Change Model. It will evaluate how each step can be utilized to establish a sustainability culture at B.H.S, including raising awareness, building a guiding coalition, mobilizing commitment, creating a vision, empowering action, generating short term wins, consolidating gains, and achoring new practices. The significance of this report lies in its potential to inspire other educational institutions in St. Vincent and the Grenadines to embed sustainability as a core value and inspire teachers and students to drive the sustainability cause.