Alexandra Gheorghe 2117801

Planning and Delivering an International Meeting.

International Meetings Management BMIH6007

Kathryn Flynn

Contents

Introduction	3

Key Focus Areas	3

The Event Cycle	4

Application to the International Meeting on Sustainable Development in the Digital Age	4

Event Concept	5

Itinerary	5

Aim and Objectives of the Meeting / Event	6

SMART Objectives	7

Skills Required	8

Resources Needed	9

Breakdown of Costs	10

Breakdown of Income	11

Funding Sources	12

Income Generation Strategies	13

Trends	14

Issues	15

Impacts	15

References	17

# Introduction

Event Description and Background The "International Meeting on Sustainable Development in the Digital Age," organized by Sustainable Tech Solutions, is a premier event aimed at addressing the intersection of sustainable development and digital technology. This event is strategically chosen due to its critical relevance in tackling global challenges such as climate change, resource depletion, and social inequality. Scheduled to be held in Nottingham, a city recognized for its commitment to sustainability and technological innovation, the event will serve as a platform to bring together a diverse group of stakeholders, including experts, policymakers, researchers, and activists. The primary objective is to catalyze actionable solutions towards a sustainable future by leveraging the transformative power of technology.

About Us Sustainable Tech Solutions is a leading organization dedicated to promoting sustainable development and technological innovation on a global scale. Founded in 2024, we specialize in organizing conferences, events, and initiatives that unite experts, stakeholders, and thought leaders to explore solutions to pressing environmental and social issues.

## Key Focus Areas

Sustainable Development: Advocating for practices that balance economic growth, social equity, and environmental protection.

Technology Innovation: Utilizing the transformative power of technology to address global challenges such as climate change, resource depletion, and social inequality.

Collaboration and Networking: Facilitating collaboration and knowledge-sharing among diverse stakeholders, including government agencies, NGOs, academia, industry leaders, and grassroots organizations.

Our Event: International Meeting on "Sustainable Development in the Digital Age"

Theme: "Harnessing Technology for Environmental and Social Progress"

Objective: To explore the intersection of sustainable development and digital technology, identify innovative solutions, and catalyze action towards a more sustainable future.

Audience: Professionals, policymakers, researchers, entrepreneurs, activists, and other stakeholders passionate about sustainable development and technology.

Format: Keynote speeches, panel discussions, workshops, networking sessions, and exhibits highlight innovative technologies and sustainable initiatives.

Date and Venue: 31st May 2024 at Motorpoint Arena, Nottingham, United Kingdom

Website: www.stechs.co.uk

## The Event Cycle

Event Cycle Definition The event cycle refers to the comprehensive stages an event goes through from its inception to completion and post-event evaluation. According to Bladen et al. (2012), the event cycle consists of five primary stages: initiation, planning, implementation, event execution, and closure.

# Application to the International Meeting on Sustainable Development in the Digital Age

Initiation: During this stage, the event’s scope, purpose, and objectives are defined. For the "International Meeting on Sustainable Development in the Digital Age," this involved establishing the theme of harnessing technology for environmental and social progress and setting clear objectives to explore innovative solutions and foster collaboration.

Planning: This phase includes detailed logistical planning, budgeting, and marketing strategies. Key activities involve selecting a sustainable venue, coordinating with speakers, and developing promotional materials to attract attendees.

Implementation: In this stage, plans are put into action. This includes setting up the venue, finalizing attendee lists, coordinating with vendors, and ensuring all logistical details are in place.

Event Execution: This is the event’s actual occurrence, where scheduled activities such as keynote speeches, panel discussions, workshops, and exhibitions take place. Effective management during this phase ensures that the event runs smoothly, and any real-time issues are promptly addressed.

Closure: The final stage involves post-event activities like collecting feedback, conducting evaluations, financial reconciliation, and reporting on the event’s outcomes. This helps in understanding the event’s impact and areas for improvement (Bowdin et al., 2023).

## Event Concept

About the Event the "International Meeting on Sustainable Development in the Digital Age" aims to address the intersection of sustainable development and digital technology. This event is designed to bring together a diverse group of stakeholders to explore and promote innovative solutions that leverage technology to address environmental and social challenges.

## Itinerary

Day 1:

9:00 AM - Opening Ceremony

10:00 AM - Keynote Speech by Renowned Expert

11:30 AM - Panel Discussion: "Tech Innovations for Sustainability"

1:00 PM - Lunch Break

2:00 PM - Workshop: "Implementing Sustainable Practices"

4:00 PM - Networking Session

6:00 PM - End of Day 1

Day 2:

9:00 AM - Welcome Address

9:30 AM - Presentation: "Digital Solutions to Climate Change"

11:00 AM - Break

11:30 AM - Interactive Session: "Collaborative Efforts for Social Equity"

1:00 PM - Lunch Break

2:00 PM - Exhibit Tour: Showcasing Sustainable Technologies

4:00 PM - Closing Remarks

Delegate Experience Delegates attending the event will experience a comprehensive program that includes:

Keynote Speeches: Insights from leading experts in sustainable development and technology.

Panel Discussions: Interactive sessions on diverse topics related to sustainability and innovation.

Workshops: Hands-on sessions designed to enhance skills and knowledge.

Networking Sessions: Opportunities to connect with peers and industry leaders to foster collaborations.

Exhibits: Highlighting innovative technologies and sustainable initiatives, providing a platform for companies and organizations to present their innovations.

The concept of the event is to create an immersive and engaging environment where attendees can gain knowledge, share experiences, and collaborate on sustainable solutions. By focusing on both sustainable development and technological innovation, the event aims to drive forward-thinking discussions and practical actions towards a sustainable future (O’Toole, 2008).

## Aim and Objectives of the Meeting / Event

Aim The overarching aim of the "International Meeting on Sustainable Development in the Digital Age" is to explore and promote the integration of digital technology and sustainable development to address global environmental and social challenges. This aligns with Sustainable Tech Solutions' mission to leverage innovation, collaboration, and sustainability principles to create a better world for current and future generations (Sustainable Tech Solutions, n.d.).

## SMART Objectives

Increase Awareness

Specific: Raise awareness about the potential of digital technology in promoting sustainability among event attendees.

Measurable: Achieve a 90% satisfaction rate in post-event surveys regarding the knowledge gained on sustainable development technologies.

Achievable: Ensure all keynote speeches and panel discussions focus on practical examples and case studies.

Relevant: Aligns with the event’s theme and the organization’s mission.

Time-bound: By the end of the two-day event.

Facilitate Collaboration

Specific: Create networking opportunities for stakeholders to collaborate on sustainable initiatives.

Measurable: Facilitate at least 50 new partnerships or collaborations between attendees by the event’s conclusion.

Achievable: Organize structured networking sessions and workshops aimed at fostering connections.

Relevant: Collaboration is crucial for advancing sustainable development goals.

Time-bound: By the end of the event.

Showcase Innovations

Specific: Present innovative technologies and solutions that contribute to sustainable development.

Measurable: Feature at least 30 exhibitors highlighting innovative technologies and sustainable initiatives.

Achievable: Curate a diverse and relevant exhibitor list and provide adequate exhibition space.

Relevant: Demonstrating real-world applications of technology in sustainability.

Time-bound: During the exhibition sessions on both days of the event.

Event Operations

Successfully organizing the "International Meeting on Sustainable Development in the Digital Age" will need a wide range of abilities and resources in order to guarantee smooth operation and meet the event's goals. The necessary abilities and supplies for the event are listed below.

## Skills Required

Event Planning and Management

Expertise in coordinating various aspects of the event, including scheduling, coordination, and on-site management. Effective event planning ensures that all elements come together smoothly (Grant, 2005).

Technical Support

Skilled IT professionals to manage audiovisual (AV) equipment, digital platforms, and virtual participation options. This includes setting up and troubleshooting equipment, managing live streaming, and ensuring a seamless technological experience for both in-person and virtual attendees (Creative Tenders, 2021).

Communication and Marketing

Effective communication skills are essential for promoting the event, engaging with stakeholders, and facilitating clear and effective information dissemination. Marketing professionals will develop and execute promotional strategies to attract attendees and sponsors (O’Toole, 2008).

Sustainability Expertise

Knowledge of sustainable practices and the ability to integrate these into the event planning process. This includes selecting eco-friendly materials, implementing waste reduction strategies, and ensuring the event aligns with sustainability principles (Bladen et al., 2012).

Networking and Facilitation

Skills in networking and facilitating discussions to promote collaboration among attendees. This involves organizing and managing networking sessions, workshops, and panel discussions to maximize participant engagement and partnership opportunities (Quick, 2020).

## Resources Needed

Venue

A facility with adequate space and modern amenities that aligns with the event’s sustainability goals. The venue should have sufficient capacity for all planned activities, including keynote speeches, panel discussions, workshops, and exhibitions (Bowdin et al., 2023).

Catering

Catering services that provide sustainable, locally sourced, and diverse food options. This ensures that the event supports local businesses and aligns with its sustainability objectives (Bladen et al., 2012).

Audiovisual Equipment

High-quality AV equipment, including microphones, projectors, screens, and live streaming capabilities. Reliable technical support will be required to manage this equipment throughout the event (Grant, 2005).

Marketing Materials

Digital and print materials for promoting the event, such as brochures, social media content, email newsletters, and banners. These materials will help attract attendees and sponsors, and keep them informed about event details (O’Toole, 2008).

Staff and Volunteers

A team of trained staff and volunteers to handle various tasks, including registration, attendee assistance, coordination management, and technical support. Ensuring adequate staffing levels is crucial for smooth event operations (Quick, 2020).

Transportation and Accommodation

Arrangements for eco-friendly transportation options for attendees, such as shuttle services or promoting the use of public transport. Additionally, partnerships with local hotels for accommodation can enhance attendee experience and convenience (Creative Tenders, 2021).

Sustainable Materials

Use of sustainable materials for event signage, décor, and other physical elements. This includes recyclable or reusable materials that minimize environmental impact (Bladen et al., 2012).

By leveraging these skills and resources, Sustainable Tech Solutions aims to deliver an impactful and smoothly executed event that not only meets its objectives but also sets a benchmark for sustainability in event management.

Event Budget

A comprehensive event budget is crucial to ensure the financial success and sustainability of the "International Meeting on Sustainable Development in the Digital Age." Below is a detailed breakdown of the income and expenditure, along with an explanation of costs, funding sources, and income generation strategies.

## Breakdown of Costs

Expenditure

Venue Rental: £16,000

The cost for renting a facility that aligns with the event's sustainability goals and provides adequate space and amenities for all activities (Getz, 2007).

Staff Salaries: £12,000

Compensation for event staff including planners, coordinators, and support personnel to ensure smooth operations (Silvers, 2008).

Marketing Expenses: £8,000

Costs for promoting the event through digital advertising, print materials, social media campaigns, and email marketing to attract attendees and sponsors (Hoyle, 2002).

Catering: £9,600

Provision of sustainable, locally sourced, and diverse food options for attendees to support local businesses and align with the event’s sustainability objectives (Allen et al., 2011).

Equipment Rental (AV, lighting, etc.): £6,400

Rental of high-quality audiovisual equipment and lighting necessary for presentations, workshops, and live streaming (Shone & Parry, 2010).

Administrative Costs: £4,000

General administrative expenses including office supplies, printing, signage, and other miscellaneous costs (Goldblatt, 2011).

Miscellaneous Expenses: £4,000

Additional unforeseen expenses that may arise during the planning and execution of the event (Masterman, 2009).

Total Expenditure: £60,000

## Breakdown of Income

Income

Registration Fees: £74,000

Revenue generated from attendees registering for the event. This includes regular attendees, students, and early bird registrations (Shone & Parry, 2010).

Regular Attendees (200 participants x £240): £48,000

Student Attendees (50 participants x £120): £6,000

Early Bird Discount (100 participants x £200): £20,000

Sponsorships: £60,000

Funds from corporate sponsors who gain visibility and promotional benefits by supporting the event (Allen et al., 2011).

Platinum Sponsorship: £24,000

Gold Sponsorship: £16,000

Silver Sponsorship: £12,000

Bronze Sponsorship: £8,000

Partnerships: £8,000

Financial support from partnerships with organizations that have a personnel stake in sustainable development and technology (Masterman, 2009).

Exhibitor Fees: £4,000

Fees charged to companies and organizations that highlight their products, services, or research findings at the event (Hoyle, 2002).

Other Revenue Sources: £2,000

Additional income from merchandise sales, optional workshops, and other value-added services (Getz, 2007).

Total Income: £148,000

## Funding Sources

Corporate Sponsorships

Engaging companies that align with the event’s theme and offering them various levels of visibility and benefits to incentivize their support (Allen et al., 2011).

Grants

Applying for grants from government agencies and non-profit organizations that support sustainability initiatives. Although this example assumes no grants, they can be a significant source of funding (Goldblatt, 2011).

Registration Fees

Charging attendees for participating in the event, with tiered pricing to accommodate distinct categories of attendees and encourage early registration (Shone & Parry, 2010).

Partnerships

Forming strategic partnerships with relevant organizations to share resources, co-host the event, or provide financial support (Masterman, 2009).

Exhibitor Fees

Charging companies and organizations for the chance to exhibit their products and services, giving them with a platform to reach a targeted audience (Hoyle, 2002).

Other Revenue Sources

Generating additional revenue through merchandise sales, optional workshops, and networking events (Getz, 2007).

## Income Generation Strategies

Tiered Pricing

Offering different registration packages at varying price points to accommodate different attendee categories and encourage early registration through discounts (Shone & Parry, 2010).

Sponsorship Packages

Developing comprehensive sponsorship packages with attractive benefits to incentivize companies to sponsor the event at various levels (Allen et al., 2011).

Strategic Partnerships

Collaborating with relevant organizations to co-host the event, share resources, and reach a broader audience (Masterman, 2009).

Value-added Services

Offering optional workshops, networking events, or add-ons to enhance the attendee experience and generate additional revenue (Getz, 2007).

The meetings and events industry are dynamic, continuously evolving to address emerging trends, issues, and impacts. For the "International Meeting on Sustainable Development in the Digital Age," understanding these trends is crucial to ensure the event remains relevant, innovative, and impactful.

## Trends

Hybrid Events

Definition: Hybrid events combine in-person and virtual elements, allowing participants to attend either physically or remotely. This trend has gained significant traction due to its flexibility and ability to reach a broader audience (Eventbrite, 2021).

Impact: For our event, incorporating hybrid elements will increase accessibility and inclusivity, allowing more stakeholders to participate regardless of geographic constraints.

Sustainability

Definition: There is a growing emphasis on sustainability within the events industry, driven by increasing environmental awareness and the demand for eco-friendly practices (Jones, 2014).

Impact: Our event will implement sustainable practices such as using recyclable materials, minimizing waste, and promoting eco-friendly transportation options, aligning with our mission to address environmental challenges.

Technological Advancements

Definition: The integration of advanced technologies like Artificial Intelligence (AI), Virtual Reality (VR), and Augmented Reality (AR) is revolutionizing the event experience (Rogers, 2013).

Impact: Utilizing these technologies will enhance attendee engagement through interactive sessions and immersive experiences, showcasing the potential of digital solutions in sustainable development.

## Issues

Economic Uncertainty

Definition: Economic fluctuations and uncertainties can impact funding, sponsorship, and attendee numbers (Davidson & Cope, 2003).

Impact: To mitigate these risks, our event will diversify funding sources, including corporate sponsorships, partnerships, and registration fees, ensuring financial stability even during economic downturns.

Health and Safety

Definition: The COVID-19 pandemic has heightened the focus on health and safety protocols at events (Silvers, 2012).

Impact: The event will implement comprehensive health and safety measures, including social distancing, sanitation stations, and virtual attendance options to ensure participant safety.

## Impacts

Economic Impact

Definition: Events can stimulate local economies through spending on hotels, restaurants, and other local services (Bowdin et al., 2011).

Impact: Our event is expected to generate significant economic benefits for the host city, supporting local businesses and creating job opportunities.

Social Impact

Definition: Events provide platforms for networking, knowledge sharing, and community engagement (Allen et al., 2010).

Impact: By fostering collaboration among diverse stakeholders, the event will contribute to social cohesion and drive collective action towards sustainable development.

Environmental Impact

Definition: Events can have substantial environmental footprints, including waste generation and carbon emissions (Raj & Musgrave, 2009).

Impact: By adopting sustainable practices, the event aims to minimize its environmental impact, serving as a model for green event management.

Cultural Sensitivity

Definition: Cultural sensitivity involves being aware of and respectful towards the cultural differences and norms of participants (Hofstede, 2010).

Impact: Ensuring cultural sensitivity will involve selecting speakers and content that reflect diverse perspectives and avoiding culturally insensitive materials. This will foster an inclusive environment where all attendees feel valued and respected.

Global Relevance

Definition: Global relevance refers to addressing issues that are pertinent to a worldwide audience, recognizing the global nature of sustainable development challenges (Deresky, 2017).

Impact: By focusing on globally relevant topics, the event will attract a diverse audience and facilitate international collaboration. This will enhance the event's impact and contribute to its objective of driving global sustainable development.

Accessibility

Definition: Accessibility involves making the event accessible to people with disabilities and those from different time zones, ensuring equal participation opportunities (Sharma, 2013).

Impact: Providing virtual attendance options, ensuring physical venue accessibility, and offering translation services will make the event more inclusive. This broadens the event's reach and ensures that all interested parties can participate.

# References

Allen, J. et al. (2011). “Festival and Special Event Management.” Milton, Qld: John Wiley & Sons.

Bladen, C. et al. (2012). “Events Management: An Introduction.” Abingdon: Routledge Seven.

Bowdin, G., et al. (2023). “Events Management.” Oxford: Elsevier.

Creative Tenders (2021). “A Guide to the Bidding Process in Event Management.” Available at: Creative Tenders (Accessed: 25th May 2024).

Davidson, R., et. al. (2003). “Business Travel: Conferences, Incentive Travel, Exhibitions, Corporate Hospitality and Corporate Travel.” Harlow: Pearson Education.

Deresky, H. (2017). “International Management: Managing Across Borders and Cultures.” Upper Saddle River, NJ: Pearson.

Eventbrite (2021). “The Rise of Hybrid Events.” Available at: Eventbrite (Accessed: 25th May 2023).

Getz, D. (2007). “Event Studies: Theory, Research and Policy for Planned Events.” Oxford: Butterworth-Heinemann.

Goldblatt, J. (2011). “Special Events: A New Generation and the Next Frontier.” Hoboken, NJ: John Wiley & Sons.

Grant, R. (2005). “Contemporary Strategy Analysis.” Melbourne: Blackwell.

Hofstede, G. (2010). “Cultures and Organizations: Software of the Mind.” New York: McGraw-Hill.

Hoyle, L. H. (2002). “Event Marketing: How to Successfully Promote Events, Festivals, Conventions, and Expositions.” New York: John Wiley & Sons.

Jones, M. (2014). “Sustainable Event Management: A Practical Guide.” London: Earthscan.

Masterman, G. (2009). “Strategic Sports Event Management: An International Approach.” Oxford: Butterworth-Heinemann.

O’Toole, W. (2008). “Event Feasibility and Development.” Amsterdam: Routledge.

Quick, L. (2020). “Managing Events, Real Challenges Real Outcomes.” SAGE Publications Ltd.

Raj, R., et al. (2009). “Event Management and Sustainability.” Wallingford: CABI.

Rogers, T. (2013). “Conferences and Conventions: A Global Industry.” Abingdon: Routledge.

Sharma, A. (2013). “Event Planning and Management.” New Delhi: Excel Books.

Shone, A., et al. (2010). “Successful Event Management: A Practical Handbook.” Andover: Cengage Learning.

Silvers, J. R. (2008). “Risk Management for Meetings and Events.” Oxford: Butterworth-Heinemann.

Silvers, J. R. (2012). “Risk Management for Meetings and Events.” Oxford: Butterworth-Heinemann.