International Meetings Management- BMIH6007

Event Strategic Planning and Delivery

Considerations for an International Meeting

Mihaela Masca
ID: 2126876

Lecturer: Jemma Smith

Table of Contents

1. Introduction	4

2.The Event Cycle………………………………..……………………………………………4

2.1 Pre-event (Planning)	4

2.2 For Event Day Arrangements (Delivery) ……………………..………………...………5

2.3 Post-Event Phase	6

3. Event Concept	7

4. Aim and Objectives of the Event	7

A. The Aim ……………………..……………………………………………………….…7

B. SMART Objectives	7

5. Event Operations	8

5.1 Skills Required	8

5.2 Resources Required	8

6. Event Budget	9

7. Industry Trends, Issues, and Impacts in the Events Industry……………………………..…9

A.Trends, Issues, and Impacts………………..………………………………....…………..9

B. SWOT and PESTEL Analyse…………..………………………………………..……..10

C. Influence on LuxeDine Designs' 10th Anniversary Event…………..………………….11

8. Cultural and Situational Considerations………….……………………………………….11

9 .Recommendations…………….……………………...……………………….…………..12

References………………...…………………………………………………………………13

Executive Summary

Approaching its momentous 10th-anniversary celebration, LuxeDine Designs showcases a remarkable decade of innovation and excellence in the hospitality furniture industry. The event takes place in the vibrant city of London at Hilton Heathrow Hotel and incorporates cutting-edge technologies like AR/VR to elevate the attendee experience. Stringent health and safety measures have been implemented to address post-pandemic concerns. LuxeDine will be showcasing its latest eco-friendly designs, highlighting the industry's increasing focus on sustainability and environmental consciousness. Although there are many opportunities to take advantage of London's global reputation and expand our network through strategic sponsorships, it is crucial to carefully plan our budget in order to navigate economic uncertainties and the high costs associated with technology and logistics. Emphasising cultural sensitivity and inclusivity will be crucial to create an environment where a wide range of international attendees feel embraced and appreciated. Through a thorough examination of the key factors outlined in our SWOT and PESTEL analyses, LuxeDine Designs is committed to creating an exceptional event that is both informative and influential. This will further establish our leadership in the hospitality design industry and pave the way for future progress and creativity.

# Introduction

# The event being planned is a commemoration of LuxeDine Designs' 10th anniversary since its establishment in London. As a company specializing in furniture for restaurants and hotels, LuxeDine Designs aims to celebrate this milestone by showcasing its journey of innovation and technological advancement within the industry. The event is designed to highlight company’s' evolution over the past decade, emphasizing its commitment to pushing boundaries and setting new standards in furniture design for hospitality spaces (Martin et al., 2019). It will serve as a platform to unveil the latest innovations and technologies integrated into their products, demonstrating how LuxeDine Designs continues to stay at the forefront of the industry. Additionally, the event will provide an opportunity for networking and collaboration, bringing together key stakeholders, industry experts, and potential clients to exchange ideas, explore partnerships, and envision the future of hospitality furniture design (Rogers and Davidson 2015).

- The Event Cycle

Corporate events include a variety of functions such as product launches, yearly meetings, team-building exercises, and conferences. It entails thorough preparation, execution, and post-event review, with the main goal of meeting business goals and improving company image (Getz and Page, 2019). In the case of LuxeDine Designs' 10th anniversary celebration, this cycle includes strategic planning to highlight innovation and sustainability, meticulous execution incorporating cutting-edge technologies and rigorous health precautions, and post-event evaluation to assess the impact on brand reputation and market leadership (Dounavi et al., 2022). LuxeDine Designs hopes to use this cycle to not only celebrate its milestone, but also to cement its position as a pioneer in the hotel furnishings sector, all while establishing meaningful relationships with stakeholders and accomplishing its business goals. From planning to reflection, the event cycle guarantees a methodical approach to arranging successful events (Arcodia, 2022).

2.1 Pre-event (Planning):

In the framework of LuxeDine Designs' tenth anniversary celebration, the pre-event preparation period includes a number of critical responsibilities. During this phase, defined event goals are established, such as:

- promoting innovation, highlighting sustainability efforts, and increasing the company's network.

Budgeting is used to guarantee that financial resources are distributed properly, taking into account economic risks as well as the expenses of technology and logistics (Evanthi, and Azhar, 2023).

- The Hilton Heathrow Hotel in London was chosen as the event's site after careful consideration of accessibility and prominence.

- Employing workers entails putting together a professional team to oversee all areas of the event, from logistics to marketing.

- Marketing efforts are intended to attract a varied range of foreign participants and sponsors, with an emphasis on tolerance and cultural sensitivity.

- To pique interest and enthusiasm among prospective attendees, create a comprehensive programme of events that highlights important sessions, activities, and speakers. Include entertainment, education, and engagement components in the programme.

- Obtaining the required licences, contracts, and agreements with partners, sponsors, and suppliers (Getz and Page, 2019).

Overall, this phase ensures that the event's goals, budget, and timeline are consistent with LuxeDine Designs' overall objectives and available resources, laying the groundwork for a successful 10th anniversary celebration. (Page and Connell, 2020).

In order to negotiate the logistical challenges of event management, it is essential that the necessary permissions, contracts, and agreements be obtained. Regularly engage with sponsors, partners, and suppliers to ensure seamless operations and execution (Lorette, 2014).

2.2 For Event Day Arrangements (Delivery):

The actual event's execution is covered in this phase. It entails conducting the event in accordance with the pre-event strategy. Registration, presentations, entertainment, networking, and making sure everything goes as planned are all part of this phase's activities (Ahmed, 2022).

Registration stations will be set up with digital check-in systems to ensure participants can check in and get their badges easily. To create an atmosphere that is both immersive and visually appealing, position themed decorations, signage, and branding components in various locations around the venue (Berridge, 2020). Coordination of audiovisual equipment, lighting, and staging for presentations and entertainment ensures presenters and audiences have the optimum visibility and sound quality. Specialised sections, interactive lectures, and specialised breaks are needed to let participants network and share their expertise (Allen, Harris and Jago, 2022).

The agenda of the day:

a. Welcome Reception: Guests will be welcomed with a stylish reception that includes drinks and the    chance to network with industry colleagues, also includes the registration.

b. Keynote Presentations: Inspiring speeches from LuxeDine Designs' founders, industry experts, and technology partners on the growth of design and innovation in the hospitality sector

c. Product Showcases: Get an exclusive peek at LuxeDine Designs' most recent furniture collections, emphasising novel materials, design methods, and technological integrations including smart furniture features (Vo, Kongar and Suárez Barraza, 2019).

d. Interactive demonstrations: provide hands-on experience with emerging technology incorporated in furniture, such as touch-responsive surfaces, integrated charging stations, and sustainable materials.

e. Panel Discussions: Experts will explore future trends in hospitality design, furniture sustainability, and the role of technology in improving guest experiences.

f. Networking Opportunities: Structured networking sessions enable participants to meet possible partners, clients, and industry leaders (Rogers and Wynn-Moylan, 2022).

g. Celebratory Gala: The event will conclude with a gala dinner commemorating company’s accomplishment via entertainment, excellent eating, and a look back at noteworthy events from the previous decade.

h. Collecting feedback: In order to guarantee that there is a continuing development, the guests are invited to provide feedback on the event that commemorates LuxeDine Designs' tenth anniversary. The information offered is very beneficial for affecting next events and enhancing the total experience (Dowson and Bassett, 2015).

2.3 Post-Event Phase:

After LuxeDine Designs' 10th-anniversary celebration concludes, the post-event evaluation stage commences. This involves tasks such as assessing feedback, analyzing data, and preparing reports. Surveys, attendance records, and ROI calculations are scrutinized to gauge the event's success, identify areas for improvement, and gather insights for future endeavors. Post-event reports are crafted to document outcomes and guide future event planning endeavors. (Pardo, 2014).

To guarantee everything goes well after the event, post-event procedures must be followed through:

- Ensure thorough cleaning of event space and return borrowed items in good condition.

- Timely return of rental equipment to avoid penalties.

- Calculate total expenses, including damages, and provide detailed event invoice.

- Evaluate suppliers' performance and compare actual expenses to budget.

- Gather guest feedback through questionnaires and interviews.

- Express gratitude to partners, sponsors, and attendees for their support (Müller, 2015).

- Event Concept

The LuxeDine Designs 10th Anniversary Celebration is a prominent event that honours a decade of innovation and quality in restaurant and hotel furniture design. LuxeDine Designs, founded in London, has been in the forefront of combining cutting-edge technology with elegant design. The event is a multifaceted celebration that highlights LuxeDine Designs' journey and progress over the last decade. It seeks to highlight the company's dedication to innovation, quality, and design excellence. The event will include keynote talks, interactive product exhibits, live demonstrations of technical integrations, and opportunity to network with industry experts (Martin and Cazarre, 2016).

- Aim and Objectives of the Event

- The Aim:

The aim is to commemorate LuxeDine Designs' 10th anniversary by highlighting their ingenuity and technology achievements in restaurant and hotel furniture design. This will also enhance industry ties and position the firm as a hospitality leader (Expert, 2013).

B. SMART Objectives:

1. Showcase Innovation: In line with our mission to lead in design and innovation, LuxeDine Designs will showcase at least five new products featuring cutting-edge design and technology while tracking guest interactions and feedback to leverage R&D resources and partnerships (Molina-Castillo, et al., 2023).

2. Increase Brand Awareness: Leveraging existing marketing channels and industry networks, confirm attendance and media coverage within one-month post-event, aiming to attract at least 100 industry professionals and media representatives, enhancing brand visibility and credibility through measurable registrations and media mentions (Wardani and Sanica, 2020).

3. Foster Networking and Partnerships: Organize targeted networking sessions post-event to facilitate at least three new strategic partnerships or client leads within three months, recording follow-up meetings and partnership agreements, supporting business growth and industry collaboration (Ihm and Castillo, 2017).

- Event Operations

5.1 Skills Required:

- With project management expertise, meticulous attention to detail and problem-solving skills, the organizer must excel in overseeing the entire event planning process, ensuring flawless execution from start to finish.

- Marketing and Communications encompasses crafting compelling promotional materials, managing media relations for press coverage, and engaging with the audience on social media platforms before, during, and after the event to enhance visibility and attract attendees (Mahoney and Tang, 2024).

- Skilled in AV/IT support, managing equipment, and live streaming for seamless tech integration. Proficient in website/app management, developing and maintaining registration platforms, and mobile apps for events.

- Event planning, exhibition setup with interactive displays, and graphic design for LuxeDine-branded brochures, banners, and promotional materials are our services.

- Guest Relations provides excellent service, resolving queries and assuring a good experience, while On-Site Assistance administers registration desks, directs visitors, and resolves difficulties (Silvers, 2012).

  - Resources Required:

- A suitable location in London with the capacity to host various segments of the event, including receptions, presentations, and demonstrations. Hilton London Heathrow Airport is an excellent venue option for any event since it provides plenty of space, first-rate facilities, unrivalled accessibility, and incomparable convenience. This makes it the ideal place to have an amazing and successful get-together (www.hilton.com, n.d.).

- Technology offerings include high-quality audio-visual equipment, interactive devices for product demos, and robust Wi-Fi infrastructure for seamless connectivity.

- Event staff provide registration, guest services, and on-site logistics; technical crew manage AV equipment and lighting, while security ensures attendee safety (Hind et al., 2019).

- Utilize brochures, banners, and digital content to promote the event while offering swag bags or giveaways for a memorable guest experience.

- Gathering: High-quality catering services for receptions, networking breaks, and the gala dinner.

- Transportation and logistics involve planning VIP guest transportation while also overseeing venue-bound equipment and material logistics (Dowson et al., 2022).

By using these expertise and resources, the company can guarantee that their 10th Anniversary Celebration is unique, well-organized, and powerful, emphasising their dedication to innovation and quality in hospitality furniture design.

- Event Budget

To ensure success, LuxeDine Designs meticulously plans its budget for its upcoming 10-year anniversary event. With an estimated 130 attendees, the occasion will offer unparalleled insights into hotel technology and innovation. Sponsorship from various sectors, including hospitality solutions and IT corporations, alongside internal budget allocations, will cover venue, accommodations, transportation, entertainment, and honorariums, guaranteeing a successful event. (Wahyudi, 2023).

The event generated a substantial revenue of £49,000, with Protocol contributing £44,000, while Beverage Sponsor and Technology Company Sponsor contributed £3,000 and £2,000 respectively, resulting in a successful funding.

Expenditures for the event amounted to £45,900, covering various aspects such as entertainment, decoration, accommodation, catering, venue rental, transportation, honorariums, promotion, and miscellaneous expenses, ensuring a well-organized and engaging celebration (Masca, 2024).

Despite the comprehensive expenses, the event remained within budget, reflecting effective financial management and planning.

- Industry Trends, Issues, and Impacts in the Events Industry

- Trends, Issues, and Impacts

The anniversary event seamlessly integrated modern elements, sustainability, technology, personalized experiences, and rigorous health measures for a safe and enjoyable celebration. It navigated economic, technological, environmental, and health challenges with resilience, showcasing adaptability in planning and execution. Smart cost management balanced innovative technology and eco-friendly methods, enhancing attendee engagement and overall experience. (Hudson and Hudson, 2017).

But planning and carrying out hybrid events made things more complicated, and health and safety rules had to be carefully followed to make sure the party went smoothly, and everyone had a good time.

- SWOT and PESTEL Analyse

SWOT Analyse

| Strengths | Weaknesses |
| --- | --- |
| - LuxeDine Designs' reputation for innovation and quality. - Strong network and industry relationships. - Expertise in integrating technology with design. | - High costs associated with implementing new technologies. - Limited experience in organizing large-scale events. - Potential for logistical challenges in a hybrid event setup. |
| Opportunities | Threats |
| - Growing interest in innovative and tech-driven event experiences. - Potential for new partnerships and sponsorships in the hospitality and technology sectors. - Ability to showcase sustainability efforts, aligning with industry trends. | - Economic instability affecting budget and sponsorship availability. - Rapid changes in technology requiring constant adaptation. - Potential health and safety risks impacting attendee confidence. |

(Wang, Zhao and Zhang, 2022)

PESTEL Analyse

| Political | - Regulations on event safety and health standards. - Trade policies affecting import of materials or technology. |
| --- | --- |
| Economic | - Economic downturns affecting sponsorship and budget allocations. - Inflation impacting costs of materials and services. |
| Social | - Increasing consumer demand for personalized and unique experiences. - Rising awareness and preference for sustainable practices. |
| Technological | - Advancements in AR/VR, AI, and IoT transforming event experiences. - Challenges in adopting and integrating new technologies. |
| Environmental | - Pressure to adopt sustainable practices and minimize carbon footprint. - Potential impact of climate change on event logistics and planning. |
| Legal | - Compliance with health and safety regulations. - Intellectual property concerns related to technology use. |

(Kitchen, 2022).

Through strategic alignment with current industry trends and proactive problem-solving, LuxeDine Designs can guarantee that their 10th-anniversary celebration will make a lasting impression and showcase their unwavering dedication to innovation and excellence (Ismail et al., 2023).

Influence on LuxeDine Designs' 10th Anniversary Event

Influencing LuxeDine Designs' 10th Anniversary Event, the hybrid event trend is embraced, integrating virtual elements to extend reach and accommodate remote attendees. Sustainability takes center stage as LuxeDine showcases eco-friendly practices, while technology integration, leveraging AR/VR, promises to elevate the attendee experience and highlight innovative products. Moreover, economic prudence and strict adherence to health regulations underscore the importance of careful budget planning, ensuring both a successful and safe celebration (Celuch, 2021).

- Cultural and Situational Considerations

For LuxeDine Designs' 10th-anniversary celebration, meticulous attention to cultural and situational nuances is paramount. With a diverse audience in mind, the event embraces inclusivity and cultural sensitivity, catering to international and multicultural guests. Leveraging London's esteemed status in the hospitality and design realms, the celebration aims to attract esteemed attendees and garner widespread media coverage, amplifying its significance on a global scale (Ford and Sturman, 2023). In light of the post-pandemic landscape, stringent safety measures are implemented to instil attendee confidence and prioritize health and well-being. Furthermore, the event embraces sustainability, aligning with societal values and the growing emphasis on environmental responsibility, ensuring its relevance and appeal to a broad audience (Mair, and Smith, 2022).

- Recommendations

LuxeDine Designs' 10th-anniversary event is set to showcase the company's cutting-edge innovations and prominent role in the industry. Despite the potential risks, the high costs of advanced technologies and sustainability efforts, along with potential logistical challenges of a hybrid event, cannot be overlooked. In addition, the attendance and sponsorship may be affected by the changing economic conditions and health concerns. To ensure the success of the event, LuxeDine Designs should optimize its budget by prioritizing essential elements and adopting cost-effective technology solutions. Strengthening sponsorships through existing industry relationships will provide robust support. Enhancing safety measures with comprehensive health protocols and promoting cultural sensitivity will maximize impact and manage potential challenges effectively.

References

Ahmed, A. (2022) Planning an International Business Event: Company X.

Allen, J., Harris, R., & Jago, L. (2022). Festival & special event management. John Wiley & Sons.

Arcodia, C. (2022) The Routledge Handbook of Business Events. Taylor & Francis. Available at: http://books.google.ie/books?id=RxV_EAAAQBAJ&pg=PA216&dq=Rogers,+T.+and+Davidson,+R.,+2015.+Marketing+destinations+and+venues+for+conferences,+conventions+and+business+events.+Routledge&hl=&cd=2&source=gbs_api [Accessed 15 May 2024].

Berridge, G. (2020) Designing event experiences. In The Routledge handbook of events (pp. 378-395). Routledge.

Celuch, K. (2021). Event technology for potential sustainable practices: A bibliometric review and research agenda. International Journal of Event and Festival Management, 12(3), 314-330.

Dounavi, L.E., Dermitzakis, E., Chatzistelios, G. and Kirytopoulos, K. (2022) Project management for corporate events: a set of tools to manage risk and increase quality outcomes. Sustainability, 14(4), p.2009.

Dowson, R., Albert, B. and Lomax, D. (2022) Event Planning and Management. Kogan Page. Available at: http://books.google.ie/books?id=yTYNzwEACAAJ&dq=Dowson,+R.,+Albert,+B.+and+Lomax,+D.,+2022.+Event+planning+and+management:+Principles,+planning+and+practice.+Kogan+Page+Publishers.&hl=&cd=1&source=gbs_api. [Accessed 16 May 2024].

Evanthi, A. and Azhar, R.M. (2023) Planning and Implementation of Event Marketing in Sociopreneurship. International Journal of Science, Technology & Management, 4(6), pp.1451-1459.

Expert, C.P.E. (2013) How to Deliver Outstanding Corporate Events. Lulu.com. Available at: http://books.google.ie/books?id=pk6IDgAAQBAJ&printsec=frontcover&dq=Powell,+C.,+(2013)+How+to+deliver+outstanding+corporate+events.+Lulu.+com.&hl=&cd=1&source=gbs_api. [Assessed 16 May 2024].

Ford, R.C. and Sturman, M.C. (2023) Managing Hospitality Organizations. SAGE Publications. Available at: http://books.google.ie/books?id=R9brEAAAQBAJ&pg=PT570&dq=Kitchen,+E.,+2022.+Strategic+event+planning.+In+The+Routledge+Handbook+of+Business+Events+(pp.+32-42).+Routledge&hl=&cd=1&source=gbs_api. [Accessed 16 May 2024].

Getz, D. and Page, S. J. (2019) Event Studies. Routledge. Available at: http://books.google.ie/books?id=Snm6DwAAQBAJ&printsec=frontcover&dq=Getz,+D.+and+Page,+S.,+(2019)+Event+studies:+theory,+research+and+policy+for+planned+events.+3rd+Edition.+Routledge:+Oxford&hl=&cd=1&source=gbs_api. [ Accessed 15 May 2024].

hilton.com. (n.d.). Heathrow Airport Hotels T4| Hilton London Heathrow Airport Hotel. [online] Available at: https://www.hilton.com/en/hotels/lhraptw-hilton-london-heathrow-airport [Accessed 16 May 2024].

Hind, D.W.G., Disimulacion, M.A., Fernandez, K., Lin, K.-W.E., Sharma, A. and Suroto, P.Z. (2019) International Best Practice in Event Management. Prasetiya Mulya Publishing. Available at: http://books.google.ie/books?id=vRzdDwAAQBAJ&printsec=frontcover&dq=Hind,+D.W.,+Disimulacion,+M.A.,+Fernandez,+K.,+Lin,+K.W.E.,+Sharma,+A.+and+Suroto,+P.Z.,+2019.+International+Best+Practice+in+Event+Management:+Based+on+The+APIEM+Certified+Event+Manager.+Prasetiya+Mulya+Publishing.&hl=&cd=1&source=gbs_api. [Accessed 16 May 2024].

Hudson, S. and Hudson, L. (2017) Marketing for Tourism, Hospitality & Events: A Global & Digital approach. https://openlibrary.org/books/OL28310867M/Marketing_for_Tourism_Hospitality_Events [Accessed 15 May 2024].

Ihm, J. and Castillo, E.A. (2017) “Development and transformation of collaborative networks in events,” Journal of Convention & Event Tourism, 18(3), pp. 205–224. doi:10.1080/15470148.2017.1322021.

Ismail, A., Hidajat, T., Dora, Y. M., Prasatia, F. E., and Pranadani, A. (2023). Leading the Digital Transformation: Evidence from Indonesia. Asadel Publisher.

Kitchen, E. (2022) Strategic event planning. In The Routledge Handbook of Business Events (pp. 32-42). Routledge.

Lorette, K. (2014). The Complete Guide to Running Successful Workshops & Seminars: Everything You Need to Know to Plan, Promote and Present a Conference Explained Simply. Atlantic Publishing Company.

Mahoney, L.M. and Tang, T. (2024) Strategic social media: From marketing to social change. John Wiley & Sons.

Mair, J. and Smith, A. (2022) Events and sustainability: why making events more sustainable is not enough. In Events and sustainability (pp. 1-17). Routledge.

Martin, L., Jerrard, B. and Wright, L. (2019) Pubscape: innovation by design in the British pub. International Journal of Contemporary Hospitality Management 31(8), pp. 3018–3036. Available at: http://dx.doi.org/10.1108/ijchm-06-2018-0537. [Accessed 15 May 2024].

Martin, V. and Cazarre, L. (2016) Technology and Events. Goodfellow Publishers Ltd. Available at: http://books.google.ie/books?id=FsRLEAAAQBAJ&printsec=frontcover&dq=Martin,+V.+and+Cazarr%C3%A9,+L.,+2016.+Technology+and+Events:+Organizing+an+engaging+event.+Goodfellow+Publishers+Ltd&hl=&cd=1&source=gbs_api. [Accessed 15 May 2024].

Masca, M. (2024) Feasibility plan for an international meeting-Power Point Presentation. International Meetings Management for the Hotel Industry (BMIH6007). University of Wales Trinity Saint David. Unpublished assignement.

‌Molina-Castillo, F.-J., Meroño-Cerdán, A.-L., Lopez-Nicolas, C. and Fernandez-Espinar, L. (2023) “Innovation and Technology in Hospitality Sector: Outcome and Performance,” Businesses, 3(1), pp. 198–220. doi:10.3390/businesses3010014.

Müller, M. (2015) “The Mega-Event Syndrome: Why So Much Goes Wrong in Mega-Event Planning and What to Do About It,” Journal of the American Planning Association, 81(1), pp. 6–17. doi:10.1080/01944363.2015.1038292.

Page, S. J. and Connell, J. (2020) The Routledge Handbook of Events. Routledge. Available at: http://books.google.ie/books?id=qOreDwAAQBAJ&printsec=frontcover&dq=Berridge,+G.,+2020.+Designing+event+experiences.+In+The+Routledge+handbook+of+events+(pp.+378-395).+Routledge&hl=&cd=5&source=gbs_api [Accessed 15 May 2024].

Pardo, A. (2014). Designing learning analytics experiences. In Learning analytics: From research to practice (pp. 15-38). New York, NY: Springer New York.

Rogers, T. and Davidson, R. (2015) Marketing destinations and venues for conferences, conventions and business events. Routledge.

Rogers, T., and Wynn-Moylan, P. (2022) Conferences and conventions: A global industry. Routledge.

Silvers, J.R. (2012) Professional Event Coordination. John Wiley & Sons. Available at: http://books.google.ie/books?id=S-y-JCI3sCUC&printsec=frontcover&dq=Silvers,+J.R.,+2012.+Professional+event+coordination+(Vol.+62).+John+Wiley+%26+Sons.&hl=&cd=1&source=gbs_api. [Accessed 16 May 2024].

Vo, B., Kongar, E. and Suárez Barraza, M.F. (2019) 'Kaizen event approach: a case study in the packaging industry,' International Journal of Productivity and Performance Management, 68(7), pp. 1343–1372. https://doi.org/10.1108/ijppm-07-2018-0282.

Wang, L., Zhao, F. and Zhang, G. (2022) “Analysis on the Impact of Large-Scale Sports Events on Regional Economy Based on SWOT-PEST Model,” Journal of Mathematics. Edited by M. Chen, 2022, pp. 1–12. doi:10.1155/2022/7769128.

Wardani, P.S. and Sanica, I.G. (2020) “STRATEGY TO RAISE BRAND AWARENESS USING SOSIAL MEDIA TO THE MILENIALS,” Jurnal Bisnis Terapan, 4(2), pp. 171–182. doi:10.24123/jbt.v4i2.2961.