ESSAY – PROJECT PLAN

Student Name:- Sahil Girishbhai Bhuva

Student Number:- 2127449

Module Code:- LCBB5005

Lecturer Name:- Dr. Anupam Mazumdar

Table of Contents

Introduction	3

Discussion of the overall plan	4

Budget planning	4

Time schedule	8

Analysis of quality stakeholders	10

Risk analysis based on risk matrix	13

The ultimate evaluation of the project plan	16

Conclusion	17

Reference list	18

# Introduction

Google LLC is a multinational technology company from the US; it focuses on online advertising, the use of artificial intelligence (AI), cloud computing, search engine technology, computer software, e-commerce, consumer electronics, and quantum computing. This company intends to construct another commercial building in the UK, which would be completely owned by this company. In this concern, this company is going to promote an eco-friendly or sustainable building to support both the UK economy and Google employees (Gillespies, 2023). This project will allow Google to expand its business operations through this project and manage operational access with more swiftness. At the time of constructing the multi-storeyed building, Google remembers providing accommodation to 4500 people from the UK, as well as supporting almost 7000 Google employees with multi-faceted facilities, such as a cafe, gym, pool, and gaming zones.

Hence, this essay is going to prepare and review a business plan for Google so that it can successfully complete the project and manage its overall business operations. This essay will provide a detailed budget plan with each minute information of in the expense sections. Furthermore, this study will provide a detailed time frame for this project; in this case, the way this company and its managers communicate with each stakeholder and finally accomplish the overall project is included. This project further provides a detailed analysis of quality stakeholders and risk factors to guide the overall project plan. In the final step, this essay evaluates the overall project plan for this company and its success in eco-friendly building construction.

# Discussion of the overall plan

In order to develop a new building for the Knowledge Quarter and King’s Cross’s growing knowledge-based economy, Google will focus on managing the core elements of this project. Those elements are the budget, time schedule, quality stakeholders, risk factors, and evaluation of the final project plan.

## Budget planning

| Commercial development budget |  |  |  |
| --- | --- | --- | --- |
| Date: Project name: Google Headquarters Project in London, UK Location: King's Cross, London Project description: This project will cover 60400 square meters of prime office space and provide accommodation for 4500 people throughout its 11 storeys. Furthermore, it will provide 7000 Google employees with office and house accommodation, including a gym, cafe, pool, and multi-use gaming facilities. The most important aspect of this project is to build an eco-friendly and sustainable building in the UK, which will have an expansive rooftop garden. This project will be based on natural themes and all ingredients sourced through “Google’s Healthy Materials Programme” (Gillespies, 2023). Estimate developed by: |  |  |  |
| Products or item | Cost per unit | Budget | Notes |
| land or property acquisition cost (£) | 1391 | 84016400 | This is an estimated budget of the overall expense for constructing the Google building in the UK. It can be changed based on deals and contracts with bids, suppliers, investors, and workers. |
| purchasing price for building or land | 1300 | 78520000 |  |
| appraisal of property | 11 | 664400 |  |
| inspection | 80 | 4832000 |  |
| construction cost (£) | 13230 | 3018793250 |  |
| raw material | 3500 | 2325400000 |  |
| average labour cost (for six years) | 2400 | 144960000 |  |
| equipment | 3230 | 195092000 |  |
| security | 1250 | 1250 |  |
| permit | 300 | 199320000 |  |
| contingency | 250 | 15100000 |  |
| environmental remediation | 2300 | 138920000 |  |
| professional services (£) | 8200 | 283883500 |  |
| fees for project management | 500 | 30200000 |  |
| cost for architecture and engineering | 2500 | 151000000 |  |
| cosultant fees | 500 | 30200000 |  |
| legal fees | 1000 | 60400000 |  |
| environmental analysis | 2500 | 2500 |  |
| soil testing | 1000 | 1000 |  |
| inspection | 200 | 12080000 |  |
| financings and loan cost (£) | 115000 | 3310000 |  |
| surveys | 10000 | 10000 |  |
| financing fee | 15000 | 15000 |  |
| construction loan interest (for six years based on 0.9% per month) | 45000 | 3240000 |  |
| titles and escrow fee | 10000 | 10000 |  |
| lender fee | 15000 | 15000 |  |
| charges for environmental implementation | 20000 | 20000 |  |
| completion of decoration (£) | 1900 | 899960000 |  |
| electrical | 500 | 332200000 |  |
| light and air | 250 | 166100000 |  |
| interior | 250 | 166100000 |  |
| exterior | 300 | 199320000 |  |
| rooftop garden | 600 | 36240000 |  |
| other expenses (£) | 65250 | 15165000 |  |
| tax | 65000 | 65000 |  |
| insurance coverage | 200 | 12080000 |  |
| miscellaneous expenses | 50 | 3020000 |  |
| ALL TOTAL | 204971 | 4305128150 |  |

Table 1: Budget planning

Land price in London is £1300 per square metre; Google is going to purchase 60400 square metre of land for its 11-storied new purpose-built headquarter in London, near King's Cross (Lonon Government, 2023). Furthermore, in this city, the inspection cost is £80, which is also included in the budget list (London Capital Homes, 2023). In 2023, material cost has reached up to £3500 per square metre on average (Proficiency, 2023). Construction labourers work for 8 hours a day, and their average hourly wage is £10 (Payscale, 2023). For empirical buildings, the average equipment cost is £3230 in London (Costmodelling, 2023); as Google is going to build a multi-purpose building, this will be the essential cost. The average cost for architecture and engineering in London is £4500; this includes consultation fees, legal costs, site services, and insurance (Agarchitecture, 2023). In this city, soil testing or soil survey requires an average of £10000, including the cost of machines and drivers (Self-Build, 2023). Construction loan interest in London is 0.9% in a month (Fleximize, 2023); this project is estimated to require more than six years with a £5 million loan.  Table 1 indicates a budget estimation based on the expected areas of expenses in the UK; this is beneficial for the development of the financial management in this UK project of Google.

## Time schedule

| List of activities | Duration |
| --- | --- |
| Meeting with existing managers and employees | 01/12/2023 - 24/12/2023 |
| Communication with governments | 02/01/2024 - 30/01/2024 |
| Communication with investors | 03/02/2024 - 15/02/2024 |
| Communication with bids | 16/02/2024 - 28/02/2024 |
| Soil testing and environmental analysis | 01/03/2024 - 15/03/2024 |
| Selection and recruitment of construction labour | 16/03/2024 - 23/03/2024 |
| Gathering necessary construction equipment | 16/03/2024 - 23/03/2024 |
| Construction of the building | 25/03/2024 - 26/12/2029 |
| Risk analysis | 25/03/2024 - 26/12/2029 |
| Development and application of risk mitigation plan | 02/01/2030-15/01/2030 |
| Environmental analysis | 25/03/2024 - 26/12/2030 |
| Interior decoration | 02/01/2030-15/01/2030 |
| Exterior decoration | 16/01/2030 - 31/01/2023 |
| Rooftop environment building | 01/02/2030 - 31/08/2023 |
| Completion of final project | 01/12/2023 - 31/12/2030 |

Table 2: Time schedule for overall completion of this project

(Source: Self-developed)

Table 2 mentions a detailed division of time fame for constructing the new Google headquarter in the UK. This shows that this project will require over six years to be completed properly; however, this is not associated with risk analysis and risk matrix. Lee et al. (2021) mentioned that the timeframe is quite beneficial to guide a construction company or a project owner to complete the project systematically. In order to maintain the proper time in the construction project, having the right materials and equipment at the right time is required. Without any time planning, a company cannot compete properly.

## Analysis of quality stakeholders

| Type | Stakeholders | Interest | Estimated project impact | Estimated priority |
| --- | --- | --- | --- | --- |
| Primary | Owner (Google) | Achieving targets | Medium | 2 |
|  |  | Liability (avoiding all costs) | High |  |
|  |  | Increasing margin of sale | Medium |  |
|  | Sponsors and investors | Successful addressing the needs of consumers | Low | 3 |
|  |  | Providing new market to expand business operations | Medium |  |
|  |  | Addressing the needs of Google employees and their family members | Medium |  |
|  |  | Assessing the financial needs in each section of the construction | High |  |
|  | Project Managers | Promoting innovation in Google services | High | 3 |
|  |  | Managing and maintaining cooperation among all departments and employees | High |  |
|  |  | Avoiding strike | Medium |  |
|  | Team members | Cooperation and communication among all employees | Medium | 3 |
|  |  | Participation in organisational operations | High |  |
| Secondary | Customers and Google Employees | Having office accommodation | High | 2 |
|  |  | Having ancillary spaces including cafes, a gym, a multi-use games area (MUGA) and pool facilities | Medium |  |
|  | Bids [Heatherwick Studio and Bjarke Ingels Group (BIG)] | Supplying necessary resources for the construction of Google building | Medium | 2 |
|  |  | Achieving profit from Google’s performance | High |  |

Table 3: Analysis of Quality Stakeholders

(Source: Self-developed)

| Power | Keep satisfied - Owner - Project manage - Board members | Manage closely - Sales team - Innovation and R&D team - Suppliers |
| --- | --- | --- |
|  | Monitor - Bids and investors - Departments - Competitors | Keep informed - Customers - Investors |
|  | Interest |  |

Table 4: Stakeholder matrix

Table 3 and Table 4 present a stakeholder analysis and stakeholder matrix in tabular format; Lin et al. (2019) mentioned that stakeholders assist a company to incorporate social responsibility within its construction project. This is Google’s construction project and for this reason, it focuses on its corporate social responsibility and the development of the business activities. The analysis of quality stakeholders highlights the way these stakeholders are effective for incorporating the CSR activities and contribution to the UK economy, society, and environment.

## Risk analysis based on risk matrix

| No | Risk description | Potential consequences | Likelihood | Impact | Severity (L*I) | Risk allocation | Mitigation strategy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Changes in design | Miscommunication and disharmony can occur among stakeholders | 3 | 2 | 6 | Owner and managers | Daily communication with all stakeholders |
| 2. | Inadequate supply of construction materials and equipment | 1. Delay in project completion 2. Issues with bids and construction material suppliers | 2 | 3 | 6 | Project manager | Communication with bids and suppliers, along with a written legal contract |
| 3. | Lack of financial resources | 1. Delay in project completion 2. Issues with investors 3. Lower wages for construction employees 4. Burden of interest | 3 | 3 | 9 | Financial manager | Communication and legal contracts with investors |
| 4. | Less number of workers and a lack of workers' cooperation | 1. Delay in project completion 2. Disharmony among workers due to workload | 2 | 2 | 4 | HR and line manager | Providing rules and regulations for leave and equal distribution of workload |
| 5. | Inefficient environmental analysis and soil testing | Issues in project initiating and inspection processes | 2 | 1 | 2 | Risk manager and project manager | Managing waste properly Communication with soil testing agencies |
| 6. | Late certification for this project | Delay in project completion | 2 | 1 | 2 | Risk manager and project manager | Communication with investors, the government, and certification agencies |
| 7. | Delay in overall construction | 1. Delay in project completion 2. Google employees will get accommodation in late 3. Opening the UK headquarters will be late 4. Google services in the UK will be late in this country | 2 | 3 | 6 | Owner, Risk manager and project manager | Communication with all stakeholders and directing them according to the situation demand |

Table 4: Risk analysis based on risk matrix

(Source: Self-developed)

Qazi et al. (2021) mentioned that a risk matrix and that matrix-based data involves sustainability in a construction project. The components of the risk matrix table are risk description, potential consequences, likelihoods, impact, severity, risk allocation, and mitigation strategy [mentioned in Table 4]. Severity is calculated by multiplying the provided numbers in likelihood and impact; based on its analysis, especially severity, a company ranks the risks and takes major initiatives to mitigate those. As a result, prioritised risk subjects expose risk zones and mention individual risks; then, the project owner and risk manager can combine to make decisions regarding operational strategies to complete a sustainable construction project. Google is going to conduct a sustainable construction project as its new headquarter in the UK will have an expandable rooftop garden to contribute to the UK economy and environment equally.

## The ultimate evaluation of the project plan

This essay presented the way the project plan includes the project schedule, budget planning, risk analysis, and stakeholder analysis. According to Andiyan et al. (2021), the project schedule is one of the most effective parts of project planning. Hence, it can be said that this planning is beneficial for the construction project of Google. Furthermore, risk analysis is another important aspect to rank the risks based on severity and take necessary initiatives. Moreover, the current project plan includes detailed budget planning; this is in the form of allocating financial resources. However, a minute observation will highlight its focus on both human resources and material resources simultaneously. In this concern, this project plan also includes stakeholder analysis; this highlights the primary and secondary stakeholders to highlight their interests in the overall Google project.

# Conclusion

It can be concluded that planning an infrastructure of project management is crucial for an organization to understand the key aspects needed to fulfil the requirements of a project. An efficient project plan leads a construction project to be successful and meet the needs of the clients. In this essay, there is a detailed overview of a project plan for the company Google has described. The company intends to construct a new headquarters at King’s Cross located in London by 2024. The project will be based on 650000 square feet with an estimated cost of one billion pounds. The whole construction project will be a milestone for one of the largest companies, Google, creating self-owned and designed working premises. A detailed budget plan for this project has been evaluated in which costs related to direct and indirect factors are analyzed. The inspection cost for the project is estimated to be £80 as expenses related to highly professional inspection individuals can be high.

There will be an enormous number of labourers working on this project, and for this reason, the labour cost is assumed to be £10 per hour. The total amount of labour cost is a direct expense that can rise as per the market involvement and extended time period. There will also be a cost related to the equipment to be utilized in this construction project. The cost of equipment, which is projected to be £3230, can increase after changing the project management strategy along with the cost of architecture and engineering. The projected budget plan will be followed by Google as per the schedule, reflecting different stages of communication, risk prevention, and design. Professional meetings will take place with the managers, employees, and government. In order to gather enough funds to accomplish this construction project, the company will try to maintain coordination with the potential stakeholders. The grants and investments will be asked of the government to ensure the proper flow of funds. As per the risk matrix, the potential risks that can be faced by the company in the future are reflected along with their solution to control them.

# Reference list

Agarchitecture, 2023. How much does it cost to build a new house in the UK in 2023? Available at: https://agarchitecture.net/blog/how-much-does-it-cost-to-build-a-new-house-in-the-uk-in-2023/#:~:text=We%20would%20expect%20our%20clients,site%20preparation%20and%20professional%20fees. [accessed on 15/11/2023]

Andiyan, A., Putra, R.M., Rembulan, G.D. and Tannady, H., 2021, June. Construction project evaluation using CPM-Crashing, CPM-PERT and CCPM for minimize project delays. In Journal of Physics: Conference Series (Vol. 1933, No. 1, p. 012096). IOP Publishing.

Costmodelling., 2023. TYPICAL UK CONSTRUCTION COSTS OF BUILDINGS. Available at: https://costmodelling.com/building-costs#:~:text=The%20cost%20of%20a%20building,m2%20%2D%20%C2%A33%2C230%2Fm&text=95%25%20of%20buildings%20will%20be,m2%20%2D%20%C2%A34%2C230%2Fm [Accessed on 15/11/2023].

Fleximize., 2023. Construction Financing. Available at: https://fleximize.com/business-loans/construction-finance [Accessed on 15/11/2023].

Gillespies., 2023. Google Headquarters. Available at: https://www.gillespies.co.uk/projects/google-headquarters [Accessed on 15/11/2023].

Lee, D., Lee, S.H., Masoud, N., Krishnan, M.S. and Li, V.C., 2021. Integrated digital twin and blockchain framework to support accountable information sharing in construction projects. Automation in construction, 127, p.103688.

Lin, X., McKenna, B., Ho, C.M. and Shen, G.Q., 2019. Stakeholders’ influence strategies on social responsibility implementation in construction projects. Journal of Cleaner Production, 235, pp.348-358.

London Capital Homes., 2023. Landlords Price List. Available at: https://www.londoncapitalhomes.co.uk/landlords/price-list/ [Accessed on 15/11/2023].

Lonon Government., 2023. 4: The value of land and housing in London. Available at: https://www.london.gov.uk/sites/default/files/chapter4-economic-evidence-base-2016.pdf [Accessed on 15/11/2023].

Payscale., 2023. Hourly Rate for Industry: Construction. Available at: https://www.payscale.com/research/UK/Industry=Construction/Hourly_Rate [Accessed on 15/11/2023].

Proficiency., 2023. HOW MUCH DOES IT COST TO BUILD A HOUSE. Available at: https://www.proficiencyltd.co.uk/cost-of-building-a-house.html#:~:text=In%202023%2C%20the%20cost%20of,%C2%A32%2C750%20per%20square%20metre. [Accessed on 15/11/2023].

Qazi, A., Shamayleh, A., El-Sayegh, S. and Formaneck, S., 2021. Prioritizing risks in sustainable construction projects using a risk matrix-based Monte Carlo Simulation approach. Sustainable Cities and Society, 65, p.102576.

Self-Build., 2023. Soil Surveys Explained. Available at: https://www.self-build.co.uk/soil-survey/#:~:text=How%20much%20will%20the%20soil,250%20on%20top%20of%20that. [Accessed on 15/11/2023].