## Lists
Cyber & Technology | People & Behaviour | Operational | Physical & Environmental | Financial | Strategic
Cyber Security | Human Error | Process Failure | Physical Security | Financial Fraud | Strategic
Data Privacy | Insider Threat | Supply Chain | Natural Disaster | Budget Overrun | Political / Regulatory
System Failure | Social Engineering | Business Continuity | Environmental | Economic | Third Party / Vendor
Software/Hardware | Reputational | Compliance / Legal | Health & Safety

## Risk Register
Risk Management Register
Scenario: TechTraders Ltd. E-Commerce Platform Group: _____1______________________
Risk ID | Hazard / Risk Description | Who is at Risk | Category | Sub Category | Likelihood (1–5) | Severity (1–5) | Risk Score (L × S) | Risk Level | Existing Controls | Additional Controls Needed | Responsible Person | Target Date | Residual Likelihood (1–5) | Residual Severity (1–5) | Residual Risk Score | Residual Risk Level | Status
R-01 | RISK NAME: Customer account takeover HAZARD: Stolen login credentials DESCRIPTION: Criminals access accounts to steal data or make purchases. | Customers; customer service; business | Cyber & Technology | Cyber Security | 5 | 4 | 20 | Critical | Password hashing, HTTPS, basic login monitoring. | Require multi-factor authentication; block repeated login attempts; detect automated bots; warn customers about suspicious account activity. | Head of Security | 2026-08-15 | 2 | 4 | 8 | Medium | In Progress
R-02 | RISK NAME: Web application or API attack HAZARD: Vulnerable website, app or API DESCRIPTION: Attackers exploit flaws to access data or disrupt services. | Customers; employees; business partners | Cyber & Technology | Cyber Security | 4 | 5 | 20 | Critical | TLS, code review, perimeter firewall and production logging. | Test code before release; scan the website and APIs for weaknesses; use a web application firewall; fix serious flaws quickly. | Engineering Director | 2026-08-31 | 2 | 5 | 10 | High | Planned
R-03 | RISK NAME: Malware or ransomware infection HAZARD: Malicious software DESCRIPTION: Malware steals or encrypts data and interrupts operations. | Employees; customers; operations | Cyber & Technology | Cyber Security | 4 | 5 | 20 | Critical | Anti-malware, backups and email filtering. | Install advanced endpoint protection; limit malware spreading between systems; keep protected offline backups; test the ransomware response plan. | IT Operations Manager | 2026-08-20 | 2 | 4 | 8 | Medium | In Progress
R-04 | RISK NAME: Customer data breach HAZARD: Unauthorised access to personal data DESCRIPTION: Customer information is exposed, causing legal and reputational harm. | Customers; TechTraders; regulators | Cyber & Technology | Data Privacy | 4 | 5 | 20 | Critical | Privacy notice, role-based access and encryption in transit. | Classify sensitive data; restrict access to authorised staff; encrypt stored information; monitor data transfers; review access and retention regularly. | Data Protection Officer | 2026-08-31 | 2 | 5 | 10 | High | Planned
R-05 | RISK NAME: Payment-card data theft HAZARD: Compromised payment system DESCRIPTION: Stolen card details cause fraud and loss of trust. | Customers; finance; TechTraders | Financial | Financial Fraud | 3 | 5 | 15 | Critical | Third-party payment service, TLS and restricted payment access. | Use tokenised or hosted payment fields; prevent unauthorised checkout scripts; monitor script changes; complete PCI DSS security checks. | Payments Product Owner | 2026-08-10 | 1 | 5 | 5 | Medium | In Progress
R-06 | RISK NAME: Staff phishing attack HAZARD: Fraudulent emails or login pages DESCRIPTION: Staff reveal credentials or unknowingly install malware. | Employees; customers; business | People & Behaviour | Social Engineering | 5 | 4 | 20 | Critical | Spam filtering and annual awareness training. | Require phishing-resistant MFA; block risky logins; run staff phishing exercises; verify payment or account-change requests through a second channel. | Security Awareness Lead | 2026-08-15 | 2 | 4 | 8 | Medium | Planned
R-07 | RISK NAME: Insider data misuse HAZARD: Unauthorised staff access DESCRIPTION: Staff intentionally or accidentally disclose protected information. | Customers; employees; business | People & Behaviour | Insider Threat | 3 | 5 | 15 | Critical | Employment screening and standard access permissions. | Limit privileged access; separate sensitive duties; approve large data exports; monitor unusual activity; remove access promptly when staff leave. | HR & IT Access Owner | 2026-09-15 | 2 | 4 | 8 | Medium | Planned
R-08 | RISK NAME: Distributed denial-of-service (DDoS) attack HAZARD: Excessive malicious traffic DESCRIPTION: The platform becomes unavailable to genuine customers. | Customers; sales; operations | Operational | Business Continuity | 4 | 4 | 16 | Critical | Cloud hosting, CDN and basic auto-scaling. | Use managed DDoS and bot protection; increase capacity across multiple locations; test peak traffic; maintain outage and customer-communication procedures. | Site Reliability Lead | 2026-08-15 | 2 | 3 | 6 | Medium | In Progress
R-09 | RISK NAME: Cloud-system misconfiguration HAZARD: Incorrect cloud security settings DESCRIPTION: Exposed cloud resources allow unauthorised access. | Customers; employees; business | Cyber & Technology | System Failure | 4 | 5 | 20 | Critical | Cloud IAM and manual deployment review. | Build cloud systems from approved secure templates; automatically block unsafe settings; protect passwords and keys; monitor configuration changes continuously. | Cloud Platform Lead | 2026-08-31 | 2 | 4 | 8 | Medium | Planned
R-10 | RISK NAME: Unpatched software vulnerabilities HAZARD: Outdated software DESCRIPTION: Known weaknesses are exploited to compromise services. | Customers; employees; business | Cyber & Technology | Software/Hardware | 4 | 5 | 20 | Critical | Monthly patching and developer dependency alerts. | Maintain a complete software inventory; prioritise critical patches; automate dependency updates; apply temporary protection when immediate patching is impossible. | Vulnerability Manager | 2026-08-20 | 2 | 4 | 8 | Medium | In Progress
RISK LEVEL LEGEND
Critical (15–25) |  |  |  | Immediate action — stop or redesign activity
High (10–14) |  |  |  | Urgent controls needed — inform senior management
Medium (5–9) |  |  |  | Monitor closely — additional controls required
Low (1–4) |  |  |  | Acceptable — review periodically

## Risk Heatmap
RISK SCORE HEATMAP - Likelihood × Severity
Use this matrix to identify the risk level for any combination of Likelihood and Severity.
SEVERITY →
← LIKELIHOOD |  | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic
| 5 – Almost Certain | 5 Medium | 10 High | 15 Critical | 20 Critical | 25 Critical
| 4 – Likely | 4 Low | 8 Medium | 12 High | 16 Critical | 20 Critical
| 3 – Possible | 3 Low | 6 Medium | 9 Medium | 12 High | 15 Critical
| 2 – Unlikely | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 High
| 1 – Rare | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium

## Action Tracker
RISK CONTROL ACTION TRACKER
Risk ID | Risk Description | Action Required | Priority | Responsible Person | Start Date | Target Date | Completion Date | Evidence / Notes | Status
R-01 | RISK NAME: Customer account takeover HAZARD: Stolen login credentials DESCRIPTION: Criminals access accounts to steal data or make purchases. | Require multi-factor authentication; block repeated login attempts; detect automated bots; warn customers about suspicious account activity. | High | Head of Security | 2026-07-22 | 2026-08-15 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | In Progress
R-02 | RISK NAME: Web application or API attack HAZARD: Vulnerable website, app or API DESCRIPTION: Attackers exploit flaws to access data or disrupt services. | Test code before release; scan the website and APIs for weaknesses; use a web application firewall; fix serious flaws quickly. | High | Engineering Director | 2026-07-22 | 2026-08-31 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | Planned
R-03 | RISK NAME: Malware or ransomware infection HAZARD: Malicious software DESCRIPTION: Malware steals or encrypts data and interrupts operations. | Install advanced endpoint protection; limit malware spreading between systems; keep protected offline backups; test the ransomware response plan. | High | IT Operations Manager | 2026-07-22 | 2026-08-20 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | In Progress
R-04 | RISK NAME: Customer data breach HAZARD: Unauthorised access to personal data DESCRIPTION: Customer information is exposed, causing legal and reputational harm. | Classify sensitive data; restrict access to authorised staff; encrypt stored information; monitor data transfers; review access and retention regularly. | High | Data Protection Officer | 2026-07-22 | 2026-08-31 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | Planned
R-05 | RISK NAME: Payment-card data theft HAZARD: Compromised payment system DESCRIPTION: Stolen card details cause fraud and loss of trust. | Use tokenised or hosted payment fields; prevent unauthorised checkout scripts; monitor script changes; complete PCI DSS security checks. | High | Payments Product Owner | 2026-07-22 | 2026-08-10 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | In Progress
R-06 | RISK NAME: Staff phishing attack HAZARD: Fraudulent emails or login pages DESCRIPTION: Staff reveal credentials or unknowingly install malware. | Require phishing-resistant MFA; block risky logins; run staff phishing exercises; verify payment or account-change requests through a second channel. | High | Security Awareness Lead | 2026-07-22 | 2026-08-15 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | Planned
R-07 | RISK NAME: Insider data misuse HAZARD: Unauthorised staff access DESCRIPTION: Staff intentionally or accidentally disclose protected information. | Limit privileged access; separate sensitive duties; approve large data exports; monitor unusual activity; remove access promptly when staff leave. | High | HR & IT Access Owner | 2026-07-22 | 2026-09-15 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | Planned
R-08 | RISK NAME: Distributed denial-of-service (DDoS) attack HAZARD: Excessive malicious traffic DESCRIPTION: The platform becomes unavailable to genuine customers. | Use managed DDoS and bot protection; increase capacity across multiple locations; test peak traffic; maintain outage and customer-communication procedures. | High | Site Reliability Lead | 2026-07-22 | 2026-08-15 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | In Progress
R-09 | RISK NAME: Cloud-system misconfiguration HAZARD: Incorrect cloud security settings DESCRIPTION: Exposed cloud resources allow unauthorised access. | Build cloud systems from approved secure templates; automatically block unsafe settings; protect passwords and keys; monitor configuration changes continuously. | High | Cloud Platform Lead | 2026-07-22 | 2026-08-31 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | Planned
R-10 | RISK NAME: Unpatched software vulnerabilities HAZARD: Outdated software DESCRIPTION: Known weaknesses are exploited to compromise services. | Maintain a complete software inventory; prioritise critical patches; automate dependency updates; apply temporary protection when immediate patching is impossible. | High | Vulnerability Manager | 2026-07-22 | 2026-08-20 |  | Evidence: approved design/change ticket, configuration screenshots, test results, review minutes and updated procedures. | In Progress

## Guidance Notes
HOW TO USE THIS RISK MANAGEMENT WORKBOOK
SHEETS OVERVIEW
| Risk Register | Complete one row per identified hazard. Risk Score and Risk Level are auto-calculated.
| Risk Heatmap | 5×5 colour-coded matrix showing how Likelihood and Severity combine into a risk level.
| Action Tracker | Log all control actions, assign responsibility, and track completion.
| Guidance Notes | This page — definitions and instructions.
LIKELIHOOD SCALE
| 1 – Rare | Could happen but probably never will (once every 5+ years)
| 2 – Unlikely | Not expected but possible (once every 2–5 years)
| 3 – Possible | Could occur at some time (once per year)
| 4 – Likely | Will probably occur in most circumstances (monthly)
| 5 – Almost Certain | Expected to occur in most circumstances (weekly/daily)
SEVERITY SCALE
| 1 – Negligible | No impact; minor inconvenience
| 2 – Minor | Small impact; easily recoverable
| 3 – Moderate | Noticeable impact; some recovery effort needed
| 4 – Major | Significant impact; difficult to recover from
| 5 – Catastrophic | Severe or irreversible impact
RISK LEVEL GUIDE
| Low (1–4) | Monitor and review periodically; standard controls sufficient
| Medium (5–9) | Manage through routine procedures; monitor more frequently
| High (10–14) | Urgent action required; inform responsible person immediately
| Critical (15–25) | Stop or redesign activity until risk is reduced to acceptable level
RISK CATEGORIES
| Cyber & Technology | Cyber Security, Data Privacy, System Failure, Software/Hardware
| People & Behaviour | Human Error, Insider Threat, Social Engineering, Reputational
| Operational | Process Failure, Supply Chain, Business Continuity, Compliance / Legal
| Physical & Environmental | Physical Security, Natural Disaster, Environmental, Health & Safety
| Financial | Financial Fraud, Budget Overrun, Economic
| Strategic | Strategic, Political / Regulatory, Third Party / Vendor
TIPS FOR STUDENTS
| Research first | Identify risks through research before filling in the register
| Be specific | Describe the hazard clearly — avoid vague terms like 'something goes wrong'
| Think about controls | Consider both existing controls and what additional ones are needed
| Residual risk | After controls are applied, re-score Likelihood and Severity to get residual risk
| Hierarchy of controls | Eliminate > Substitute > Engineering > Administrative > PPE

## Assessment Summary
TECHTRADERS LTD. — CYBERSECURITY RISK ASSESSMENT SUMMARY
Scope: customer website, mobile app, cloud services, payment integration, staff endpoints, customer service, suppliers and supporting operations.
1. DATA CLASSIFICATION SCHEME
Class | Definition | TechTraders examples | Required handling | Access | Storage / transfer | Retention / disposal | Owner
Public | Approved for unrestricted release. | Product catalogue, published prices, public policies, marketing content. | Integrity and publishing approval are the priority. | Anyone after approval. | Normal business storage; HTTPS for official publishing. | Retain to business need; normal secure deletion. | Marketing / Product
Internal | Non-public operational information with limited harm if disclosed. | Internal procedures, project plans, routine staff communications. | Label Internal; do not post publicly; share on need-to-know basis. | Authenticated workforce and approved suppliers. | Approved collaboration tools; encrypted transfer externally. | Schedule by business/legal need; controlled disposal. | Department owner
Confidential | Personal or commercially sensitive data causing material harm if disclosed. | Customer names, addresses, order history, support records, employee data, contracts, sales reports. | Encrypt; least privilege; access logging; DLP; approved sharing; incident escalation. | Named roles with quarterly review. | Encryption at rest/in transit; no unmanaged devices or personal email. | Documented retention; secure deletion and deletion verification. | DPO / Data owner
Restricted | Highest-impact or regulated secrets; compromise could enable fraud or systemic access. | Payment tokens, authentication secrets, API keys, admin credentials, encryption keys, vulnerability reports. | Vault/tokenise; MFA/PAM; dual control where appropriate; continuous monitoring; never email plaintext. | Minimal named privileged roles; time-bound approval. | HSM/secrets vault; strong encryption; segmented systems; prohibit local copies. | Shortest necessary period; cryptographic erasure and logged destruction. | CISO / System owner
2. METHODOLOGY EVALUATION AND SELECTION
Method | Strengths | Limitations | Fit for TechTraders | Decision | Scoring approach | Review cycle | Output
NIST SP 800-30 Rev.1 | Clear threat–vulnerability–impact process; repeatable and evidence-based. | Detailed process needs tailoring for a medium-sized retailer. | Strong fit for system and scenario risk assessment. | SELECTED as assessment method. | 5×5 likelihood × severity; inherent and residual scores. | Quarterly and after major change/incident. | Risk register and treatment actions.
ISO/IEC 27005 | Aligns well with ISO 27001 governance and continuous improvement. | Less prescriptive; standard access and implementation effort may be higher. | Useful governance overlay if certification is pursued. | Use as supporting lifecycle guidance. | Organisation-defined criteria. | At ISMS review points. | Risk treatment plan.
OCTAVE Allegro | Asset-focused and workshop-friendly; strong business context. | More workshop time; less direct technical control mapping. | Useful for focused data-asset workshops. | Not primary; use selectively. | Qualitative impact areas. | For major services/data flows. | Asset risk profiles.
Selected hybrid | NIST SP 800-30 assessment steps + this workbook's 5×5 matrix + NIST CSF 2.0 gap profile. | Scores are relative and require calibrated judgement; not a substitute for testing. | Balances rigour, speed and communication for TechTraders. | APPROVED RECOMMENDATION. | 1–5 likelihood and impact; score 1–25; record assumptions and evidence. | Quarterly; annually full refresh. | Register, heatmap, gap plan, action tracker and metrics.
3. HOW RISKS, THREATS AND VULNERABILITIES ARE ASSESSED
Step | Activity | Evidence | Key question | Output | Owner | Cadence | Quality check
1 | Prepare: define scope, business objectives, assets, data flows, dependencies and risk appetite. | Architecture, inventory, data-flow maps, contracts, business impact analysis. | What must TechTraders protect to continue trading? | Assessment scope and assumptions. | CIO / Risk owner | Annual / major change | Scope approved by business and technology.
2 | Identify threat events and sources: cybercriminals, insiders, suppliers, automation abuse, failures and disasters. | Threat intelligence, incidents, fraud trends, supplier reports. | Who or what could cause harm, and by what event? | Specific threat scenarios. | Security lead | Quarterly | Avoid vague one-word risks.
3 | Identify vulnerabilities and predisposing conditions. | Scans, penetration tests, configuration reviews, access reviews, audit findings. | What weakness makes the threat credible? | Evidence-linked weaknesses. | Control owners | Continuous / scheduled | Validate findings; remove duplicates.
4 | Assess likelihood using threat capability/intent, exposure, control effectiveness and event frequency. | Telemetry, attack data, control tests, past incidents. | How probable is the scenario within the stated period? | Likelihood 1–5 with rationale. | Risk workshop | Quarterly | Use Guidance Notes scale consistently.
5 | Assess impact across confidentiality, integrity, availability, safety, legal, financial and reputation. | BIA, revenue/downtime estimates, data volumes, legal obligations. | What is the credible worst consequence? | Severity 1–5 with rationale. | Business owner / DPO | Quarterly | Consider customers and business success.
6 | Calculate inherent risk, evaluate controls, define treatment, then score residual risk and obtain acceptance. | Control design/operating tests, tickets, exercise results. | Is residual risk within appetite; who accepts it? | Prioritised treatment and accountable owner. | Executive risk owner | Quarterly | Acceptance must be explicit and time-limited.
4. MALWARE, CONFIDENTIALITY EXPOSURE, COUNTERMEASURES AND HARDENING
Topic | Potential outcomes | Prevent | Detect | Respond / recover | Evaluation | Business measure | Conclusion
Malware / ransomware | Website/app outage; fulfilment and support interruption; encrypted or stolen data; fraud; recovery cost; lost sales; contractual/regulatory response; reputational harm. | EDR, patching, allow-listing, phishing-resistant MFA, segmentation, least privilege, secure email/web controls. | EDR/XDR, SIEM, canary alerts, unusual encryption/exfiltration detection. | Isolate hosts, revoke credentials, preserve evidence, eradicate, restore immutable backups, notify stakeholders as required. | Defence-in-depth is strongest when controls are tested; signature-only antivirus and untested backups are insufficient. | Recovery time, restore success, downtime cost, detection/containment time. | Prioritise R-03, R-10, R-12 and R-13.
Confidential data exposure | Identity theft, account takeover, targeted fraud, customer distress, complaints, loss of trust, litigation, supplier claims and possible regulatory investigation/notification. | Classification, minimisation, encryption, tokenisation, least privilege, PAM, secure coding, DLP and supplier controls. | Access analytics, DLP alerts, cloud exposure monitoring, export and admin audit logs. | Contain access, identify affected records, assess risk to people, document notification decision, support customers, remediate root cause. | Encryption reduces harm only if keys and privileged access remain protected; prevention must be paired with monitoring and response. | Records exposed, complaint rate, churn, notification time, access-review exceptions. | Prioritise R-02, R-04, R-05, R-07 and R-09.
Identity and access | Limits both external account takeover and insider misuse. | MFA/passkeys, RBAC, least privilege, PAM, joiner-mover-leaver automation. | Impossible travel, risky sign-in and privileged-session alerts. | Rapid disablement and credential/key rotation. | High value and broad coverage; usability and recovery processes must be designed well. | MFA coverage; stale accounts; access review completion. | Foundational countermeasure.
Secure engineering | Prevents vulnerabilities from entering web, mobile, API and cloud releases. | Threat modelling, coding standards, SAST/DAST/SCA, IaC scanning, peer review. | WAF/API telemetry, error and abuse monitoring. | Rollback, hotfix and coordinated vulnerability response. | Most effective when release gates are risk-based and false positives are managed. | Critical defects; remediation SLA; change failure rate. | Protects revenue and release velocity.
System hardening purpose | Reduce attack surface; remove defaults; enforce secure configuration; contain compromise; create a repeatable, auditable baseline. | Disable unused services/ports, patch, secure builds, endpoint firewall, encryption, secure boot, separate admin accounts, secrets management. | Configuration drift monitoring and baseline compliance scans. | Rebuild from trusted images and rotate secrets. | Hardening lowers likelihood and blast radius but requires compatibility testing, exception governance and continuous maintenance. | Baseline compliance; drift age; exploitable services; patch SLA. | Apply to cloud, servers, endpoints, network devices, containers and mobile back ends.
Business success | Security protects availability, customer trust, lawful trading and predictable operations while enabling safer growth. | Prioritise controls by customer/revenue impact and residual risk. | Board dashboard combining risk, reliability, fraud, privacy and delivery indicators. | Exercise crisis decisions and communicate transparently. | Success is reduced loss and resilient service—not merely control counts. Excessive friction or poorly targeted spend can harm conversion and innovation. | Checkout availability, conversion, fraud loss, churn, downtime, audit findings, time to release. | Treat security as a business capability with accountable outcomes.
REFERENCES (OFFICIAL SOURCES)
NIST SP 800-30 Rev.1 | https://www.nist.gov/publications/guide-conducting-risk-assessments
NIST Cybersecurity Framework 2.0 | https://www.nist.gov/cyberframework
PCI DSS v4.0.1 | https://blog.pcisecuritystandards.org/just-published-pci-dss-v4-0-1
ICO personal data breach guidance | https://ico.org.uk/for-organisations/report-a-breach/personal-data-breach/personal-data-breaches-a-guide/

## Gap Analysis
TECHTRADERS LTD. — CYBERSECURITY GAP ANALYSIS PLAN
Approach: compare the current state with a risk-based target profile aligned to NIST CSF 2.0; validate through interviews, document review, technical testing and evidence sampling.
ID | Area / target outcome | Current state | Gap / risk | Planned action | Owner | Priority | Target date | Evidence of completion | Success measure
G-01 | Govern: approved cyber risk appetite and accountable owners. | Ad-hoc meetings; unclear control ownership. | Decisions and acceptance may be inconsistent. | Approve appetite, RACI, quarterly risk forum and exception process. | CIO | Critical | 2026-08-31 | Board minutes; RACI; risk policy. | 100% critical risks have named executive owner and decision.
G-02 | Identify: complete asset, data and dependency inventory. | Partial technical inventories; no unified data map. | Unknown assets and data flows escape protection. | Create ownership-based inventory, data-flow maps and supplier dependencies. | Enterprise Architect | Critical | 2026-09-15 | Inventory export; approved maps. | ≥98% discovered assets assigned owner/classification.
G-03 | Protect: formal four-level data classification and handling. | Informal labels and inconsistent retention. | Confidential data may be over-shared or retained too long. | Adopt scheme in Assessment Summary; train staff; add handling and retention controls. | DPO | Critical | 2026-09-15 | Policy; training; labelled repositories; retention schedule. | 100% priority repositories classified; ≥95% training completion.
G-04 | Protect: phishing-resistant identity and privileged access. | MFA incomplete; standing administrator access. | Credential theft can become broad compromise. | Roll out MFA/passkeys, conditional access, PAM and automated lifecycle controls. | IAM Lead | Critical | 2026-09-30 | Coverage reports; PAM logs; access reviews. | 100% privileged and ≥98% workforce MFA; zero orphan admin accounts.
G-05 | Protect: secure development and vulnerability management. | Inconsistent scans and monthly patch cycle. | Critical web/API/dependency flaws may reach production. | Implement threat modelling, SAST/DAST/SCA/IaC gates and risk-based SLAs. | Engineering Director | Critical | 2026-09-30 | Pipeline controls; penetration test; SLA dashboard. | No overdue critical flaws; ≥95% high flaws within SLA.
G-06 | Protect: hardened, continuously monitored cloud and endpoint baselines. | Manual build review; configuration drift not measured. | Misconfiguration and unused services increase attack surface. | Publish baselines; enforce IaC/policy-as-code; EDR; drift monitoring; exception expiry. | Cloud Platform Lead | High | 2026-10-15 | Baseline scans; EDR inventory; approved exceptions. | ≥95% baseline compliance; 100% supported endpoints report to EDR.
G-07 | Detect: central telemetry and actionable detection coverage. | Application logs fragmented; limited 24/7 alert route. | Attackers may remain undetected and evidence may be lost. | Central SIEM, retention standard, high-risk detections and alert escalation. | Security Operations Lead | Critical | 2026-09-30 | SIEM dashboards; alert tests; retention settings. | ≥90% critical log sources onboarded; high alerts triaged within 30 minutes.
G-08 | Respond: tested incident and personal-data-breach process. | Informal escalation and limited exercises. | Slow containment and poor notification decisions increase harm. | Define roles/playbooks; maintain decision log; run ransomware and breach tabletops. | CISO / DPO | Critical | 2026-09-15 | Approved plans; exercise report; action closure. | Two exercises/year; all high-priority lessons closed within 60 days.
G-09 | Recover: immutable backups and proven recovery objectives. | Daily cloud backup; restoration not routinely tested. | Ransomware or deletion could cause prolonged outage. | Implement 3-2-1/immutable design; approve RPO/RTO; quarterly restore and annual DR test. | Business Continuity Lead | Critical | 2026-09-30 | Restore logs; DR report; RPO/RTO approval. | 100% quarterly restore tests pass; critical services meet RTO.
G-10 | Supply chain: tiered assurance and controlled integrations. | Contract-led, informal supplier review. | Supplier compromise may expose data or interrupt fulfilment. | Tier suppliers; due diligence; clauses; least-privilege access; ongoing assurance and exit plans. | Procurement Manager | High | 2026-10-31 | Tier register; assessments; contract clauses. | 100% critical suppliers assessed annually and have incident contacts.
G-11 | Payment security: minimise card-data environment and monitor scripts. | Third-party processor used; assurance fragmented. | Checkout compromise could drive fraud and loss of payment capability. | Confirm scope; use hosted/tokenised fields; script inventory/authorisation/integrity monitoring; PCI evidence. | Payments Product Owner | Critical | 2026-09-15 | Scope diagram; PCI evidence; script reports. | No sensitive authentication data stored; 100% checkout scripts authorised.
G-12 | Measure business outcomes and continuously improve. | Technical activity counts dominate reporting. | Security investment may not align to revenue, trust or resilience. | Board scorecard: residual risk, checkout availability, fraud loss, breach/incident time, recovery, exceptions and delivery impact. | CIO | High | 2026-10-15 | Approved scorecard; quarterly review pack. | Quarterly decisions documented; critical residual risks trend downward.