University of Wales Trinity St. David

Project Planning - M5X01176

George Dalton – Brown

1801728

BEng Motorsport Engineering

Contents

Abstract - 3

List of Members & Responsibilities - 4

List of Overall Group Tasks & Associated Timings - 5

List of Tasks - 9

List of Tasks (Detailed) - 9

Bill of Materials - 10

Project Gateway - 11

Areas of Concern - 12

Overall Summaries - 13

- Abstract

This year’s group project module is based around using the pre-existing Formula 3 “tub” chassis to generate a preliminary plan for running the vehicle as a purpose-built electric hill climb car. This chassis was the only component that we were given, the rest was completely determined by us, the group.

The class has been split into multiple groups that focus on different aspects of the car, however all groups are working towards the same shared goal. The groups’ areas of responsibility are; aerodynamics, simulation, chassis and finally powertrain and control. As I am part of the powertrain and control group it is our job to identify a suitable method of propulsion and all of the related parts. As a group we decided that we would meet at a minimum of once a week on a Tuesday on top of the Monday lecture and would meet more than this should circumstances require it for busier weeks.

Despite this project being group based and smaller sub-groups, each individual person has a specific aspect of the car that they are responsible for in the powertrain group.

- List of Members & Responsibilities

Tim Stanbury: Power storage, Tim is responsible for selecting the appropriate power storage device a long with calculating the estimated values for energy storage.

Reza Shaife Pour Motlagh: Motors, Reza is responsible for finding and selecting the motor or motors that will drive the vehicle and works with person responsible the transmission to decide on ratios and angular motion related calculations.

Pete Olliffe: Safety and Regulations, Pete is responsible for investigating research rules and safety regulations that the vehicle and the driver will have to abide by in order to compete in an electric hill climb series.

Jeff Elliss: Transmission, works with Reza to decide on possible motor solutions in relation to number of motors and how the drive from these motors will be sent to the wheels of the vehicle.

Stefan Robinson: Cooling, Steffan is responsible for deciding on the method of cooling for the whole of the powertrain system based off calculations using values that he will be given to by the other members of the groups.

Dan Wilcox: Duty Cycle, Dan’s research mainly revolves around looking deep into and analysing statistics for potential tracks that we would potentially be competing on, this includes looking into aspects like the amount of time each run takes and the top speed that could potentially be reached this data is then fed back to other members of the group like transmission and motors to make sure that these components are to the correct specifications.

George Dalton – Brown: Controllers, My area of responsibility is controllers, this includes motor controllers along with all chassis controllers like accelerometers and additionally other features such as launch control and abs. In addition to this there are some parts of the car that could be useful to pull data off for example battery temperatures and tyre temperatures. These temperatures need to be monitored to ensure that the car is always run in its optimal condition for both performance and safety.

The Belbin’s model questionnaire determined that my personality trait is that of a teamworker, this means that I encourage co-operation within the group which is ideal for choosing controllers as I need information from each member to ensure that the controllers that I choose are compatible with the other components that the other members of the group have chosen and that they conform to the regulations.

- List of Overall Group Tasks and Associated Timings

| Task Name | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- |
| Team Meetings | 126.13 days | Mon 30/09/19 | Tue 24/03/20 | Dan W,George DB,Jeff E,Peter O,Reza SPM,Steffan R,Tim S |
| Team Meetings 1 | 1 hr | Mon 30/09/19 | Mon 30/09/19 |  |
| Team Meetings 2 | 1 hr | Tue 01/10/19 | Tue 01/10/19 |  |
| Team Meetings 3 | 1 hr | Mon 07/10/19 | Mon 07/10/19 |  |
| Team Meetings 4 | 1 hr | Tue 08/10/19 | Tue 08/10/19 |  |
| Team Meetings 5 | 1 hr | Mon 14/10/19 | Mon 14/10/19 |  |
| Team Meetings 6 | 1 hr | Tue 15/10/19 | Tue 15/10/19 |  |
| Team Meetings 7 | 1 hr | Mon 21/10/19 | Mon 21/10/19 |  |
| Team Meetings 8 | 1 hr | Tue 22/10/19 | Tue 22/10/19 |  |
| Team Meetings 9 | 1 hr | Mon 28/10/19 | Mon 28/10/19 |  |
| Team Meetings 10 | 1 hr | Tue 29/10/19 | Tue 29/10/19 |  |
| Team Meetings 11 | 1 hr | Mon 04/11/19 | Mon 04/11/19 |  |
| Team Meetings 12 | 1 hr | Tue 05/11/19 | Tue 05/11/19 |  |
| Team Meetings 13 | 1 hr | Mon 11/11/19 | Mon 11/11/19 |  |
| Team Meetings 14 | 1 hr | Tue 12/11/19 | Tue 12/11/19 |  |
| Team Meetings 15 | 1 hr | Mon 18/11/19 | Mon 18/11/19 |  |
| Team Meetings 16 | 1 hr | Tue 19/11/19 | Tue 19/11/19 |  |
| Team Meetings 17 | 1 hr | Mon 25/11/19 | Mon 25/11/19 |  |
| Team Meetings 18 | 1 hr | Tue 26/11/19 | Tue 26/11/19 |  |
| Team Meetings 19 | 1 hr | Mon 02/12/19 | Mon 02/12/19 |  |
| Team Meetings 20 | 1 hr | Tue 03/12/19 | Tue 03/12/19 |  |
| Team Meetings 21 | 1 hr | Mon 09/12/19 | Mon 09/12/19 |  |
| Team Meetings 22 | 1 hr | Tue 10/12/19 | Tue 10/12/19 |  |
| Team Meetings 23 | 1 hr | Mon 16/12/19 | Mon 16/12/19 |  |
| Team Meetings 24 | 1 hr | Tue 17/12/19 | Tue 17/12/19 |  |
| Team Meetings 25 | 1 hr | Mon 23/12/19 | Mon 23/12/19 |  |
| Team Meetings 26 | 1 hr | Tue 24/12/19 | Tue 24/12/19 |  |
| Team Meetings 27 | 1 hr | Mon 30/12/19 | Mon 30/12/19 |  |
| Team Meetings 28 | 1 hr | Tue 31/12/19 | Tue 31/12/19 |  |
| Team Meetings 29 | 1 hr | Mon 06/01/20 | Mon 06/01/20 |  |
| Team Meetings 30 | 1 hr | Tue 07/01/20 | Tue 07/01/20 |  |
| Team Meetings 31 | 1 hr | Mon 13/01/20 | Mon 13/01/20 |  |
| Team Meetings 32 | 1 hr | Tue 14/01/20 | Tue 14/01/20 |  |
| Team Meetings 33 | 1 hr | Mon 20/01/20 | Mon 20/01/20 |  |
| Team Meetings 34 | 1 hr | Tue 21/01/20 | Tue 21/01/20 |  |
| Team Meetings 35 | 1 hr | Mon 27/01/20 | Mon 27/01/20 |  |
| Team Meetings 36 | 1 hr | Tue 28/01/20 | Tue 28/01/20 |  |
| Team Meetings 37 | 1 hr | Mon 03/02/20 | Mon 03/02/20 |  |
| Team Meetings 38 | 1 hr | Tue 04/02/20 | Tue 04/02/20 |  |
| Team Meetings 39 | 1 hr | Mon 10/02/20 | Mon 10/02/20 |  |
| Team Meetings 40 | 1 hr | Tue 11/02/20 | Tue 11/02/20 |  |
| Team Meetings 41 | 1 hr | Mon 17/02/20 | Mon 17/02/20 |  |
| Team Meetings 42 | 1 hr | Tue 18/02/20 | Tue 18/02/20 |  |
| Team Meetings 43 | 1 hr | Mon 24/02/20 | Mon 24/02/20 |  |
| Team Meetings 44 | 1 hr | Tue 25/02/20 | Tue 25/02/20 |  |
| Team Meetings 45 | 1 hr | Mon 02/03/20 | Mon 02/03/20 |  |
| Team Meetings 46 | 1 hr | Tue 03/03/20 | Tue 03/03/20 |  |
| Team Meetings 47 | 1 hr | Mon 09/03/20 | Mon 09/03/20 |  |
| Team Meetings 48 | 1 hr | Tue 10/03/20 | Tue 10/03/20 |  |
| Team Meetings 49 | 1 hr | Mon 16/03/20 | Mon 16/03/20 |  |
| Team Meetings 50 | 1 hr | Tue 17/03/20 | Tue 17/03/20 |  |
| Team Meetings 51 | 1 hr | Mon 23/03/20 | Mon 23/03/20 |  |
| Team Meetings 52 | 1 hr | Tue 24/03/20 | Tue 24/03/20 |  |
| Duty Cycle | 120.63 days | Mon 07/10/19 | Mon 23/03/20 |  |
| Track research | 5 hrs | Mon 07/10/19 | Mon 07/10/19 | Dan W |
| Record runs | 2 hrs | Mon 07/10/19 | Mon 07/10/19 | Dan W |
| Research Top Speeds | 3 hrs | Mon 14/10/19 | Mon 14/10/19 | Dan W |
| Calculate average speed | 2 hrs | Mon 14/10/19 | Mon 14/10/19 | Dan W |
| Time on Throttle | 4 hrs | Mon 28/10/19 | Mon 28/10/19 | Dan W |
| Calculate wheel speed | 2 hrs | Mon 04/11/19 | Mon 04/11/19 | Dan W |
| Heat loss | 6 hrs | Mon 04/11/19 | Mon 04/11/19 | Dan W |
| Group Project week | 20 hrs | Mon 04/11/19 | Wed 06/11/19 | Dan W |
| Viva preparation | 5 hrs | Mon 25/11/19 | Mon 25/11/19 | Dan W |
| Testing | 30 hrs | Mon 03/02/20 | Thu 06/02/20 | Dan W |
| Report | 5 hrs | Mon 02/03/20 | Mon 02/03/20 | Dan W |
| Final viva | 5 hrs | Mon 23/03/20 | Mon 23/03/20 | Dan W |
| Motors | 39.75 days | Mon 07/10/19 | Fri 29/11/19 |  |
| Identify power and torque requirements | 3 hrs | Mon 07/10/19 | Mon 07/10/19 | Reza SPM |
| Finalize motor choice | 2 hrs | Mon 14/10/19 | Mon 14/10/19 | Reza SPM |
| work with group on power storage solution | 6 hrs | Fri 01/11/19 | Fri 01/11/19 | Reza SPM |
| cost motors | 6 hrs | Mon 07/10/19 | Mon 07/10/19 | Reza SPM |
| meet with chassis group to determine motor and battery positioning | 12 hrs | Wed 16/10/19 | Thu 17/10/19 | Reza SPM |
| run FEA on rear subframe and motor cage | 22 hrs | Wed 27/11/19 | Fri 29/11/19 | Reza SPM |
| perform shakedown runs at various circuits and tracks | 20 hrs |  |  | Reza SPM |
| Cooling | 90.38 days | Mon 07/10/19 | Mon 10/02/20 |  |
| Cooling in EV's | 4 hrs | Mon 07/10/19 | Mon 07/10/19 | Steffan R |
| High performance systems | 4 hrs | Mon 14/10/19 | Mon 14/10/19 | Steffan R |
| Emrax motors | 5 hrs | Mon 21/10/19 | Mon 21/10/19 | Steffan R |
| Heat to lose per run | 6 hrs | Mon 28/10/19 | Mon 28/10/19 | Steffan R |
| Radiators | 4 hrs | Mon 04/11/19 | Mon 04/11/19 | Steffan R |
| Basic cooling understanding | 2 hrs | Mon 11/11/19 | Mon 11/11/19 | Steffan R |
| Flow rate | 4 hrs | Mon 18/11/19 | Mon 18/11/19 | Steffan R |
| Finding a pump | 3 hrs | Mon 25/11/19 | Mon 25/11/19 | Steffan R |
| Calculating amount of water/coolant | 7 hrs | Mon 02/12/19 | Mon 02/12/19 | Steffan R |
| Mapping the system | 5 hrs | Mon 06/01/20 | Mon 06/01/20 | Steffan R |
| Piping | 3 hrs | Mon 20/01/20 | Mon 20/01/20 | Steffan R |
| Testing | 3 hrs | Mon 10/02/20 | Mon 10/02/20 | Steffan R |
| Batteries | 128.75 days | Mon 09/09/19 | Thu 05/03/20 |  |
| Research of energy storage | 10 hrs | Mon 09/09/19 | Tue 10/09/19 | Tim S |
| Finding the batteries | 5 hrs | Mon 16/09/19 | Mon 16/09/19 | Tim S |
| Identify quantity and parameters | 6 hrs | Mon 23/09/19 | Mon 23/09/19 | Tim S |
| Create CAD model | 15 hrs | Mon 30/09/19 | Tue 01/10/19 | Tim S |
| Buy the batteries | 2 hrs | Mon 02/12/19 | Mon 02/12/19 | Tim S |
| Test the batteries | 20 hrs | Mon 13/01/20 | Wed 15/01/20 | Tim S |
| fit the battery packs into the car | 30 hrs | Mon 02/03/20 | Thu 05/03/20 | Tim S |
| Transmission | 90.5 days | Mon 09/09/19 | Mon 13/01/20 |  |
| Calculate Gear Ratios | 2 hrs | Mon 09/09/19 | Mon 09/09/19 | Jeff E |
| Decide whether multiple gears required | 2 hrs | Mon 16/09/19 | Mon 16/09/19 | Jeff E |
| Choose gearbox type | 2 hrs | Mon 23/09/19 | Mon 23/09/19 | Jeff E |
| Select gear sizes | 6 hrs | Mon 25/11/19 | Mon 25/11/19 | Jeff E |
| Select shaft sizes | 4 hrs | Mon 09/12/19 | Mon 09/12/19 | Jeff E |
| Model gearbox assembly | 15 hrs | Mon 16/12/19 | Tue 17/12/19 | Jeff E |
| Analyse Model | 15 hrs | Mon 06/01/20 | Tue 07/01/20 | Jeff E |
| Size driveshafts and joints | 4 hrs | Mon 13/01/20 | Mon 13/01/20 | Jeff E |
| Health, Safety and Regulations | 39 days | Mon 07/10/19 | Thu 28/11/19 |  |
| Investigate Existing Electric Car Technical Regulations for hillclimb | 4 days | Mon 07/10/19 | Thu 10/10/19 | Peter O |
| Research Battery and electrical safety regulations for road vehicles | 4 days | Fri 11/10/19 | Wed 16/10/19 | Peter O |
| Model battery packs to fit in cad model | 14 days | Mon 21/10/19 | Thu 07/11/19 | Peter O |
| Monitor and advise on legality of developments throughout the project | 20 days | Fri 01/11/19 | Thu 28/11/19 | Peter O |
| Controllers | 101 days | Mon 14/10/19 | Mon 02/03/20 |  |
| Enquire about motor choice | 1 hr | Mon 14/10/19 | Mon 14/10/19 | George DB |
| Research compatible controller solutions | 3 hrs | Mon 21/10/19 | Mon 21/10/19 | George DB |
| Find additional sensor/feature regulations | 1 hr | Mon 28/10/19 | Mon 28/10/19 | George DB |
| Find additional sensors and additional features controllers | 8 hrs | Mon 04/11/19 | Mon 04/11/19 | George DB |
| Install all parts | 30 hrs | Mon 13/01/20 | Thu 16/01/20 | George DB |
| Test parts | 4 hrs | Mon 03/02/20 | Mon 03/02/20 | George DB |
| Test car as a whole | 8 hrs | Mon 02/03/20 | Mon 02/03/20 | George DB |

4.1) List of Tasks

| Type | Title | Start date | End date | Duration (in days) |
| --- | --- | --- | --- | --- |
| Task | Discuss motor choice with Reza | 10/14/2019 | 10/14/2019 | 1 |
| Task | Research motor controllers | 10/15/2019 | 10/21/2019 | 5 |
| Milestone | Finalise motor controller choice | 10/21/2019 | 10/21/2019 | - |
| Task | Discuss Regulations with Pete | 10/28/2019 | 10/28/2019 | 1 |
| Task | Find additional sensors and controllers | 10/29/2019 | 11/04/2019 | 5 |
| Task | Group viva preparation | 11/05/2019 | 12/04/2019 | 22 |
| Milestone | Group viva | 12/06/2019 | 12/06/2019 | - |
| Task | Setup controllers with software | 01/06/2020 | 01/20/2020 | 11 |
| Task | Install controllers | 01/21/2020 | 02/10/2020 | 15 |
| Task | Test parts while car is stationary | 02/11/2020 | 02/24/2020 | 10 |
| Task | Test parts while car is in use | 02/25/2020 | 03/09/2020 | 10 |
| Task | Group viva and report preparation | 03/10/2020 | 03/22/2020 | 9 |
| Milestone | Group viva and report deadline | 03/23/2020 | 03/23/2020 | - |

4.2 List of tasks (Detailed)

Discuss motor choice with Reza: In order for me to choose the motor controller I need to have a discussion with Reza about his final choice for the motor and number of motors that will be used to power the hillclimb vehicle. Time taken for this should be approximately two hours.

Research motor controllers: I need to use online resources to learn about motor controllers and then find some preliminary compatible possible motor controllers. Time taken for this should be approximately six hours.

Finalise motor controller choice: After conducting my research I will need to decide on the best motor controller for our vehicle by comparing all possible realistic options. Time taken for this should be approximately three hours.

Discuss Regulations with Pete: I then need to discuss with Pete the regulations that constrain what optional driving aids we can use on the vehicle, this includes things like traction and launch control as well as other features like abs. Time taken for this should be approximately two hours

Find additional sensors and controllers: After choosing aforementioned features I will then need to find components and the controllers that allow these components to do their respective job(s). Time taken for this should be approximately twenty hours

Group viva preparation: This time will be spent preparing slides and information that I am going to recall during the group viva on the 5th of December Time taken for this should be approximately 8 hours

Group viva: This is the day that the viva will be presented. Time taken for this should be approximately 1 hour.

Setup controllers with software: Controllers and other components that I have chosen will need to be integrated with some software in order for these controllers to know under which parameters they are meant to do their job(s). Time taken for this should be approximately eighteen hours

Install controllers: The controllers and various sensors now need to be installed in the vehicle including doing all of the wiring and then cable management. Time taken for this should be approximately thirty hours

Test parts while car is stationary: At this point I will then have to test all of the sensors to make sure that they are getting some form of signal or input after they have been installed on the vehicle in preparation for the next task. Time taken for this should be approximately two hours

Test parts while car is in use: The newly installed controllers then needed to be tested when the vehicle is in motion on some form of test day, but this can only occur if almost all other members of the group have correctly done their job, the date for this task can therefore depend on all other members’ successful contribution to this project. Time taken for this should be approximately nine hours.

Group viva and report preparation: The time allocated here will be used to write and submit my contribution to the group report and prepare my slides and some of the information that I will be recalling during the Viva around the 23rd of march. Time taken for this should be approximately twenty hours

Group viva and report deadline: This is the due date for the group report and viva. Time taken for this should be approximately one hour.

4.3) Bill of materials

Below is a preliminary bill of materials:

| Component | Specific Component Model | Component Price per unit (£) | Quantity | Total Component Price £ |
| --- | --- | --- | --- | --- |
| Motor Contoller | PM250DZ | 9,677.50 | 2 | 19355 |
| Wheel speed sensor | KA sensors SP08 | Price Unavailable | 4 | #VALUE! |
| Yaw sensor | Race technology DL1 pro | 1149 | 1 | 1149 |
| Steering angle senor | Race technology steering angle sensor | 238.8 | 1 | 238.8 |
| Accelerometer | Bosch Acceleration Sensor MM5.10-R | 497.27 | 1 | 497.27 |
| Tyre temperature sensor | INFKL 150°C Infrared tyre temperature sensor | 29.12 | 4 | 116.48 |
| Battery/Controller Temperature sensor | NTC M5-HS | Price Unavailable | 1 | #VALUE! |
| ABS | Bosch ABS Motorsport m5 kit 2 | Price Unavailable | 1 | #VALUE! |
| Total cost: |  |  |  | 21356.55 |

5) Project Gateway

One of the significant gateways for my area of responsibility within this project would occur at task number 6, just after milestone two.  At this point it would be wise of me to check my progress within this project, if I have not managed to hit all previous objectives by this point now would be a good time to designate some serious time into doing so as the tasks that follow this are not depended on by anyone else until the car is ready to be tested on track. The progress of this gateway can be proven by using a percentage of tasks done chart, each task is worth a set percentage that could be based on either its importance or how long the task will take, once 100% of tasks have been completed the project can continue.

This gateway occurs at a time like no other up until this point in the project. Previously other members of the powertrain group like cooling and power storage needed me to complete my tasks as information needed to be fed back to them in order to assist them to progress their contribution to this project.  By this point in the project all of my decisions should be made and all discussions with other members of my group regarding these decisions should be finished on top of this all of the assessed content for the research side of the module should be finished.

This is also an ideal time for my gateway review as my next major milestone is quite far into the future and so gives me quite a lot of time that I can use to catch up complete old tasks or this time could be used to get really far into a particularly time consuming task. If a major problem has occurred to the point where the controllers that I plan on using need to be overhauled, this point in time would be ideal to do so before I begin the process of calibrating the controllers to work within the parameters that I would like them to. This is due to the fact that calibrating, installing and wiring these components will require discussions with the chassis group as heavier components could affect their weight distribution and on top of this the calibration and installation process will take up a huge amount of my time and if it needs to change could be a huge inconvenience and effectively means that all of the installation work will need to be undone meaning that it was a waste of the time that I spent on it.

6) Areas of Concern

I have two main areas of concern and the first is controller compatibility issues, I think that I might potentially that the motor controller that I choose will not be compatible with the motor that has been selected by Reza. This could be caused by Reza changing his choice of motor during the first few initial weeks due to an issue regarding energy storage. If he changes his choice on the motor I need to be told to check and ensure that the current motor controller is compatible and if not then I will have to change my decision. This would be a catastrophic failure on a personal level but could also become a health and safety issue if it upsets the electronic circuit. On top of this, the motor controller would be very expensive and so to have one that doesn’t work would be a huge waste of money. I am also concerned about compatibility issues with the controllers as I predict that I will be using a lot of different brands of controller and so they might not communicate well when they are all being used with each other.

My second concern is the fact that this project is largely based around unexplored territory, by this I mean that a lot of the information could be quite difficult to find as there is no majorly mainstream form of electric hill climb series. Often we will probably be referring to pre-existing rules from things like formula E and more recognised hill climb rules, however as we are making assumptions there will still be a metaphorical grey area in our findings. This means that we may include feature like ABS and traction control methods that are banned due to the rules and regulations. The solution to this problem is discuss with Pete about the rules and regulations as it is his main area of responsibility and to look at things like patents and papers for information regarding the engineering behind electric vehicles.

On top of this a lot of the information regarding electric vehicles is mainly marketing information catered toward trying to sell these vehicles as economical and performance, this means that most internet based searches return results that are opinions/reviews and numbers and statistics placed to try and attract potential customers, rather that the specific technical information regarding the engineering behind the electric vehicles that I need in order to learn and understand the mechanisms that help this vehicles to perform at their optimum level.

7) Overall Summaries

Group Gantt Chart