## PERT
Earliest Possible Start | Duration | Earliest Possible Finish
Activity
Latest Possible Start | Float | Latest Possible Finish
ES | Duration | EF
Activity
LS | Float | LF
[7 empty] | 6 | 2 | 8
[5 empty] | (a) |  |  | B
[7 empty] | 7 | 1 | 9
[8 empty] | 6 | 2 | 8
C
|  |  | 0 | 6 | 6 |  |  | 6 | 0 | 8
|  |  | A | [7 empty] | 8 | 1 | 9 | 9 | 5 | 14 | 14 | 3 | 17 | 17 | 2 | 19
|  |  | 0 | 0 | 6 | [6 empty] | F |  |  | H |  |  | I |  |  | J
[8 empty] | 6 | 1 | 7 | 6 | 0 | 8 | 9 | 0 | 14 | 14 | 0 | 17 | 17 | 0 | 19
D
[8 empty] | 7 | 1 | 8
[8 empty] | 6 | 2 | 8
[9 empty] | E |  | 8 | 1 | 9
[8 empty] | 11 | 5 | 13 |  | G
[11 empty] | 13 | 5 | 4
[5 empty] | (b) | The critical path is A-C-F-H-I-J
[5 empty] | (c) | 19 weeks
[5 empty] | (d) | next spreadsheet.

## Analysis
|  | Preceding Activities | Most Likely Duration | Staff* Required per week
A | Design Survey |  | 6 | 5
B | Print questionnaire | A | 2 | 1
C | Engage interviewers | A | 2 | 3
D | Prepare interviewer instruction sheets etc | A | 1 | 1
E | Set up computer database | A | 2 | 2
F | Brief interviewers | C & D | 1 | 1
G | Test computer database | E | 1 | 2
H | Supervise fieldwork | B & F | 5 | 4
I | Analyse results | G & H | 3 | 5
J | Prepare report | I | 2 | 5
*not interviewers
(d) (1)
|  | Optimistic | Most Likely Duration | Pessimistic | Expected Time | Variance | Critical Path? | [5 empty] | Expected Time
A | Design Survey | 5 | 6 | 7 | 6 | 0.111 | Y
B | Print questionnaire | 1 | 2 | 3 | 2 | 0.111
C | Engage interviewers | 1 | 2 | 3 | 2 | 0.111 | Y | [5 empty] | Variance
D | Prepare interviewer instruction sheets etc | 1 | 1 | 2 | 1.167 | 0.028
E | Set up computer database | 1 | 2 | 3 | 2 | 0.111
F | Brief interviewers | 1 | 1 | 2 | 1.167 | 0.028 | Y
G | Test computer database | 1 | 1 | 2 | 1.167 | 0.028 | [6 empty] | Project Variance (PV)
H | Supervise fieldwork | 4 | 5 | 6 | 5 | 0.111 | Y | [5 empty] | The sum of the Critical Path Variance(s) | 0.5
I | Analyse results | 2 | 3 | 4 | 3 | 0.111 | Y
J | Prepare report | 1 | 2 | 2 | 1.833 | 0.028 | Y | [5 empty] | Project Standard deviation
|  | 14 | 19 | 24 | 19 | 0.5
|  |  | Project Variance |  |  | 0.5
|  |  | Project Standard Deviation |  |  | 0.70711
(d)(3) | the chances of completing the project in 76 or 78 days
| are not possible as the probability is a negative figure. |  | Complete by week: | Z score | probability of completion | % chance of completion
|  |  | 20 | 0.919 | 1.4142 | 92%
|  |  | 21 | 0.997 | 2.8284 | 99%
|  |  | Z | 0 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09
|  |  | 0 | 0.5 | 0.50399 | 0.50798 | 0.51197 | 0.51595 | 0.51994 | 0.52392 | 0.5279 | 0.53188 | 0.53586
|  |  | 0.1 | 0.53983 | 0.5438 | 0.54776 | 0.55172 | 0.55567 | 0.55962 | 0.56356 | 0.56749 | 0.57142 | 0.57535
|  |  | 0.2 | 0.57926 | 0.58317 | 0.58706 | 0.59095 | 0.59483 | 0.59871 | 0.60257 | 0.60642 | 0.61026 | 0.61409
|  |  | 0.3 | 0.61791 | 0.62172 | 0.62552 | 0.6293 | 0.63307 | 0.63683 | 0.64058 | 0.64431 | 0.64803 | 0.65173
|  |  | 0.4 | 0.65542 | 0.6591 | 0.66276 | 0.6664 | 0.67003 | 0.67364 | 0.67724 | 0.68082 | 0.68439 | 0.68793
|  |  | 0.5 | 0.69146 | 0.69497 | 0.69847 | 0.70194 | 0.7054 | 0.70884 | 0.71226 | 0.71566 | 0.71904 | 0.7224
|  |  | 0.6 | 0.72575 | 0.72907 | 0.73237 | 0.73565 | 0.73891 | 0.74215 | 0.74537 | 0.74857 | 0.75175 | 0.7549
|  |  | 0.7 | 0.75804 | 0.76115 | 0.76424 | 0.7673 | 0.77035 | 0.77337 | 0.77637 | 0.77935 | 0.7823 | 0.78524
|  |  | 0.8 | 0.78814 | 0.79103 | 0.79389 | 0.79673 | 0.79955 | 0.80234 | 0.80511 | 0.80785 | 0.81057 | 0.81327
|  |  | 0.9 | 0.81594 | 0.81859 | 0.82121 | 0.82381 | 0.82639 | 0.82894 | 0.83147 | 0.83398 | 0.83646 | 0.83891
|  |  | 1 | 0.84134 | 0.84375 | 0.84614 | 0.84849 | 0.85083 | 0.85314 | 0.85543 | 0.85769 | 0.85993 | 0.86214
|  |  | 1.1 | 0.86433 | 0.8665 | 0.86864 | 0.87076 | 0.87286 | 0.87493 | 0.87698 | 0.879 | 0.881 | 0.88298
|  |  | 1.2 | 0.88493 | 0.88686 | 0.88877 | 0.89065 | 0.89251 | 0.89435 | 0.89617 | 0.89796 | 0.89973 | 0.90147
|  |  | 1.3 | 0.9032 | 0.9049 | 0.90658 | 0.90824 | 0.90988 | 0.91149 | 0.91309 | 0.91466 | 0.91621 | 0.91774
|  |  | 1.4 | 0.91924 | 0.92073 | 0.9222 | 0.92364 | 0.92507 | 0.92647 | 0.92785 | 0.92922 | 0.93056 | 0.93189
|  |  | 1.5 | 0.93319 | 0.93448 | 0.93574 | 0.93699 | 0.93822 | 0.93943 | 0.94062 | 0.94179 | 0.94295 | 0.94408
|  |  | 1.6 | 0.9452 | 0.9463 | 0.94738 | 0.94845 | 0.9495 | 0.95053 | 0.95154 | 0.95254 | 0.95352 | 0.95449
|  |  | 1.7 | 0.95543 | 0.95637 | 0.95728 | 0.95818 | 0.95907 | 0.95994 | 0.9608 | 0.96164 | 0.96246 | 0.96327
|  |  | 1.8 | 0.96407 | 0.96485 | 0.96562 | 0.96638 | 0.96712 | 0.96784 | 0.96856 | 0.96926 | 0.96995 | 0.97062
|  |  | 1.9 | 0.97128 | 0.97193 | 0.97257 | 0.9732 | 0.97381 | 0.97441 | 0.975 | 0.97558 | 0.97615 | 0.9767
|  |  | 2 | 0.97725 | 0.97778 | 0.97831 | 0.97882 | 0.97932 | 0.97982 | 0.9803 | 0.98077 | 0.98124 | 0.98169
|  |  | 2.1 | 0.98214 | 0.98257 | 0.983 | 0.98341 | 0.98382 | 0.98422 | 0.98461 | 0.985 | 0.98537 | 0.98574
|  |  | 2.2 | 0.9861 | 0.98645 | 0.98679 | 0.98713 | 0.98745 | 0.98778 | 0.98809 | 0.9884 | 0.9887 | 0.98899
|  |  | 2.3 | 0.98928 | 0.98956 | 0.98983 | 0.9901 | 0.99036 | 0.99061 | 0.99086 | 0.99111 | 0.99134 | 0.99158
|  |  | 2.4 | 0.9918 | 0.99202 | 0.99224 | 0.99245 | 0.99266 | 0.99286 | 0.99305 | 0.99324 | 0.99343 | 0.99361
|  |  | 2.5 | 0.99379 | 0.99396 | 0.99413 | 0.9943 | 0.99446 | 0.99461 | 0.99477 | 0.99492 | 0.99506 | 0.9952
|  |  | 2.6 | 0.99534 | 0.99547 | 0.9956 | 0.99573 | 0.99585 | 0.99598 | 0.99609 | 0.99621 | 0.99632 | 0.99643
|  |  | 2.7 | 0.99653 | 0.99664 | 0.99674 | 0.99683 | 0.99693 | 0.99702 | 0.99711 | 0.9972 | 0.99728 | 0.99736
|  |  | 2.8 | 0.99744 | 0.99752 | 0.9976 | 0.99767 | 0.99774 | 0.99781 | 0.99788 | 0.99795 | 0.99801 | 0.99807
|  |  | 2.9 | 0.99813 | 0.99819 | 0.99825 | 0.99831 | 0.99836 | 0.99841 | 0.99846 | 0.99851 | 0.99856 | 0.99861