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Executive Summary
The purpose of this report is to act as the final report of a Feasibility study into providing a Family Art Trail for Davids Music and Arts Festival 2019.  It presents the primary and secondary research material collected in detail and goes on to analyse the data and make recommendations for the planning and implementation of the Family Art Trail. Best practice is researched on-line and observations of a possible route and attractions are made by walking the routes. Primary research is undertaken in the form of interviews with possible stakeholders to identify partners who could deliver the trail and attractions that could be included. Input from families in the community is gathered in the form of questionnaires. There is strong local support for the trail and nine stakeholder venues have expressed a wish to be included this year, with a further two to be added next year and two further possible additions were identified through observations.  A trail with an animal theme was the common factor identified within the primary research to link it all together. A trail route which is accessible has been identified that can be completed either within two hours or over the duration of the ten days that the trail is in operation. The trail has no set route mapped out to allow for people to make their own way. A map can be designed and printed by Pembrokeshire Coast National Parks Authority in-house for the visitor center at Oriel Y Parc and can be distributed from there. Each venue will display an art work of a different animal which is to be drawn on the map by participants using coloured pencils which will be handed out on request. Donations but no fixed price will be suggested at £2. On the reverse side will be spaces for participants to draw the animals into a coastal scene, clues prompt which animal to be searched for in each marked venue. If five or more animals are found and drawn then the works of art can be taken to the visitor center on completion for a sticker and a chance to be entered into a prize drawer for a family boat trip prize using the tear off contact slip which also double up a a feedback form with a likert scale for how much they enjoyed the trail. Feedback can be used for further funding evidence. Works of art may be then kept by the participants or used in an exhibition for next year’s festival. In summary recommendations for the trail are for it to have an animal theme, to run for 10 days to span the festival weekend and one week after.  For it to have no fixed route or time limit so to allow for adventures 
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1.0 Introduction
The report is a feasibility study into a self-guided Family Art Trail as an attraction to run on the weekend of the St Davids Music and Arts Festival. Two years ago a group of local musicians and artists set up the Community Music and Arts Festival in St Davids, Pembrokeshire. St Davids. The birthplace of Wales’ patron Saint has city status even though it has a small population of bellow one and a half thousand inhabitants because of its Cathedral, which stands on the former site of a monastery set up by Saint David. The artists set up a ‘not for profit group’ with aims to support and promote music and arts in St Davids. The festival is run over a weekend one week before the school summer holidays, with the aim of extending the visitor season. Events are held in established venues throughout the city. The festival has had an exhibition of local artists work, street art and workshops over the last two years but now to build on these events the committee have suggested that they would like a family art trail to engage more people with the art offer as they feel it could be better co-ordinated, promoted and their arts events better attended. The art trail could engage more locals and visitors with the Festival as a whole for social and economic benefits to the city. It could boost tourist numbers and It could help to promote local galleries and artist work to generate possible sales therefore having far reaching economic benefits. The social benefits to both visitors and the host city could be widespread as the trail could enhance socio-cutlural exchanges and interaction. These benefits could be educational, morale boosting, linked to better health and well-being by encouraging walking and art related therapeutic benefits.

1.1 Project Aim:
To assess what resources are available for a family art trail in St Davids.
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1.2 Project Objectives and Desired Outcomes if trail implemented
	Project Objectives
	Desired Outcomes

	1. To investigate best practice (secondary research)

	· To engage more locals and visitors with the Festival - socio/cultural benefits
· To promote the Festival to help boost visitor numbers- Economic benefits
· To ensure visitors engage with the Art aspect of The Festival by making it fun and accessible - Socio/Cultural benefits
· To promote local galleries and artist work to generate possible sales – Economic benefits
· To engage more locals and visitors with the Festival - socio/cultural benefits
· To promote the Festival to help boost visitor numbers- Economic benefits
· To ensure visitors engage with the Art aspect of The Festival by making it fun and accessible - Socio/Cultural benefits
· To promote local galleries and artist work to generate possible sales – Economic benefits


	2. To Identify the best partners (primary research)

	· To ensure a wide offer - socio/cultural/economic benefits
· To promote local galleries and artist work to generate possible sales – Economic benefits


	3. To identify the best route and best points of interest (primary research)

	· To ensure visitors engage with the Art aspect of The Festival by making it fun and accessible - Socio/Cultural benefits



Fundamental benefits match the aims of the committee which are to promote local arts, engage the community and help boost the tourism offer.
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2.0 Methodology Proposed Research Strategy
 A Qualitative methodology has been used to collect Primary research consisting of:
Observation by walking around to identify possible routes with my five-year old son who is within the target group age and to find out engaging elements to include
Interviews with potential stakeholders – City Council, Visitor attractions, Galleries, Community Groups - by engaging them with an initial email and organizing an interview style meeting
Questionnaires were implemented. Initially the PID recommended a Community Group Visioning Exercise with a focus group at the local Parent and Toddler Group to find out from residents where they think a route should go and what it should include to engage their kids and themselves and their families. The playgroup leader Jess Evans was contacted but the playgroup had closed early for the Easter Holidays as she was leaving her post, so a focus group session was not possible. A contingency plan to circulate the questionnaires to parents at the school gates was implemented.
The Art lead for the festival committee who has commissioned the project will be interviewed to collect information regarding their ideas for art workshops, galleries, exhibitions, street art and sites and objects of art throughout the city. A weekly meeting/email contact for report updates will to be scheduled into the project plan.
3.1 Sampling
Convenience Sampling was used to identify stakeholders for Interview as identified by the committee (Cameron and Price 2009, p. 228). However as in interviews progressed snowball sampling was implemented (Cameron and Price 2009 p.229). The focus group questionnaires were handed out using Stratified Random Sampling (Cameron and Price 2009, p.231) by speaking to every third parent outside the local St Davids Primary School gates as they waited to line up to pick up their children from school. 
3.2 Pilot
A questionnaire for a focus group session was devised and piloted by running it past three participants.The questions were easy to answer but the boxes were too small was the feedback. The boxes were amended to make them more user friendly.
3.3Quality Controls 
It was recommended in the PID that The Wales Council for Voluntary Associations web-site be consulted for advice by the committee for Quality Management Strategies, see appendices 1.
However in terms of quality controls for the purpose of this report it was agreed with the committee  that in relation to the research and findings of this report that its validity and quality be controlled by ensuring all data collected relates to the aims of the research question and be specific to art trails, the community and its families and the stakeholders within the community that provide art services.
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4.0 Data Collection – Secondary Research – Best Practice Case Studies
As set out in PID project tasks 7.1:
· Identify best practice by researching other successful trails through internet and library resources
List of Case studies researched:
Waiheike Art Trail – New Zealand 
Belper Art Trail
Lichfield Sculpture Trail
Lichfield - Birmingham Art Trail
St Fagans Easter Egg Art Trail
For details refer to Appendice 1
4.1 Best Practice Analysis 
By looking at case studies of other Art and Heritage Trails these successful elements were identified that could be used for developing this trail:
· Involve a wide range of stakeholders in order to engage the community as a whole
· Involve school and Community groups
· Use interactive Experience Elements
· Use a wide range of Art mediums
· Provide workshops
· Provide street Art
· Provide a fun map that engages children which can also be downloaded or an Ap
· Include prizes
· Auction off Art afterwards to raise funds
· Focus on colour and Vibrancy
· Make the trail free or low cost
· Use artist led initiatives
· Use workshops to create the Art
· Choose a strong theme such as animals from a story or a historical story or theme
· Use child friendly themes
· Make it fun and for the whole family
· Make it accessible
· Use sensory elements so it can be appreciated by all
· If there are limited number of maps and prizes advertise this to avoid disappointment as in a first come, first served basis.
· Make riddles and quiz clues easy
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5.0 Data Collection - Primary Research - Stakeholder Interviews
As set out in the PID Project tasks 7.1:
· Generate generic emails announcing project to engage stakeholder participation and interest and request a meeting.
Emails were sent out to engage possible stakeholders to the following organizations which the committee had identified as Possible stakeholders within St Davids all within a possible suitable walking distance:
St Davids Cathedral, Pebbles Yard Gallery and Espresso Bar, Goat Street Gallery, Pembrokeshire National Coast Park Authority - Oriel Y Parc Visitor Center Coordinator and St Davids Care in the Community. Four of these organizations emailed back and agreed to take part in a half to one-hour interviews. One organization did not respond to email in time to be interviewed but has expressed an interest. A further 4 Possible stakeholders were contacted as they again were identified as possible stakeholder venues as part of the initial interviews. These have all since been spoken to during a drop- in visit an all expressed a wish to be involved and have chosen an art work and animal for the trail:
Studio 6 Gallery,Tyddewi Gallery,New Street Gallery, Etcetera Gallery 
A further two organizations were identified in 2 of these interviews as recommended stakeholders:
Ysgol Penrhyn Dewi and Twr Y Felin Art Hotel. These 2 further organizations were contacted by email and a manager from Twr Y Felin was interviewed, the timing for the school was not suitable and they asked to be contacted in September to factor involvement in for next year.
For further detail please refer to Appendices 2 – The Stakeholder Table
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Page 6
5.1 Stakeholder Interview – Content Analysis
For transcripts of interviews please refer to Appendices 3
The popular re -occurring themes were identified in the interview discussions which worked like brainstorming sessions with each interviewee. 
	Stakeholder Interviewee
	Trail name
	Animals Trail theme
	Chosen Animal
	Flexible
Trail with no start or finish and no time constraints - do over a week
	Sculpture
	Art depicting animal
	Art Workshop
	Time of day

	1 
	Go Discover Art Trail
	 yes
	
	In favor
	Not as such but wood carvings
	
	no
	Arter 1.30pm

	2
	Make your own Discoveries
	yes
	Seal or Dolphin on an framed art photo
	In favor
	Pebble sculpture outside 
	
	no
	-

	3
	Go out and get it Discovery trail
	yes
	Raven
	In favor
	no
	1/2 hour pottery throwing display

	no
	-

	4
	The Big Discovery Art Trail
	yes
	 Bison 
	In favor
	Mabinogion – boar Tree trunk with animals
Stone circle – life of St Non
	Current Stones and bones exhibition - museum of wales - animal theme animation suite 
	In kind discovery room hire -  Find tutor for workshop
	afternoon

	5
	-
	yes
	Pig 
	In favor
	yes
	Pig sculpture 
	no
	Anytime as in window

	6

	-
	yes
	Lobster
	In favor
	no
	Painting of Lobster
	no
	Anytime as in window

	7

	-
	yes
	Bee
	In favor
	no
	Painting of bee
	no
	-

	8

	-
	yes
	Dog
	In favor
	no
	Painting of dog
	no
	Anytime as in window


	9

	-
	yes
	Cow
	In favour
	no
	Painting of cow
	no
	-

	10

	-
	-
	-
	-
	Not this year but interested for next year with earlier  planning in Sept term
	-
	no
	-

	11
	-
	-
	-
	-
	Host a sculture in garden next year
	-
	no
	-



5.2 Stakeholder Interviews -Interpretation/Analysis of results
From this data it is clear that there are nine stakeholder venues that could host a trail this year. They all display art depicting animals therefore an animal theme is a viable theme to use for the trail. There is limited sculpture available for use on a trail. Workshop provision is extremely limited therefore not a viable factor to be included on the trail. Afternoons would suit all as some places are not open, although some suggested putting trail pictures in their windows if they were to be closed at times. All were in favor of flexible time limits for the trail. The local School Ysgol Penrhyn Dewi (stakeholder interview no. 10) very much want to be included with earlier planning in future years if meetings could be set up at the beginning of the year in September. Twr Y Felin (stakeholder interview no.11) would like to be included in future years and can provide sculpture in their garden as part of the trail. Visit Wales Year of Discovery is a popular theme to use to name and market the trail -  ‘ The Discovery Art Trail’ fits with the findings as does #yearofdisovery. 
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6.0 Data Collection – Primary Research – Parent Focus Group Questionnaire  
Please refer to Appendices 4 For a copy of the parent focus group Questionnaires 
6.1 Data Analysis – Content Analysis
The re-occurring answers were identified and number of times they came up recorded as the most popular. See Appendices 5 for the Questionnaire Data Analysis Table
Most people said they would partake in the trail with their families, one said if it was child friendly and one said they would give it ago even though they had teenage children. Four people said one hour, two people said two hours, one over a few days, one half a day, one all day and one twenty to thirty minutes. Four people identified two miles, two said one mile, one said one kilometer, one said however long it was and one suggested maybe two route distances for different age groups. Oriel Y Parc had four mentions, The Cathedral Three, Galleries three, The Bishops Palace two and Pottery Two. Other things that came up were: The Wooden Sculpture by the picnic tables at OYP, Misericords carved wooden seats in the Cathedral, The stone sculpture at OYP workshops, the Edge Festival, Yarn Bombing, Bugs, Music on the Cross Square, Craft Fairs, The 39 Steps at the Cathedral, Stained glass windows, the Sea, Cliffs, Natural Beauty, and great breakfast at OYP. Dinosaurs was mentioned twice as too were sports and creative workshops. All the other single mentions were: colouring in, sea-life, prehistoric, the playground, bugs, bongo drums, anything bright and colourful, keys that open the next clue, rhymes, objects to find that forms a finished ‘Art Object’ at the end (like putting together a puzzle), music, play, games, drawing, rubbings, nature related activities, things to touch and feel. Three no comments, Two treasure hunts, Two mentions in involving galleries in planning, One mention of each of these: a map and treasure hunt, ticking things off, secret places, writing and pictures so all ages engaged, looking for things, themed activity, pirates, animals, art, a suggestion to research current interests (trends), a sensory trail, a trail workshop for children to help plan one together with lots of ideas from everyone. Animals got three mentions, flowers three, nature two, sports two, fairies two, sea-life two, fish one, superheroes one, creatures one, sports one, bugs one, drums one, ladybirds one, fossils one, unicorns one, dinosaurs one, a spooky theme one, anything that sparkles one and the Cathedral one. Only one person attempted to draw a map. It was a jug of tall flowers with each gallery named depicted as a flower on a stem 
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7.0Data Collection - Primary Research – Best Route - Observation Walking the possible routes
As set out in PID project tasks 7.1:
· Carry out my own research observations of possible routes and elements on foot with my five year-old to see what art elements there are along the way that would engage him that could be included or excluded and what time span his energy and engagement would span to tie in with other research on possible lenth of the trail.
To summarise the findings of the observation carried out the nine identified gallery venues are all within walking distance of each other within the center of St Davids. There is ample parking which needs to be identified on the trail map. All venues are on accessible routes, where there are steps by the cathedral there is an alternative route for pushchairs or wheelchairs. The route was manageable for a five-year-old child and it was done within two hours. In line with the other research carried out he engaged with looking for animals in the art work at the different venues and in order to engage him more a fun map that he can hold and draw the animals on-to a scene would be of benefit. If there were clues or riddles to solve in order to identify the animal you were looking for this would help. He was engaged by the children’s play-park. 
Nine venues proved too many for him to engage with in one day but it would work over a week so a few could be visited each time. Therefore I recommend that a minimum of five should be completed in order to receive a trail sticker and be entered into the prize drawer for the family boat trip. The sticker would’ve been an incentive for him to complete our walk as he was tired coming back up the hill from the Cathedral. This ties in with other research findings from parent questionnaires regarding time of engagement of young children and prizes and incentives being offered as rewards on completion.
The idea to use a dove on the stained-glass window proved unsuccessful as he failed to see it so small and so high up, therefore the dove on the gold leaf icon is by far a better choice of the art work to use here.  The National Galleries and Museum of Wales have a Gallery space currently (and for the festival)’ Stones and Bones’ Exhibition with an amazing, huge Bison artifact on display and an animation suite which my son loved which also had animals in it tying in the all the other research.
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8.0Route Map
Findings of the observations recommend that there should be no fixed route so families can make their own walking adventures and plan how they tackle it adding to the flexibility of it and fun.  The following is a map which illustrates the venues for the trail that the primary stakeholder interviews and observations identified within the city center and the 
[image: ]

9.0Weekly updates with Committee
Regular up-dates were carried out with Ben Lloyd who is the art lead as to how the research was progressing with reporting back to Mike Chant chair of the committee with two main meetings.
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10.0 Conclusions
In Conclusion there is wide Stakeholder Interest from a cross section of private, public and Voluntary groups to be host venues of the trail. Artist have welcomed the project and been excited about it and there are still more galleries that could be included in following years. The local school Ysgol Penrhyn Dewi, with more time to plan it into their school year, would very much want to be involved. The Cathedral is very keen to be included as too is the local National Park Authority Visitor Center. A sample of local families as a result of the questionnaires have been consulted and their involvement in this will provide valuable input for designing the trail and by already engaging them it will help with promoting the trail.  
Case studies of successful of Art Trails highlight community involvement and cross sector involvement as pivotal to the success of a trail
11.0 Recommendations
It is recommended that the trail should include these elements:
· To have an animal theme 
· For it to run for 10 days to span the festival weekend and one week after
· No fixed route to allow for adventures 
· The map to be handed out at Oriel Y Park Visitor Center (OYP)
· No set route or time limit
· OYP to distribute stickers for completion of trail to each child/family that completes five or more animal drawings
· Include Workshops
· Include Street Art
· Be fun 
· Be accessible to all
· Include sensory elements
· Be free or for a suggested donation of £2
· Be sustainable 
· Be environmentally aware and sustainable
· Build on elements that work each year
· Collect contact details on tear off slip for use in prize drawer for family boat trip around Ramsey and for feedback purposes by including a likert scale to assess the enjoyment level and to be used for evidence for future funding applications
· Involve the local schools next year and Twr Y Felin Art Hotel
· Add two remaining galleries if they are interested next year
· Participants either keep their art or donate it for an exhibition next year
· To call it ‘Discovery Art Trail’ and use #yearofdiscovery to help market it
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13.0 Appendices 
Appendices 1 – Quality Management controls
As identified by WCVA website recommendations for Quality Management Controls are:
An off the shelf system. The benefits of off-the-shelf systems are their national recognition, also many have a lot of prestige attached to them. If funders require you to implement a system, it is likely to be one like the Practical Quality Assurance System for Small Organizations (PQASSO).  
For small to medium sized voluntary and community organizations, or for projects within larger organizations, PQASSO seeks to provide a system for you to assess and improve all aspects of your work. Designed as a work pack, PQASSO has 12 quality areas, including User centered service, Staffing and volunteers, Governance and Networking and Partnerships. It is designed as a self-assessment model but Charities Evaluation Services, which produces the system, are considering whether external assessment should be offered.  

Appendices 2 - Best Practice Case Studies

Waiheke Art Trail
A trail of discovery and experience in Waiheke’s scenery and some of the art it has inspired this small island community. A family friendly 3km walk along the foreshore and through native bush then through a park which showcases several sculptures from past biannual exhibitions. Then to the Artworks Centre with the Waiheke Community Art Gallery which features creative work from around New Zealand and Waiheke. There’s also Whittaker’s Musical Museum with an extraordinary range of antique, working instruments, Waiheke’s Cinema and the new library with interesting architecture to take in. In the village itself is The Artist Goldsmith and Toi Gallery with contemporary art, the amazing Tivoli art shop and more. In summer the whole village becomes an art exhibition when Sculpt Waiheke swings into action with art works in public spaces. At the end of the trail is the beach, where at low tide you can walk around the rocks to a small beach. Or there’s a track around the cliff top with amazing views over the bay. The beach is the perfect place to rest, with free BBQ's, park, and a children’s playground. 
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Belper Arts Trail 
This artist led trail has proved successful in its aims which are:
· For artists to exhibit and promote their work 
· To help strengthen the local artistic community. 
· To find interesting and creative solutions to the lack of dedicated space in Belper for artists to exhibit.
By utilizing every possible space as a venue. Art can now be found in a variety of unusual spaces. Belper and Derbyshire have much artistic talent and the interactive trail of creativity has been successfully growing each year to become a key event in Derbyshire.
Close links to Belper Town Council and Amber Valley Borough Council ensure that the streets of Belper are more vibrant and colorful in the run up to the Trail.


Lichfield City of Sculpture Trail 
 A trail that takes you around Lichfield City to explore all the public art on offer and understand more about their fascinating history. 
A free walking trail leaflet is available from tourist information at Lichfield Library. Or you can follow the trail on-line or download the trail from the App store 'City of Sculpture'. 
About the City of Sculpture Project
An ongoing initiative to develop the visual and new media arts in the city of Lichfield. The project is looking at expandig into the development of new media and digital public art, soundscapes and the creation of opportunities to develop new physical public art. The project will look to develop walking tours of the area, sound tours and more over the coming years.
So far the project has carried out free workshops for over 3000 local people. It has involved local schools, care homes, community groups, libraries, City and District Councils, Museums, Tesco and Art Colleges. It has created exhibitions and installation seen by over 100,000 people. It has involved many high-quality artists and succeeds in encourage people to say ‘YES’ to the arts and to engage with art in its widest sense. 
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Litchfield City Art Trail
This involves people in a trail to search The City’s streets for Hares and Tortoises
The Aesop's Fable about the slow and steady tortoise and the speedy, boastful hare is one of the most familiar and faithful stories around. And now the tale of 'The Hare and the Tortoise' is coming alive in the city of Litchfield in Staffordshire as part of the annual Litchfield Festival which runs from July 7 to 15.
 
Sculptures of around 30 hares and tortoises in various shades and colours have been carefully created and designed and now form part of a City Art Trail.  Visitors to Litchfield during the course of the festival will be encouraged to follow the art trail and find as many of the hidden hares and tortoises they can find. There is also a competition for people to complete a series of clues and claim a prize, At the end of the Festival, people will be able to purchase either a hare or a tortoise when the sculptures are auctioned off in aid of charity. All these beautifully painted and decorated models created by local schools, community groups and businesses will be found new homes.

The Litchfield Festival, which is the city's biggest annual arts event, features a vibrant mix of music, theatre, film, comedy, author talks, family events and visual arts, offering something for everyone. In addition, free exhibitions include imaginative superhero characters dreamed up by local children and community artists, 
St Fagans – Easter Egg Art Trail
St Fagans held four days of an art related Easter Hunt during the Easter holidays. It ran between 10am to 3pm and cost £3.50 entry and booking was not required. It was advertised as having limited availability and was run on a first come, first served basis. After purchasing the trail map from the Atrium the aim was to solve the riddles and follow the trail around the site, then head back to the start to claim your chocolate bunny lolly-pop prize. It was advertised as suitable for children age 4+ years
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Appendices 3 - Stakeholder Table
As set out in the PID Project tasks 7.1:
· Produce Stakeholder Table
	
	Organization
	Contact name
	Role
	Interviewed
	Agreed to be Venue
	Email Address

	1
	St Davids Cathedral
	Janet Ingram
	Education Officer 
	yes
	ye Page 16 s
	education@sdavidscathedral.org.uk

	2
	Pebbles Yard Gallery and Espresso Bar
	Jacki Sime
	Photography Artist Owner
	yes
	yes
	info@jackisime.co.uk

	3
	Goat Street Gallery
	Dan and Amanda Wright
	Artist Owners 
	yes 
	yes
	goatstreetgallery@gmail.com

	4
	Oriel Y Parc,
Pembrokeshire Coast  National Parks 
	Katie Murphy
	Center Coordinator
	yes 
	yes
	katiem@pembrokeshire.org.uk

	5
	St Davids Care in the Community – Pilgrims 
	Elly Morgan
	Arts Workshop Tutor
	no
	yes
	gerellybye@yahoo.com

	6

	Studio 6 Gallery
	Rose Perium
	Artist Owner
	Not interviewed. Introduced project and their interest was recorded
	They would like to be avenue
	No email contact only verbal at this stage

	7

	Tyddewi Gallery
	Pauline Beynon
	Artist Owner
	Not interviewed. Introduced project and their interest was recorded
	They would like to be a venue

	No email contact only verbal at this stage


	8
	New Street Gallery





	Grahame Hurd Wood
	Artist Owner
	Not interviewed. Introduced project and their interest was recorded
	They would like to be a venue

	No email contact only verbal at this stage



	
9








	Etcetera Gallery
	Jane Sqire 
	Owner
	Not interviewed Not interviewed. Introduced project and their interest was recorded


	They would like to be a venue
	No email contact only verbal at this stage



	10
	Ysgol Penrhyn Dewi
	Karen Morris
	Head of Art
	No as time frame proved impossible with exams coming up 
	Not this year but maybe in future years

	morrisk167@hwbmail.net




	11
	Twr Y Felin Hotel

	Emma Bowen
	Marketing Manager
	yes
	Not this year but maybe in future years
	marketing@retreatsgroup.com 
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Appendice 4 - Stakeholder Interview Transcripts
1.Stakeholder Interviewee 1: Janet Ingram/St Davids Cathedral Education Officer
Possible name: “Go Discover Art Trail”
Possible themes
St Davids Icon is a must
Have done Animal Safari themed activities with Primary School Children. Where they look for carvings of a dove, mouse, owl, raven, fish, bees, greyhound
Kids like to gather things
Gargoyle of Bishop Wynne
Devil’s Footprints story
Bell Tower Custom 
Cannon’s Horse grave
Start Cathedral end at OYP. But this is not set in concrete
Must confirm dates asap as diary fills up quick/already limited access on July 13th as wedding 12.30-1.30
Concern over kids being in school during week
Suggesting that we run it only during afternoons from 2pm 
Possible activities
· Make a stained-glass window by tracing a tile in Cathedral on tracing paper. Place laminet over it at OYP and colour in with sharpies
· Rubbing stonework or carvings in Cathedral with local beeswax. Painting over water colours at OYP to discover an image
· Rub stamps made of wood at each venue and collect them as you go round like in a passport.
· Rub stamps made in clay at each venue annd collect as you go in a passport
· Use stamps to make badges, especially good for blind as sensory
· Take photos of things and upload on National Parks Portal?
· Take your passport to OYP to collect your prize/badge
· Dig in sandpit for treasure or fossils like archaology unearth your prize/badge on completion of trail
They did a St Davids day themed “Find the little things” trail all be it last minute in shop/venue windows and only 5 people completed it, so poor uptake
Could every Art Gallery be invited to exhibit in Ebeniezer then those not on trail may feel included as we cannot feature every Gallery on trail (or can we?)
Possible case studies : Annwick Castle, Pilgrim Project Glouscester, Hereford
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2. Stakeholder Interview 2: Jacki Sime Pebbles Yard Gallery and Espresso Bar
Possible Name: “Make your own Discoveries”
Possible themes
Kids like to leave things behind as well as gather - An option for gathering and leaving:shells, pebbles, sticks, flowers – Maybe a communal sculpture evolves, or painted pebble garden
Link to her book: “St Davids Peninsula: A Journey in Time”
Avoid using “Art Trail” sounds boring for kids
Pirate Theme – pirates in her book
Indigenous Animals/Birds – especially Dolphins and Seals
Each venue could have an animal theme to collect as ceramic stamp or just view or take own photograph
Promote Plastic Awareness as she is involved in a big project with this and she would definitely be involved with this theme

Possible points of interest
Pebble stack sculpture made by husband Graham
Footprint plaque in ceramic from 20 or so years ago outside by tree that kids did as part of Eco City activities relating to wind-turbines
Gallery with her Photography
Café , kids and dogs welcome, outside seating
Giftshop with Her Books, jewellery craft items
She could have a Dolphin or Seal Image as her theme displayed on wall as Framed Art Photograph
Allow for thinking out the box, collect things they identify with or see on the way. Allow for free expression
Possible Activities
· Pirate Treasure map, X marks spot for treasure reward on completion of trail, dig in sandpit on completion for treasure/badge etc
· Likes idea of someone making a ceramic image to rub as ec- friendly defo no plastic, doesn’t like stained glass idea as involves plastic use
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3. Stakeholder Interviewee 3: Dan and Amanda Wright - Goat Street Gallery
Possible name: “Go out and get it Discovery Trail “
Possible themes
Music
Images of music
Bee theme – Oriel Y Felin – see Sarah Beynon and her Mum’s gallery
Animals, Rook


Possible points of Art Interest
Galleries


Possible activities
A drawing from each place
Afternoons only as no-one comes in morning
Dan could do a throwing demonstration for ½ hour at set time each day
Ceramic workshop
Chalk on pebbles at beach
Badge making – empty badges to fill (metal – make a sticker to go on)
Carve in plaster to make a stamp
Rubbings
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Suggestions
List all galleries in St Davids on map on back
Find out who is in Refrectory at that time exhibiting
Twr Y Felin – email Keith Griffiths
Contact Ysgol Penrhyn Dewi for involvement
CADW – Bishops Palace
Put a competitive element in like a photo competition of animals or a Fun run around Cathedral or steps, contact Man Up UK
Art Installations on trail
Involve Lifeboat station and Bug farm
Not too much writing
Keep it flexible
 Accessible and for 0- 12 year olds
All galleries listed but not all a venue
Build on it next year and roll out 1st week every month April, May, June and July
Possible case studies: 
Lichfield and Birmingham Art trails
4. Stakeholder Interviewee 4: Katie Morgan – OYP Visitor Centre Coordinator- PCNP
Possible name: “The Big Discovery Art Trail”
Possible themes
Pirate map. Keep trail as open as possible and flowing. No fixed route, no time scale – can do over several days. 
Adder – strong link as used for art before lantern sculpture and project with school
Prehistoric Indigenous Animals, Palaeolithic – link to Stones and Bones Exhibition from the National History Museum 23rd may through to July which has elements of art. Archaeology, Animation suit coming as part of exhibition, can choose an animal when know what is coming at a later date. Possible – Sabre tooth tiger (bone artefact that was found locally). Allrock cow skeleton found on Whitesands beach, Rhino horn from rhino mammoth. Non-plastic theme.
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Future ideas include a possible Waldo Williams theme. As a collaboration as W W Trust is coming in Sept to OYP and want to devise a city trail to run year-round.
A Trail is something OYP really want to be working towards
Possible points of Art Interest
Animal Sculpture tree trunk by picnic tables – need to find out artists name
Stone Circle in woods – St Non’s life _ artists name?
Twrch – boar sculpture – Mabinogion – artists name?
Local Galleries
Cathedral
Bishops Palace – architectural
Possible activities
Afternoons only as no-one comes in morning
Discovery room is free for festival weekend for workshops – week in lead up?
Happy for trail to run for fortnight from 12th July
Exhibition in Tower – 30th june – july. 
For the end of trail to be at OYP and a dig in a sandpit for your prize like an archaeological dig for a treasure coin? Volunteers Friends of OYP to manage this possibly? Prize could be tooth – sabre tooth tiger, bones, coin, shell, something made in kids workshops to unearth.
Suggestions
List all galleries in St Davids on map on back
Find out who is in City Hall at that time exhibiting
Contact Creative cafe
Look for a business sponsor – Twr Y Felin, email paula.ellis@retreatsgroup.com. Art open day 17th may at hotel. Wales’ premier Art Hotel
Contact Ysgol Penrhyn Dewi for involvement
Possible case studies: 
None identified but agreed The St Fagans one was good to work from
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4.Stakeholder Interview 5 – Twr Y Felin Art Hotel – Emma Bowen – Marketing Manager
The hotel is marketed as Wales’ Premier Art Hotel
They are not able to give sponsorship but will support if they have something in return. The hotel hosts paintings depicting local scenes and other art works by renowned artists. It is a retreat hotel not a family hotel as such. They are open to being involved in the project if it promotes them and especially if it is sustainable, has legacy and can extend the tourist season by being placed outside the seasonal holiday period to bring in revenue and guests.
A good link has been made to build from for next year.
The best idea discussed would be for their garden to host a sculpture as part of the trail. They are having an extension and ground-works so the garden is currently unavailable. Adam Buik local potter has had Monoliths on display there and they plan to return them after their ground works so these could be on the trail possibly
They have a live Wildlife Cam that guests can watch
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Appendices 5 - Data Collection - Primary Research – Parent Focus Group Questionaires
As set out in PID project tasks 7.1:
· Email Playgroup leader to announce project and request focus group exercise
· Put up poster on playgroup face book page to announce focus session 
· Devise Focus group exercises for collecting data (Morgan 1997)
	1

	Would your family participate on a Family Art Trail?



	2
	How long would you spend on a trail?



	3
	How far would you walk?



	4
	Name any interesting art related elements that are in St Davids that have engaged or interested your kids




	5
	Name any elements that we could provide that might engage or interest your kids. Art or non-art related?




	6
	List or comment any other ideas you may have that you think would benefit the planning of such a trail





	7
	What themes interest your kids that we could link a trail too?



	8
	If you would like to please feel free to draw a map or picture of an art trail in St Davids that you would like to see, you may use the back of this form
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Appendices 6 - Questionnaire Data Analysis Table
The re-occurring answers were identified and number of times they came up recorded as the most popular.
	Question no
	Highest number  said yes
	Highest number said 1  hour
	Highest number said 2 miles
	Most Frequetly mentioned and number of mentions
	How many drew a map and what was drawn

	1
	8
	
	
	
	

	2
	
	4
	
	
	

	3
	
	
	4
	
	

	4
	
	
	
	Oriel Y Parc - 4

Cathedral - 3
Galleries - 3
Bishops Palace - 2
Pottery - 2

	

	5
	
	
	
	Dinasours- 2
Sports - 2
Creative workshops - 2

	

	6
	
	
	
	No comment- 3
Treasure hunt -2
Clues -2
Gallery involvement - 2

	

	7
	
	
	
	Animals - 3
Sealife -2
Flowers -2
Nature - 2
Fairies - 2
	

	8
	
	
	
	
	1 person drew a jug of flowers as the map
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Appendices 7 – Observations transcript – walking the possible route
The nine identified gallery venues are all within walking distance of each other within the center of St Davids. There is ample parking which needs to be identified on the trail map. All venues are on accessible routes, where there are steps by the cathedral there is an alternative route for pushchairs or wheelchairs. The route was manageable for a five year-old child and it was done within two hours. There was plenty of things to look at on the way and there will be much more in the way of street art when the festival is on.  My five year old enjoyed looking for animals in the art work at the different venues and in order to engage him more a fun map that he can hold and draw the animals on-to a scene would be of benefit. If there were clues or riddles to solve in order to identify the animal you were looking for this would help. He was engaged by the children’s play park which is on New Street opposite the supermarket, the bus-stop next to this and post box along the way as too was he by the ice cream parlor on High Street. Nine venues proved too many for him to engage with in one day but it would work over a week so a few could be visited each time. Therefore I recommend that a minimum of five should be completed in order to receive a trail sticker and be entered into the prize drawer for the family boat trip. The sticker would’ve been an incentive for him to complete our walk as he was tired coming back up the hill from the Cathedral. The area by the cathedral would make a perfect picnic spot by the river to rest before the climb back uphill. This ties in with other research findings from parent questionaires regarding time of engagement of young children and prizes and incentives being offered as rewards on completion. Next to this is Cadw’s Bishop’s Palace which is a great space for children and families to explore its grounds and dungeons as it is very much like a ruined castle with a big open grass area and benches to relax. There is also parking by the Cathedral so you can avoid the hill if needs be. There are many cafes and restaurant too for lunch or dinner including one at the Cathedral and The Visitor Center. The Refectory has art exhibitions so in future trails this could be factored in as does the City Hall and sometimes the Cathedral as there was an Art on The Faith Trail exhibition on in The Cathedral which runs through till 31st July (see link below to web-site). The idea to use a dove on the stained glass window proved unsuccessful as he failed to see it so small and so high up, therefore the dove on the gold leaf icon is by far a better choice of the art work to use here. The icon’s being painted by local artist Sarah Crisp. We walked past wo more Galleries which could be added in future The Albion Gallery and the John Rogers’ Gallery. At the Cross square he enjoyed climbing the steps and sitting and listening to a charity choir who happened to be there. During the festival there will be a market here with local produce and buskers to entertain. The incentive for families to take their children back to the visitor center to claim their sticker would be helped by a tea off slip at the bottom of the map for contact details to be entered into a prize drawer. A prize of a family boat trip around the local Ramsey Island was offered as a prize from one of the many boat trip vendors that line the streets namely Voyages os Discovery which would tie with the Discovery Theme for the Trail and Visit Wales’ Year of Discovery this year. The tear of slip could also act as a way of gathering feedback If it had a Likeart scale on it to assess the enjoyment level by participants, this in turn could help with funding. The picnic area at the visitor center with its carved wooden tree stump sculpture of native animals engaged my five year-old as did the stone circle sculpture which kids can climb on that depicts the life of St Non in the wooded area. The outdoor area is perfect for outdoor arts workshops, they have a Discovery Room for Indoor workshops, a tower with local art exhibitions (currently the school) which can all be used for the festival. The National Galleries and Museum of Wales have a Gallery space currently (and for the festival)’ Stones and Bones’ Exhibition with an amazing, huge Bison artifact on display and an animation suite which my son loved.
 http://www.art-on-the-faith-trail.co.uk/ accessed on 25.06.19
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