|  | Negligible | Minor | Moderate | Major | Catastrophic |
| --- | --- | --- | --- | --- | --- |
| Rare |  |  |  |  |  |
| Unlikely |  |  |  | 4 | 6 |
| Possible | 3 |  | 10 | 5, and 8 |  |
| Likely |  | 9 | 7 |  | 1 |
| Certain |  |  | 2 |  |  |

Risk scores in order

- Software integration failure: Likelihood = 4, Impact = 5

Risk score= 20

- Delay in component delivery: Likelihood = 5, Impact = 3

Risk score= 15

- Network communication failure: Likelihood = 4, Impact = 3

Risk score= 12

- Overheating of control cabinet: Likelihood = 3, Impact = 4

Risk score= 12

- Power supply instability during testing: Likelihood = 3, Impact = 4

Risk score= 12

- Failure of safety interlock system: Likelihood = 2, Impact = 5

Risk score= 10

- Mechanical alignment error: Likelihood = 3, Impact = 3

Risk score= 9

- Sensor calibration issue: Likelihood = 2, Impact = 4

Risk score= 8

- Operator training delay: Likelihood = 4, Impact = 2

Risk score= 8

- Minor documentation error: Likelihood = 3, Impact = 1

Risk score= 3

High priority:

1,2,3,4, and 5

Medium priority:

6,7,8, and 9

Low priority:

10

Risk exposure

Risk exposure (RE) before mitigation = (potential damage) x (probability of occurrence)

RE= 150,000 x 0.02 = 3000

Risk exposure (RE) after mitigation = (potential damage) x (probability of occurrence)

RE= 150,000 x 0.005 = 750

Risk Reduction Leverage (RRL)

RRL= (RE_before - RE_after)/ (Cost of risk reduction)

RRL > 1.0 = Worth implementing

RRL < 1.0 = Not cost-effective, Not worth it

RRL= (3000 – 750)/1500 = 1.5

PERT (Program Evaluation and Review Technique)

Most likely time (m) = 12 days

Optimistic time (a) = 20 days

Pessimistic time (b) = 8 days

Expected time t_e=((a+4m+b))/6 = ((20+4(12)+8))/6

= 12.67 days

Standard deviation S=((b-a))/6 = ((8-20))/6

= -2 days

Z value = ((T-t_e))/S = ((15-12.67))/-2 = -1.165

A higher positive z means tells the project manager that there is a lower probability of not meeting the target date.

A z of 0 tells the project manager that there is about a 50% chance of meeting or not meeting the target date.

A negative z tells the project manager that there is a higher probability of not meeting the target date.

Software integration failure: Do early software testing

Delay in component delivery: Have backup supplies and alternative suppliers prepared