## Sheet1
JCT24
Job | Twelve Flats at SA1
Job No. | 1234
Valuation Date: | 2025-01-30
Certificate No. | 6
Due Date:
Final Date for Payment:
Work Properly Executed
|  |  | Value of work | Value of work included
BoQ No. |  |  | £ | £
Bill 1 Preliminaries | As Schedule
| Set Up |  | 73350
| Weeks | 25
| Per Week | 4050
Bill 2 Substructure | Complete |  | 327600
Less (agreed)
| BoQ page 32/G | 30000
| BoQ page 32/H | 12000
Bill 3 Concrete Work | BoQ page 35 | 90970
| BoQ page 36 | 75447
| BoQ page 37 | 73806
| BoQ page 38 | 23138.36
| BoQ page 39 | 6618
| BoQ page 40 | 25926
| BoQ page 41/A-K | 1980
| BoQ page 42/F | 432
| BoQ page 42/G | 72
| BoQ page 45/M | 1638
Bill 4 Masonary | BoQ page 47/A-D
Variations
|  |  | £ | £
Instruction No. | Omission or Addition?
AI 3 Swimming Pool | Addition |  | 98338
| Less to complete | 18000
AI 5 Drainage Remeasure | Addition
| Excavation | 7422
| Surronds/beds | 17994
| Pipework | 5058
| Chambers say…. | 13200
Provisional Sums
|  |  | £ | £
Provisional Sums Items. | Amount inc. in Tender | Amount Expended
|  | Cost of Provisional Sums: |  | 0
Site Materials
| Invoices for: | £ | £ | £
| Bricks | 8538
| Blocks | 1650
| Sand | 618
| Cement | 1362
| Aggregates | 2940
| Chamber Covers | 3000
| Timber | 4200
| Pipes | 1200
| Roof Tiles | 6000
Fluctuations Provision - clause 14.14.1
|  |  | £ | £
| See Separate List |  | 1454
Gross Valuation
Retention % |  | 3
Net Valuation
Less Previous
Valuation No. 6
Ammount Due for Payment:
Amount in Words:
#NAME?
Note: VAT Exclusive