## Lists (hidden)
Cyber & Technology | People & Behaviour | Operational | Physical & Environmental | Financial | Strategic
Cyber Security | Human Error | Process Failure | Physical Security | Financial Fraud | Strategic
Data Privacy | Insider Threat | Supply Chain | Natural Disaster | Budget Overrun | Political / Regulatory
System Failure | Social Engineering | Business Continuity | Environmental | Economic | Third Party / Vendor
Software/Hardware | Reputational | Compliance / Legal | Health & Safety

## Risk Register
Risk Management Register
Scenario: ___________________________ Group: ___________________________
Risk ID | Hazard / Risk Description | Who is at Risk | Category | Sub Category | Likelihood (1–5) | Severity (1–5) | Risk Score (L × S) | Risk Level | Existing Controls | Additional Controls Needed | Responsible Person | Target Date | Residual Likelihood (1–5) | Residual Severity (1–5) | Residual Risk Score | Residual Risk Level | Status
R01 | Someone without permission could access private student or staff information. | Students, teachers and admin staff | Cyber & Technology | Data Privacy | 4 | 5 | 20 | Critical | Staff use passwords, and access is limited based on their roles. | Add two-factor authentication and regularly review user access. | IT Administrator | 2026-11-06 | 2 | 5 | 10 | High | Active
R02 | The system could stop working, making it difficult to check timetables or record attendance. | Teachers, students and admin staff | Cyber & Technology | System Failure | 3 | 4 | 12 | High | Regular maintenance is carried out to keep the system working. | Add two-factor authentication and regularly review user access. | IT Manager | 2026-11-13 | 2 | 4 | 8 | Medium | Active
R03 | Teachers could accidentally enter incorrect attendance information. | Students and teachers | Operational | Process Failure | 4 | 3 | 12 | High | Teachers receive guidance on how to record attendance correctly. | Add automatic checks to identify mistakes in attendance records. | Attendance Officer | 0/11/2026 | 2 | 3 | 6 | Medium | Active
RISK LEVEL LEGEND
Critical (15–25) |  |  |  | Immediate action — stop or redesign activity
High (10–14) |  |  |  | Urgent controls needed — inform senior management
Medium (5–9) |  |  |  | Monitor closely — additional controls required
Low (1–4) |  |  |  | Acceptable — review periodically

## Risk Heatmap
RISK SCORE HEATMAP - Likelihood × Severity
Use this matrix to identify the risk level for any combination of Likelihood and Severity.
SEVERITY →
← LIKELIHOOD |  | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic
| 5 – Almost Certain | 5 Medium | 10 High | 15 Critical | 20 Critical | 25 Critical
| 4 – Likely | 4 Low | 8 Medium | 12 High | 16 Critical | 20 Critical
| 3 – Possible | 3 Low | 6 Medium | 9 Medium | 12 High | 15 Critical
| 2 – Unlikely | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 High
| 1 – Rare | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium

## Action Tracker
RISK CONTROL ACTION TRACKER
Risk ID | Risk Description | Action Required | Priority | Responsible Person | Start Date | Target Date | Completion Date | Evidence / Notes | Status

## Guidance Notes
HOW TO USE THIS RISK MANAGEMENT WORKBOOK
SHEETS OVERVIEW
| Risk Register | Complete one row per identified hazard. Risk Score and Risk Level are auto-calculated.
| Risk Heatmap | 5×5 colour-coded matrix showing how Likelihood and Severity combine into a risk level.
| Action Tracker | Log all control actions, assign responsibility, and track completion.
| Guidance Notes | This page — definitions and instructions.
LIKELIHOOD SCALE
| 1 – Rare | Could happen but probably never will (once every 5+ years)
| 2 – Unlikely | Not expected but possible (once every 2–5 years)
| 3 – Possible | Could occur at some time (once per year)
| 4 – Likely | Will probably occur in most circumstances (monthly)
| 5 – Almost Certain | Expected to occur in most circumstances (weekly/daily)
SEVERITY SCALE
| 1 – Negligible | No impact; minor inconvenience
| 2 – Minor | Small impact; easily recoverable
| 3 – Moderate | Noticeable impact; some recovery effort needed
| 4 – Major | Significant impact; difficult to recover from
| 5 – Catastrophic | Severe or irreversible impact
RISK LEVEL GUIDE
| Low (1–4) | Monitor and review periodically; standard controls sufficient
| Medium (5–9) | Manage through routine procedures; monitor more frequently
| High (10–14) | Urgent action required; inform responsible person immediately
| Critical (15–25) | Stop or redesign activity until risk is reduced to acceptable level
RISK CATEGORIES
| Cyber & Technology | Cyber Security, Data Privacy, System Failure, Software/Hardware
| People & Behaviour | Human Error, Insider Threat, Social Engineering, Reputational
| Operational | Process Failure, Supply Chain, Business Continuity, Compliance / Legal
| Physical & Environmental | Physical Security, Natural Disaster, Environmental, Health & Safety
| Financial | Financial Fraud, Budget Overrun, Economic
| Strategic | Strategic, Political / Regulatory, Third Party / Vendor
TIPS FOR STUDENTS
| Research first | Identify risks through research before filling in the register
| Be specific | Describe the hazard clearly — avoid vague terms like 'something goes wrong'
| Think about controls | Consider both existing controls and what additional ones are needed
| Residual risk | After controls are applied, re-score Likelihood and Severity to get residual risk
| Hierarchy of controls | Eliminate > Substitute > Engineering > Administrative > PPE