## Summary
INITIAL FEASIBILITY
Element of Work | Lower specification | Higher specification | Percentage of Total cost | Time Factor | Location Factor | TOTAL with indices applied
PRELIMINARIES | 880342 | 880342 | 2.058% | 1.19 | 0.86 | 900942.0028
ENABLING WORKS | 164620.81 | 164620.81 | 0.3848% | 1.19 | 0.86 | 168472.937
EXCAVATE AND FILL | 5352764.4669 | 5352764.4669 | 12.51% | 1.19 | 0.86 | 5478019.1554
SUBSTRUCTURE | 2866919.61 | 5399377.7788 | 12.62% | 1.19 | 0.86 | 5525723.2188
DRAINAGE | 204130.56 | 228130.56 | 0.5333% | 1.19 | 0.86 | 233468.8151
CAR PARKING | 6300000 | 10120000 | 23.66% | 1.19 | 0.86 | 10356808
GENERAL SUPERSTRUCTURES AND FACILITIES | 10735119.2572 | 14464812.746 | 33.81% | 1.19 | 0.86 | 14803289.3643
SPORTS PITCH | 385887.5 | 509320 | 1.191% | 1.19 | 0.86 | 521238.088
GENERAL GARDEN LANDSCAPED AREA | 68690 | 80245 | 0.1876% | 1.19 | 0.86 | 82122.733
OVERHEADS | 4043771.1306 | 5579942.0042 | 13.04% | 1.19 | 0.86 | 5710512.6471
| 31002245.3348 | 42779555.3659 | 100% |  |  | 43780596.9615

## Allowances & Assumptions (hidden)
Further Allowances, Assumptions & Information Used |  | Notable exerpts from Groundworks tender pack
1 | In exerpt 4, we have a referral to 'SKETCH SK005 ENABLING WORK', mentioning cut and turn specification | 1 | MIN 200 THK RC SLAB WITH 2 | REVOLVING DOOR ASSUME DIMS
| Also with exerpt 2, we are not in receipt of 'DWG 101' for 'GROUND IMPROVEMENT' |  | LAYERS A393 MESH, FOR
| Based on this limited information, we assumed an excavation of 2 metres and filled with import stone. |  | REVOLVING DOOR, REFER TO
| We have use the drawing 'Library Building Sub-structure Sections' to inform this assumption. |  | ARCHITECT'S DRAWING FOR
SETTING-OUT.
2 | The drawing 'LibrarY Building Ground Floor Layout' gives a number of specifications we have used:
| - "150 THK RC GROUND BEARING SLAB WITH 1 LAYER OF A393 MESH ON 2000g DPM | 2 | 150 THK RC GROUND BEARING SLAB
| ON 150 THK WELL COMPACTED STONEDUST BLINDED TYPE 1 MATERIAL, FOR DETAILS OF |  | WITH 1 LAYER OF A393 MESH ON 2000g DPM
| GROUND IMPROVEMENT BELOW SLAB REFER TO SECTION 1-1 & 2-2 ON DWG 101." |  | ON 150 THK WELL COMPACTED STONEDUST
BLINDED TYPE 1 MATERIAL, FOR DETAILS OF
3 | We have assumed the dimensions of revolving door to ensure we have allowed as per the following specification: |  | GROUND IMPROVEMENT BELOW SLAB REFER
| - "MIN 200 THK RC SLAB WITH 2 FOR REVOLVING DOOR, LAYERS A393 MESH, |  | TO SECTION 1-1 & 2-2 ON DWG 101.
REFER TO ARCHITECT'S DRAWING FOR SETTING-OUT"
|  | 3 | 1500 X 900 X 900 DEEP PIT WITH 200 THK RC | 1500 | x | 1450
4 | We have two 'DEEP PIT' items specified in the 'Library Building Ground Floor Layout'. |  | BASE SLAB AND 200THK RC WALLS WITH 1
| We have included these items within our 'Bill No. 11 - In-situ concrete works' section |  | LAYER OF A393 MESH TO ALL FACES TOP &
BOTTOM. TOP EDGE TO HAVE 100x100
5 | We have various reinforced concrete shear walls specified in the 'Library Building Ground Floor Layout' |  | GALVANISED ANGLE WITH
| We have included these items within our 'Bill No. 11 - In-situ concrete works' section |  | FISH TAIL TANGS ALL ROUND TO TO SUPPORT
CHECKER PLATE.
6 | We included a powerfloated finished slab, with the 'RC UPSTAND' and 600mm facing brickwork
| as we do not have the 'FINISHES TO ARCHITECT'S DETAILS'. We are happy to include for additional | 4 | REFER TO SKETCH SK005
| floor finishes if further specification is available. |  | 'ENABLING WORKS' FOR
CUT AND TURN
7 | We have not been provided with a ring beam detail in full. We have assumed an allowance |  | SPECIFICATION.
of reinforced steel within the pile ringbeam.

## Document Register
Document Register / Drawings Used
| Drawing / Document description | No | Revision | Project Ref

## Initial Feasability
|  |  |  | QUANTITY | UNIT | RATE (LOWER SPEC) | RATE (HIGHER SPEC) | VALUE (LOWER SPEC) | VALUE (HIGHER SPEC)
| ENABLING WORKS | [6 empty] | 164620.81 | 164620.81
Knotweed treatment
Japanese Knotweed Management Plan; PBA Solutions Ltd Formulate
Japanese Knotweed Management Plan (KMP) as recommended by the
| Environment Agency Code of Practice 2006 (EA CoP) |  |  | 1 | nr | 1359.61 | 1359.61 | 1359.61 | 1359.61
Treatment of Japanese Knotweed; PBA Solutions Ltd; removal and/or
treatment in accordance with The Knotweed Code of Practice
Commercial chemical treatments based on areas greater than 900m2 knotweed area; allows for the
provision of contractual arrangements including method statements and spraying records;
also allows for the provision of risk, environment and COSHH
assessments; rates for 3–5 year programme,
incl. management plan and post-treatment monitoring
|  | rate per visit |  | 16000 | m2 | 0.89 | 0.89 | 14240 | 14240
OR
|  | Rate per year (3-5 year) |  | 16000 | m2 | 8.11 | 8.11 | 129760 | 129760
Removal off site to a licensed landfill site using 20 tonne
gross vehicle weight lorries; price is for haulage and tipping only;
the mileage stated below is the distance from point of collection to
licensed landfill site; price excludes landfill tax and loading of material into lorries; rates
will fluctuate between landfill operators and the figures
given are for initial guidance only
|  | 20-40 miles | (Provisional) | 20 | loads | 963.06 | 963.06 | 19261.2 | 19261.2
| EXCAVATE AND FILL | [6 empty] | 5352764.4669 | 5352764.4669
GENERAL EXCAVATION
Excavate material other than topsoil, rock or artificial hard
material
| 2.0-5.0 deep |  |  | 30053.1383 |  | 11.69 | 11.69 | 351321.187 | 351321.187
EXCAVATION ANCILLARIES
Disposal of excavated earth other than rock or artificial hard material
| storage on site; 100m maximum distance; using 22.5 t ADT |  |  | 30053.1383 |  | 5.89 | 5.89 | 177012.9847 | 177012.9847
Add to the above rates where tipping charges apply:
| hazardous waste |  |  | 30053.1383 |  | 160.53 | 160.53 | 4824430.2952 | 4824430.2952
NOTE: NO ALLOWANCE FOR CONTAMINATED
LAND REMEDIATION TAX RELIEF
| SUBSTRUCTURE | [6 empty] | 2866919.61 | 5399377.7788
| Building Cost Model Used: Concert Hall |  |  | Model location is Inner London Model TPI = 131; LF = 1.06
Substructure
Piled foundations; RC ground bearing slab; lift pits
| & sumps. Partial basement 1,000 m² assumed |  |  | 11019.1383 | m2 | 490 | 490 |  | 5399377.7788
secant piled with RC lining walls and cavity drain
OR
Approximate Estimating Rates
Unless otherwise described units denoted as m² refer to appropriate unit areas (rather than gross internal floor areas).
1.1.2 Specialist Foundations
Piling
Enabling works
excavate to form piling mat; supply and lay imported hardcore – recycled
| brick and similar to form piling mat |  |  | 5509.5692 | m3 | 11.3 | 13.7 | 62258.1315
provision of plant (1 nr rig); including bringing to and removing from site;
| maintenance, erection and dismantling at each pile position |  |  | 1 | item | 19000 | 23000 | 19000
Supply and install concrete Continuous Flight Auger (CFA) piles; cart away
inactive spoil; measure total length of pile
| 750mm dia. reinforced concrete CFA piles |  |  | 936.6268 | m | 130 | 155 | 121761.4785
Pile testing
| using tension piles as reaction; typical loading test 1000 kN to 2000 kN |  |  |  | item | 7900 | 9500
| integrity testing; minimum 20 per visit |  |  | 190 | nr | 16 | 19.3 | 3040
Secant wall piling, 750mm dia. piles including site mobilization and
demobilization; Measure total area of piling (total length × total depth)
| supply and install secant wall piling |  |  | 5710 | m2 | 270 | 325 | 1541700
Steel sheet piling; Measure total area of piling (total length × total depth)
interlocking steel sheet piling to excavation perimeter; Corus LX or similar;
| extraction on completion |  |  | 3426 | m2 | 200 | 240 | 685200
Reinforced concrete basement walls;
NOTE: excluding bulk excavation costs and hardcore fill
| 200mm thick waterproof reinforced concrete |  |  | 1142 | m2 | 380 | 460 | 433960
| DRAINAGE | [6 empty] | 204130.56 | 228130.56
Soakaways: Stormwater Management
Soakaway crates; heavyweight (60 tonne) polypropylene high-void box
units; including excavation and backfilling as required. Note final surfacing
| not included |  |  | 600 | m3 | 165 | 200 |  | 120000
Soakaway crates; lightweight (20 tonne) polypropylene high-void box units;
including excavation and backfilling as required. Note final surfacing not
| included |  |  | 600 | m3 | 160 | 195 | 96000
EXTERNAL DRAINAGE
GULLIES
Vitrified clay; set in concrete grade C20, 150mm
thick; additional excavation and disposal
Yard gully (mud); trapped with rodding eye;
galvanized bucket; stopper
225mm dia., 100mm dia. outlet, cast iron hinged
| grate and frame |  |  | 20 | nr | 428.87 | 428.87 | 8577.4 | 8577.4
34.01 URBAN AND LANDSCAPE DRAINAGE
Slot and grate drainage
ACO MultiDrain M100D polymer concrete channel
drainage system; galvanized steel edge trim;
nominal bore 100mm; type of fall constant; bedding
and haunching with in situ concrete (not included)
Slotted grating
galvanized steel grating, load class A15
| (pedestrian areas) |  |  | 700 | m | 114.36 | 114.36 | 80052 | 80052
UNDER SLAB DRAINAGE
POLYVINYL CHLORIDE PIPES
Unplasticized PVC pipes; ring seal sockets;
excavation and supports, backfilling;
6 m pipe lengths unless stated otherwise
110 mm pipes; in trenches, depth
| not in trench |  |  | 150 | m | 20.38 | 20.38 | 3057 | 3057
| extra for bend; short radius (socket/spigot) |  |  | 10 | nr | 55.68 | 55.68 | 556.8 | 556.8
| extra for bend; adjustable (socket/spigot) |  |  | 6 | nr | 56.97 | 56.97 | 341.82 | 341.82
| extra for reducer |  |  | 6 | nr | 23.72 | 23.72 | 142.32 | 142.32
| extra for branches; equal (socket/spigot) |  |  | 6 | nr | 71.11 | 71.11 | 426.66 | 426.66
EXTERNAL DRAINAGE
POLYVINYL CHLORIDE PIPES
Unplasticized PVC pipes; ring seal sockets;
excavation and supports, backfilling;
6 m pipe lengths unless stated otherwise
110 mm pipes; in trenches, depth
| ne 1.50m deep |  |  | 200 | m | 34.62 | 34.62 | 6924 | 6924
| extra for bend; short radius (socket/spigot) |  |  | 10 | nr | 55.68 | 55.68 | 556.8 | 556.8
| extra for bend; adjustable (socket/spigot) |  |  | 10 | nr | 56.97 | 56.97 | 569.7 | 569.7
| extra for reducer |  |  | 10 | nr | 23.71 | 23.71 | 237.1 | 237.1
| extra for branches; equal (socket/spigot) |  |  | 10 | nr | 71.11 | 71.11 | 711.1 | 711.1
MANHOLES
Precast concrete circular manhole; CPM Perfect
Manhole; complete with preformed benching and
outlets to base; elastomeric seal to joints to
rings; single steps as required. Excavations and
backfilling not included
1200mm dia. with up to four outlets 100mm or
150mm dia.; effective internal depth:
|  | 1250 mm deep |  | 2 | nr | 929.49 | 929.49 | 1858.98 | 1858.98
|  | 1500 mm deep |  | 4 | nr | 1029.72 | 1029.72 | 4118.88 | 4118.88
| CAR PARKING | [6 empty] | 6300000 | 10120000
Building Prices per Functional Unit
Utilities, Civil Engineering facilities
Car Parking
underground car parks partially underground under buildings; natural
| ventilation; 27 to 30m2 / car |  |  | 210 | p/car | 20500 | 28500
underground car parks completely underground with landscaped roof;
| mechanical ventilation; 28 to 32m2/car |  |  | 210 | p/car | 36500 | 51000
underground car parks completely underground under buildings;
| mechanical ventilation; 28 to 32m2/car |  |  | 210 | p/car | 30000 | 42000 | 6300000
Building Prices per Square Metre
UNICLASS D1 UTILITIES, CIVIL ENGINEERING FACILITIES
Underground car parks
| partially underground under buildings; naturally ventilated |  |  | 8800 | m2 | 660 | 840
| completely underground under buildings with mechanical ventilation |  |  | 8800 | m2 | 900 | 1150 |  | 10120000
| completely underground with landscaped roof and mechanical ventilation |  |  | 8800 | m2 | 1075 | 1375
| GENERAL SUPERSTRUCTURES AND FACILITIES | [6 empty] | 10735119.2572 | 14464812.746
UNICLASS D5 RECREATIONAL FACILITIES
| Dining blocks and canteens |  |  |  | m2 | 1475 | 1875
| General purpose halls |  |  | 0 | m2 | 1350 | 1725
Swimming pools
| international standard |  |  | 1270.2 | m2 | 4200 | 5300 | 5334840 | 6732060
| Indoor bowls halls |  |  |  | m2 | 820 | 1050
| Health and fitness clubs |  |  | 1394 | m2 | 1725 | 2200 | 2404650 | 3066800
| Sports pavilions |  |  |  | m2 | 1225 | 1575
| changing only |  |  | 692.196 | m2 | 1425 | 1800 | 986379.2573 | 1245952.746
| social and changing |  |  |  | m2 | 1425 | 1800
| Clubhouses |  |  | 1710 | m2 | 1175 | 1475 | 2009250
OR
Wernick's Modular Building
Suitable standard building incorporating our standard finishes of colourcoat steel external to the external walls, vinyl faced plasterboard internal walls, suspended ceilings, comfort heating and cooling as your heat source, suitable floor coverings'
|  |  |  | 1710 |  | 1800 | 2000 |  | 3420000
| SPORTS PITCH | [6 empty] | 385887.5 | 509320
8.3 SOFT LANDSCAPING, PLANTING AND IRRIGATION SYSTEMS
8.3.1 Seeding and Turfing
Please refer to Spon’s External Works and Landscape Price Book for a more
comprehensive range of rates
Surface treatment
spread and lightly consolidate top soil from spoil heap 150mm thick; by
| machine |  |  |  | m2 | 2.35 | 2.85
Plant supply, planting, maintenance and 12 months guarantee
| turfed areas |  |  |  | m2 | 6.75 | 8.2
8.2.2 Special Surfacing and Pavings Sports Grounds
Pitch plateau construction and pitch drainage not included
FIFA one star football and IRB reg 22 rugby union
Lano Rugby Max 60mm monofilament laid on shockpad on a dynamic base
infill with 32 kg/m2 sand and 11 kg/m2 SBR rubber – IRB Clause 22 compliant;
supply and spread to required infill rates, 2EW sand and 0.5–2mm SBR
Rubber. Sand (32 kg/m2)and rubber (11 kg/m2) spread and brushed into
| surface; white lining; 3.5m high perimeter fence |  |  | 10400 | m2 | 26.5 | 35 | 275600 | 364000
Tennis and netball court
Lay final layer on existing subbase of 50mm porous stone followed by 2
coats of porous bitumen macadam. 40mm binder course; 14mm aggregate
and 20mm surface course with 6mm aggregate. Laid to fine level tolerances
and laser leveled, +/- 6mm tolerance over 3 m; white lining; 3m high
| perimeter fencing |  |  | 2595 | m2 | 42.5 | 56 | 110287.5 | 145320
Natural grass winter sports
Strip topsoil and level existing surface (cut and fill); laser grade formation and
proof roll. Load and spread topsoil, grade and consolidate; cultivate and
grade topsoil. Supply and spread 25mm approved sand and mix into topsoil
| by power harrow; apply pre-seeding fertilizer and sow winter rye sports grass |  |  |  | m2 | 9.6 | 12.6
Tennis courts; En Tout Cas Ltd
Hard playing surfaces to SAPCA
Code of Practice minimum
requirements; laid on 40mm thick
macadam base on 200mm thick
stone foundation; to include lines,
nets, posts, brick edging, 2.75m
high fence and perimeter drainage;
based on court size 573m2
Playdek; all weather porous
macadam and acrylic colour
coating hardcourt – – – – – nr £40,700.00
| GENERAL GARDEN LANDSCAPED AREA | [6 empty] | 68690 | 80245
8.3.2 External Planting
Planted areas (per m² of planted area)
| shrubbed planting |  |  | 100 | m2 | 59 | 72 | 5900 | 7200
| dense planting |  |  | 50 | m2 | 60 | 73 | 3000 | 3650
| shrubbed area including allowance for small trees |  |  | 50 | m2 | 77 | 93 | 3850 | 4650
Paved areas
Gravel paving rolled to falls and chambers paving on subbase; including
| excavation |  |  | 200 | m2 | 17.2 | 22 | 3440 | 4400
Resin bound paving
| 16mm–24mm deep of natural gravel |  |  | 100 | m2 | 71 | 90 | 7100
| 16mm–24mm deep of crushed rock |  |  | 100 | m2 | 72 | 91
| 16mm–24mm deep of marble chips |  |  | 100 | m2 | 78 | 98 |  | 9800
Dwarf support wall
| 140 mm thick; solid |  |  | 100 | m2 | 50.8 | 50.8 | 5080 | 5080
8.5 EXTERNAL FIXTURES
8.5.1 Site/Street Furniture and Equipment
Street Furniture
Roadsigns
| reflected traffic signs 0.25 m² area on steel post |  |  | 5 | nr | 140 | 165 | 700 | 825
| internally illuminated traffic signs; dependent on area |  |  | 5 | nr | 220 | 270 | 1100 | 1350
| externally illuminated traffic signs; dependent on area |  |  | 5 | nr | 860 | 1050 | 4300 | 5250
Benches; bolted to ground
| benches – hardwood or precast concrete |  |  | 10 | nr | 1125 | 1375 | 11250 | 13750
Litter bins; bolted to ground
| precast concrete |  |  | 6 | nr | 205 | 250 | 1230 | 1500
| hardwood slatted |  |  |  | nr | 210 | 255
| cast iron |  |  |  | nr | 420 | 510
| large aluminium |  |  | 3 | nr | 640 | 770 | 1920 | 2310
| Bus stops including basic shelter |  |  |  | nr | 2650 | 3200
| Pillar box |  |  |  | nr | 640 | 770
| Galvanized steel cycle stand |  |  | 10 | nr | 52 | 63 | 520 | 630
| Galvanized steel flag staff |  |  | 2 | nr | 1250 | 1525 | 2500 | 3050
RESIN BOUND AND RESIN BONDED SURFACES
Resin bonded surfaces; excavate 230mm; bring to grade; lay 150mm Type
1 granular material; hand lay base course of 60mm macadam and resin
bonded wearing course; all disposal off site; edgings excluded
|  | Natratex resin bonded macadam wearing course |  | 200 | m2 | 84 | 84 | 16800 | 16800
general paved area

## Developed Feasibility
[5 empty] | QUANTITY | UNIT | RATE (LOWER SPEC) | RATE (HIGHER SPEC) | VALUE (LOWER SPEC) | VALUE (HIGHER SPEC)
SUBSTRUCTURE
| Building Cost Model Used: Concert Hall |  |  |  | Model location is Inner London Model TPI = 131; LF = 1.06
Substructure
Piled foundations; RC ground bearing slab; lift pits
| & sumps. Partial basement 1,000 m² assumed |  |  |  | 11019.1383 | m2 | 490 |  | 5399377.7788
secant piled with RC lining walls and cavity drain
OR
Approximate Estimating Rates
Unless otherwise described units denoted as m² refer to appropriate unit areas (rather than gross internal floor areas).
1.1.2 Specialist Foundations
Piling
Enabling works
excavate to form piling mat; supply and lay imported hardcore – recycled
| brick and similar to form piling mat |  |  |  | 5509.5692 | m3 | 11.3 | 13.7 | 62258.1315 | 75481.0975
provision of plant (1 nr rig); including bringing to and removing from site;
| maintenance, erection and dismantling at each pile position |  |  |  | 1 | item | 19000 | 23000 | 19000 | 23000
Supply and install concrete Continuous Flight Auger (CFA) piles; cart away
inactive spoil; measure total length of pile
| 750mm dia. reinforced concrete CFA piles |  |  |  | 936.6268 | m | 130 | 155 | 121761.4785 | 145177.1474
Pile testing
| using tension piles as reaction; typical loading test 1000 kN to 2000 kN |  |  |  |  | item | 7900 | 9500
| integrity testing; minimum 20 per visit |  |  |  | 10 | nr | 16 | 19.3 | 160 | 193
Secant wall piling, 750mm dia. piles including site mobilization and
demobilization; Measure total area of piling (total length × total depth)
| supply and install secant wall piling |  |  |  | 3426 | m2 | 270 | 325 | 925020 | 1113450
Steel sheet piling; Measure total area of piling (total length × total depth)
interlocking steel sheet piling to excavation perimeter; Corus LX or similar;
| extraction on completion |  |  |  | 3426 | m2 | 200 | 240 | 685200 | 822240
Reinforced concrete basement walls;
NOTE: excluding bulk excavation costs and hardcore fill
| 200mm thick waterproof reinforced concrete |  |  |  | 1142 | m2 | 380 | 460 | 433960 | 525320
CAR PARKING
Building Prices per Functional Unit
Utilities, Civil Engineering facilities
Car Parking
underground car parks partially underground under buildings; natural
| ventilation; 27 to 30m2 / car |  |  |  | 210 | p/car | 20500 | 28500 | 4305000 | 5985000
underground car parks completely underground with landscaped roof;
| mechanical ventilation; 28 to 32m2/car |  |  |  | 210 | p/car | 36500 | 51000 | 7665000 | 10710000
underground car parks completely underground under buildings;
| mechanical ventilation; 28 to 32m2/car |  |  |  | 210 | p/car | 30000 | 42000 | 6300000 | 8820000
Building Prices per Square Metre
UNICLASS D1 UTILITIES, CIVIL ENGINEERING FACILITIES
Underground car parks
| partially underground under buildings; naturally ventilated |  |  |  | 8800 | m2 | 660 | 840 | 5808000 | 7392000
| completely underground under buildings with mechanical ventilation |  |  |  | 8800 | m2 | 900 | 1150 | 7920000 | 10120000
| completely underground with landscaped roof and mechanical ventilation |  |  |  | 8800 | m2 | 1075 | 1375 | 9460000 | 12100000
1 | SPECIFIC SUPERSTRUCTURE PRICING |  |  |  | 4243 | Total GIFA M2
1.1 | Frame | Steel frame; composite beam and slab floors Suspended slab; permanent steel shuttering with 130mm thick concrete; no coverings or finishes - up to 6 storeys | Changed to tpi 4Q2022 and location of wales |  | 4243 | GIFA |  | 195 |  | 827385
1.2 | Upper Floors | Post-tensioned concrete upper floors reinforced post-tensioned suspended concrete slab 150–225mm thick, 40N/mm2, reinforcement 60kg/m3, formwork | Changed to tpi 4Q2022 and location of wales |  | 1484 | m2 |  | 140 |  | 207760
1.3 | Roofing | Flat Roof - Flat roofing systemsIncludes insulation and vapour control barrier; excludes decking (U-value = 0.25W/m2K) | Changed to tpi 4Q2022 and location of wales | lower cost - 20mm thick polymer modified asphalt roofing including felt underlay. higher cost - single layer polymer roofing membrane with tapered insulation | 667 | m2 | 136 | 185 | 90712 | 123395
|  | Pitched Roof - Steel trussed with metal sheet cladding Steel roof trusses and beams; thermal and acoustic insulation (U-value =0.25W/m2K) aluminium profiled composite cladding | Changed to tpi 4Q2022 and location of wales |  | 2075 | m2 |  | 360 |  | 747000
1.4 | Stairs & Ramps | Reinforced concrete construction Staircase; terrazzofinish; mild steel balustrades and handrails; plastered soffit;balustrades and staircase soffit decorated3.00m rise; dogleg | Changed to tpi 4Q2022 and location of wales |  | 2 | nr |  | 11000 |  | 22000 | spons Pg.194
1.5 | External walls | Metal profiled cladding panel - Flat panel composite insulated roofing system; micro-rib panel; 60mm overall panel, thickness (U-value = 0.35W/m2K) | Changed to tpi 4Q2022 and location of wales | 454 perimeter 2 floors | 6764.6 | m2 |  | 305 |  | 2063203 | Spons Pg.197
| Wall Insulation | Insulation - External wall insulation - Kingspan Kooltherm K8 (Thermal conductivity 0.022W/mK) zero ODP rigiurethene insulation board or other equal; as partial cavity fill; including cutting and fitting around wall ties and retaining discs | Changed to tpi 4Q2022 and location of wales
|  | 40mm thickness low cost | 75mm Thickness high cost |  | 6764.6 | m2 | 19.6 | 24 | 132586.16 | 162350.4
1.6 | External windows & Doors
| Windows | Unitized curtain walling system with double glazed units, aluminium structural framing and sandal rails. Standard colour powered coated | Glazing to swimming pool | Changed to tpi 4Q2022 and location of wales
|  |  | Tennis side | H 7.5m x W 50m | 375 | m2 |  | 1310 |  | 491250 | spons Pg.198
|  |  | Rugby side | H 9.5-8m x 17m | 161.5 | m2 |  | 1310 |  | 211565 | spons Pg.198
window number
|  | uPVC windows, Windows; standard ironmongery; sills and factory glazed with low-e 24 mm double glazing | Changed to tpi 4Q2022 and location of wales | low cost wer rating C, high cost wer rating A
| 6 | GF |  | 4 x 3.4 | 81.6 | m2 | 289 | 295 | 23582.4 | 24072 | spons Pg. 200
| 8 |  |  | 4 x 3.4 | 108.8 | m2 | 289 | 295 | 31443.2 | 32096 | spons Pg. 200
| 4 |  |  | 0.5 x 3 | 6 | m2 | 289 | 295 | 1734 | 1770 | spons Pg. 200
| Doors | Wheel chair entrance door - Stainless steel entrance screens and doors, Purpose-made screen; double glazed, with automatic doors | Changed to tpi 4Q2022 and location of wales |  | 3 | nr |  | 3275 |  | 9825 | spons Pg.202
|  | Steel external doors Standard doors, single external steel door, including frame, ironmongery, powder coated finish | Changed to tpi 4Q2022 and location of wales |  | 9 | nr |  | 1310 |  | 11790 | spons Pg.201
1.7 | Internal Walls
| GF | Frame and panel partitions, Timber stud partitions, structure only comprising 100 mm × 38 mm softwood studs at 600 mm centres; head and sole plates | Changed to tpi 4Q2022 and location of wales | 184.593 x 3.4 | 627.6162 | m2 |  | 32 |  | 20083.7184 | spons Pg. 203
| FF | Frame and panel partitions, Timber stud partitions, structure only comprising 100 mm × 38 mm softwood studs at 600 mm centres; head and sole plates | Changed to tpi 4Q2022 and location of wales | 220.463 x 3.4 | 749.5742 | m2 |  | 32 |  | 23986.3744 | spons Pg. 203
1.8 | Lift and Conveyor installations | Passenger lifts (standard brushed stainless steel finish; 2 panel centre opening doors) 8-person; 4 stops; 1.0m/s speed | Changed to tpi 4Q2022 and location of wales |  | 3 | nr |  | 98000 |  | 294000
1.9 | Internal Windows & Doors
| Windows | internal window gym looking over pool area, Purpose-made windows, Softwood windows (U-value = 1.6 W/m2 K) painted; double glazed; over 1.50 m2 | Changed to tpi 4Q2022 and location of wales |  | 93.12 | m2 |  | 760 |  | 70771.2 | spons Pg. 200
| Doors & Screens | Toilet doors - Ironmongery sets Stainless steel ironmongery; euro locks; push plates; kick plates; signage; closures; standard sets, standard bathroom door (unisex) | Changed to tpi 4Q2022 and location of wales |  | 9 | nr |  | 350 |  | 3150 | spons Pg. 206
|  | Plant rooms - Ironmongery sets Stainless steel ironmongery; euro locks; push plates; kick plates; signage; closures; standard sets, maintenance/plant room door; lockable; fire-rated | Changed to tpi 4Q2022 and location of wales |  | 2 | nr |  | 435 |  | 870 | spons Pg. 206
|  | Fire doors Standard fire doors; cellular core; softwood lining; softwood architrave; aluminuim ironmongery (lockable, self-closure); painting or polishing; single leaf; Oak veneered; 60 min fire resistance; polished | Changed to tpi 4Q2022 and location of wales |  | 41 | nr |  | 1035 |  | 42435 | spons Pg. 206
2 | Internal Finishes
| Walls | In situ wallfinishes - one mist and two coats emulsion paint ( to General areas) GF | Changed to tpi 4Q2022 and location of wales | office 1, staff room, reception, office 2, lift, corridor | 595 | m2 |  | 5.6 |  | 3332
|  | Aquamura wall Panels; including backing (In Wet Areas) GF | Changed to tpi 4Q2022 and location of wales | Swimming pool, pool store, plant room, pool changing room, pool walkway, toilets 1, toilets 2, first aid | 2645.2 | m2 |  | 30 |  | 79356
|  | In situ wallfinishes - one mist and two coats emulsion paint ( to General areas) FF | Changed to tpi 4Q2022 and location of wales | studio 1, studio 2, gym, gallery, corridors, store 1, store 2, store 3, store 4, store 5, stairwell, store 6, emergency access | 2186.2 | m2 |  | 5.6 |  | 12242.72
|  | Aquamura wall Panels; including backing (In Wet Areas) FF | Changed to tpi 4Q2022 and location of wales | changing rooms gym, toillets, disabled toilets | 486.2 | m2 |  | 30 |  | 14586
| Floors | [7 empty] | 0
|  | Vinyl GF | Changed to tpi 4Q2022 and location of wales |  | 1154 | m2 | 20 |  | 23080
|  | Tiles GF - Glazed ceramic tiled flooring, anti-slip tiles | Changed to tpi 4Q2022 and location of wales |  | 1564 | m2 | 65 |  | 101660
|  | Vinyl FF | Changed to tpi 4Q2022 and location of wales |  | 1473 | m2 | 20 |  | 29460
| Ceilings | plaster skim coat to plasterboard ceilings | Changed to tpi 4Q2022 and location of wales |  | 4243 | m2 |  | 9 |  | 38187 | spons Pg. 210
|  | Emulsion paint to plaster, two coats |  |  | 4243 | m2 |  | 6.3 |  | 26730.9 | spons Pg. 210
3 | Fittings and Furnishings
|  | General fittings, furnishings and equipment | Provisional Sum |  | 4086.388 | GIFA | 75 | 95 | 306479.1 | 388206.86
Gym
|  | Body Power Smith Half Rack - Bench Included |  |  | 1 |  | 1059 |  |  | 1059
|  | Powertec Leg Press |  |  | 1 |  | 995 |  |  | 995
|  | Hammer Strength Plated Loaded V-Squat |  |  | 1 |  | 5898 |  |  | 5898
|  | Body-Solid Pro club line series 2 Bicep & Tricep (235lbs) |  |  | 1 |  | 2199 |  |  | 2199
|  | Powerline Preacher Curl Bench |  |  | 1 |  | 271.99 |  |  | 271.99
|  | TuffStuff Apollo AP-71MP Multi Press |  |  | 1 |  | 2795 |  |  | 2795
|  | Powertec Isolateral Workbench Multi Press |  |  | 1 |  | 859 |  |  | 859
|  | Body-Solid Pro Club Line T-Bar |  |  | 1 |  | 439 |  |  | 439
|  | Matrix Fitness Magnum MG-A52 Back Extension |  |  | 1 |  | 714 |  |  | 714
|  | Life Fitness Series Plate Loaded Row |  |  | 1 |  | 3774 |  |  | 3774
|  | Body-Solid G6B Bi-Angular Gym with Inner/Outer Thigh |  |  | 1 |  | 3399 |  |  | 3399
|  | Life Fitness Insignia Series Abdominal |  |  | 1 |  | 6936 |  |  | 6936
|  | Body-Solid Pro Club Line Series 2, Chin & Dip (235lbs) |  |  | 1 |  | 2799 |  |  | 2799
|  | Body Power Premium Ab Wheel |  |  | 3 |  | 5.99 |  |  | 17.97
|  | Solid Weight Plates |  |  | 2 |  | 42.99 |  |  | 85.98
|  | Powertec Spotter Arms |  |  | 3 |  | 69.99 |  |  | 209.97
|  | Body-Solid J Cups |  |  | 2 |  | 79.99 |  |  | 159.98
|  | Body-Solid Dip Attachment |  |  | 1 |  | 209 |  |  | 209
|  | Barbell Pad |  |  | 2 |  | 4.99 |  |  | 9.98
|  | Floor Tile Ramp Edge |  |  | 6 |  | 5.99 |  |  | 35.94
|  | Tricep Rope |  |  | 2 |  | 8.99 |  |  | 17.98
|  | Tricep Rope |  |  | 2 |  | 9.99 |  |  | 19.98
|  | Floor Tile |  |  | 3 |  | 9.99 |  |  | 29.97
|  | Soft Pilates Weights |  |  | 2 |  | 12.59 |  |  | 25.18
|  | Pro-grip Seated Row Bar |  |  | 2 |  | 14.99 |  |  | 29.98
|  | Double Handled Lat Bar |  |  | 2 |  | 29.95 |  |  | 59.9
|  | Running machine |  |  | 4 |  | 1295 |  |  | 5180
|  | Cycle bike 1 |  |  | 3 |  | 999 |  |  | 2997
|  | Cycle bike 2 |  |  | 14 |  | 495 |  |  | 6930
|  | SkiErg |  |  | 1 |  | 235 |  |  | 235
|  | Rowing Machine |  |  | 2 |  | 699 |  |  | 1398
|  | Cross trainer |  |  | 3 |  | 249 |  |  | 747
|  | Clumbmmill |  |  | 2 |  | 5399.99 |  |  | 10799.98
| Framed panel cubicles – cont | Family changing bays | 5.096 | 9 | 45.864 | m2 |  | 196 |  | 8989.344 | spons Pg. 206
| IPS duct panel systems; melamine finish chipboard; softwood timber subframe, 2.70 m high IPS back panelling system; to accommodate wash hand basins or urinals; access hatch; frame support | Double changing bays | 1.738 | 48 | 83.424 | m2 |  | 196 |  | 16351.104 | spons Pg. 206
|  | Single changing bays | 1.188 | 23 | 27.324 | m2 |  | 196 |  | 5355.504 | spons Pg. 206
4 | services
4.1 | Sanitary installations | Disabled toilet, including WC, wash hand basin, grabrails and otherfittings | Changed to tpi 4Q2022 and location of wales |  | 4 | nr |  | 1640 |  | 6560 | spons Pg. 140
|  | shower tray; glazedfireclay; chromium plated waste; riser pipe; rose andmixing valve | Changed to tpi 4Q2022 and location of wales |  | 14 | nr |  | 760 |  | 10640 | spons Pg. 213
|  | WC suite | Changed to tpi 4Q2022 and location of wales |  | 28 | nr |  | 500 |  | 14000 | spons Pg. 143
4.2 | Disposal Installations |  | Provisional sum |  | 4243 | GIFA |  | 300 |  | 1272900
4.3 | Water installations |  | Provisional sum |  | 4243 | GIFA |  | 300 |  | 1272900
4.4 | Heat source |  | Provisional sum |  | 4243 | GIFA |  | 300 |  | 1272900
4.5 | Electrical installations |  | Provisional sum |  | 4243 | GIFA |  | 300 |  | 1272900
4.6 | Power |  | Provisional sum |  | 4243 | GIFA |  | 300 |  | 1272900
GENERAL SUPERSTRUCTURES AND FACILITIES
UNICLASS D5 RECREATIONAL FACILITIES
| Dining blocks and canteens |  |  |  |  | m2 | 1475 | 1875
| General purpose halls |  |  |  | 0 | m2 | 1350 | 1725
Swimming pools
| international standard |  |  |  | 1270.2 | m2 | 4200 | 5300 | 5334840 | 6732060
| Indoor bowls halls |  |  |  |  | m2 | 820 | 1050
| Health and fitness clubs |  |  |  | 1394 | m2 | 1725 | 2200
| Sports pavilions |  |  |  |  | m2 | 1225 | 1575
| changing only |  |  |  | 692.196 | m2 | 1425 | 1800 | 986379.2573 | 1245952.746
| social and changing |  |  |  |  | m2 | 1425 | 1800
| Clubhouses |  |  |  | 1710 | m2 | 1175 | 1475 | 2009250 | 2522250
OR
Wernick's Modular Building
Suitable standard building incorporating our standard finishes of colourcoat steel external to the external walls, vinyl faced plasterboard internal walls, suspended ceilings, comfort heating and cooling as your heat source, suitable floor coverings'
[5 empty] | 1710 |  | 1800 | 2000 | 3078000 | 3420000
SPORTS PITCH
8.3 SOFT LANDSCAPING, PLANTING AND IRRIGATION SYSTEMS
8.3.1 Seeding and Turfing
Please refer to Spon’s External Works and Landscape Price Book for a more
comprehensive range of rates
Surface treatment
spread and lightly consolidate top soil from spoil heap 150mm thick; by
| machine |  |  |  |  | m2 | 2.35 | 2.85
Plant supply, planting, maintenance and 12 months guarantee
| turfed areas |  |  |  |  | m2 | 6.75 | 8.2
8.2.2 Special Surfacing and Pavings Sports Grounds
Pitch plateau construction and pitch drainage not included
FIFA one star football and IRB reg 22 rugby union
Lano Rugby Max 60mm monofilament laid on shockpad on a dynamic base
infill with 32 kg/m2 sand and 11 kg/m2 SBR rubber – IRB Clause 22 compliant;
supply and spread to required infill rates, 2EW sand and 0.5–2mm SBR
Rubber. Sand (32 kg/m2)and rubber (11 kg/m2) spread and brushed into
| surface; white lining; 3.5m high perimeter fence |  |  |  | 10400 | m2 | 26.5 | 35 | 275600 | 364000
Tennis and netball court
Lay final layer on existing subbase of 50mm porous stone followed by 2
coats of porous bitumen macadam. 40mm binder course; 14mm aggregate
and 20mm surface course with 6mm aggregate. Laid to fine level tolerances
and laser leveled, +/- 6mm tolerance over 3 m; white lining; 3m high
| perimeter fencing |  |  |  |  | m2 | 42.5 | 56
Natural grass winter sports
Strip topsoil and level existing surface (cut and fill); laser grade formation and
proof roll. Load and spread topsoil, grade and consolidate; cultivate and
grade topsoil. Supply and spread 25mm approved sand and mix into topsoil
| by power harrow; apply pre-seeding fertilizer and sow winter rye sports grass |  |  |  |  | m2 | 9.6 | 12.6
GENERAL GARDEN LANDSCAPED AREA
8.3.2 External Planting
Planted areas (per m² of planted area)
| shrubbed planting | [5 empty] | 59 | 72
| dense planting | [5 empty] | 60 | 73
| shrubbed area including allowance for small trees | [5 empty] | 77 | 93
Paved areas
Gravel paving rolled to falls and chambers paving on subbase; including
| excavation | [5 empty] | 17.2 | 22
Resin bound paving
| 16mm–24mm deep of natural gravel | [5 empty] | 71 | 90
| 16mm–24mm deep of crushed rock | [5 empty] | 72 | 91
| 16mm–24mm deep of marble chips | [5 empty] | 78 | 98
Dwarf support wall
| 140 mm thick; solid |  |  |  |  | m2 | 50.8
8.5 EXTERNAL FIXTURES
8.5.1 Site/Street Furniture and Equipment
Street Furniture
Roadsigns
| reflected traffic signs 0.25 m² area on steel post | [5 empty] | 140 | 165
| internally illuminated traffic signs; dependent on area | [5 empty] | 220 | 270
| externally illuminated traffic signs; dependent on area | [5 empty] | 860 | 1050
Benches; bolted to ground
| benches – hardwood or precast concrete | [5 empty] | 1125 | 1375
Litter bins; bolted to ground
| precast concrete | [5 empty] | 205 | 250
| hardwood slatted | [5 empty] | 210 | 255
| cast iron | [5 empty] | 420 | 510
| large aluminium | [5 empty] | 640 | 770
| Bus stops including basic shelter | [5 empty] | 2650 | 3200
| Pillar box | [5 empty] | 640 | 770
| Galvanized steel cycle stand | [5 empty] | 52 | 63
| Galvanized steel flag staff | [5 empty] | 1250 | 1525

## Material Cost Comparison
Material Cost Comparison
Material | Unit | Cost |  | Material | Unit | Cost |  | Cost Difference
UPVC Windows | No | 800 | 0.9 x 1.1 | Composite Windows | No | 1200 | 0.9 x 1.1 | 400 | Costing an additional £400.00 for that size window to have composite, while UPVC is a better financial option
Aquamura Panels | m2 | 35 |  | Wall tiles | m2 | 30 |  | 5 | The chosen material is aquamura panels as the product is easy to install reducing the labour cost for installation, is designed to have a longer lasting life line than tiles.
Roof Tiles | m2 | 170 |  | Roof panel system | m2 | 285.7143 |  | 115.7143 | The roofing panel system is considered a specialist topic in the construction area, causing only certain people can install the material which will be seen as an additional cost. the panell systems are considered to be more weather resistant and there for tend to have a longer life line, allowing the maintence costs to be lower through the life cycle which is a bigger consideration due to the location of the building.

## 1. Preliminaries-main contract
Bill of Quantities
Page of BoQ (1 of
Item No | Description | Unit | Quantity | Rate | Amount
PRELIMINARIES
Bill No. 1: Preliminaries (main contract)
PART B: PRICING SCHEDULE
1.1 | Employer's requirements
1.1.1 | Site accommodation
1.1.1.1 | Site accommodation | item | Fixed charge
Contractor's office rental
| Mobile offices (10 staff × 8 m²) = 80 m² | weeks | 66 | £ 205.00 | £ 15,170.00
Contractor's site huts
| Stores hut, 22 m² | weeks | 66 | £ 56.00 | £ 4,144.00
Canteen and welfare huts
| Canteen 70 m² (assume 70 men) | weeks | 66 | £ 180.00 | £ 13,320.00
| Washroom 30 m² | weeks | 66 | £ 70.00 | £ 5,180.00
| Staff toilets | weeks | 66 | £ 180.00 | £ 13,320.00
| Site toilets | weeks | 66 | £ 240.00 | £ 17,760.00
1.1.1.1.2 | Adaptation/alterations during works | item | Fixed charge
1.1.1.1.3 | Dismantling and removing from site, including rectifying any damage | item | Fixed charge
1.1.1.1.4 | Maintaining | weeks
1.1.1.1.5 | Cleaning | weeks
1.1.1.1.6 | Charges | weeks
1.1.1.1.7 | Off-site rented temporary accomodation
1.1.1.2 | Furniture and equipment | item | Fixed charge
| 1. Bring to site and installing | item | Fixed charge
| 2. Cleaning | week
| 3. Charges | week
| 4. Dismantling and removing from site | item | Fixed charge
1.1.2 | Site Records
1.1.2.1 | Site Records | item | Fixed charge
1.1.2.2 | Web-based information management system | item | Fixed charge
1.1.3 | Completion and post-completion requirements
1.1.3.1 | Handover requirements | item | Fixed charge
1.1.3.2 | Opetion and maintenance services | week
1.1.3.3 | Landscape management services | week
1.2 | Main Contractor's cost items
1.2.1 | Management and staff
1.2.2 | 1. Project-specific management and staff | week
| Agent | week | 66 | £ 1,895.00 | £ 125,070.00
| Senior Engineer | week | 66 | £ 1,745.00 | £ 115,170.00
| Engineers | week | 80 | £ 1,320.00 | £ 105,600.00
| General foreman | week | 66 | £ 1,020.00 | £ 67,320.00 | 26/05/2023
| Office manager/cost clerk | week | 66 | £ 870.00 | £ 57,420.00 | 30/08/2024
| Timekeeper/Storeman/Checker | week | 66 | £ 610.00 | £ 40,260.00
| Admin support | week | 66 | £ 460.00 | £ 30,360.00 | 462
| Security guard | week | 66 | £ 510.00 | £ 33,660.00 | 66
| Quantity Surveyor | week | 66 | £ 1,566.00 | £ 103,356.00
| Fitter | week | 66 | £ 850.00 | £ 56,100.00
2 Visiting management and staff
3 Extraordinary support costs
4. Staff travel
Site transport for staff and general use
| QS/Agent's cars | week | 66 | £ 160.00 | £ 10,560.00
| Engineers' cars (contribution) | week | 146 | £ 80.00 | £ 11,680.00
| Land Rover or similar SWB | week | 66 | £ 390.00 | £ 25,740.00
| Site transport – Labour | week | 60 | £ 610.00 | £ 36,600.00
1.2.2 | Site establishment
880342

## Information given by model
| Depth | Area | Volume | Length
Reinforced slab for Car park | 0.3 | 8802
Car park | 3 | 8802 | 26406
Reinforced slab for 3G pitch | 0.3 | 7324
3G pitch |  | 7324
Piling (estimate based on UWTSD library) |  |  |  | 936.6268
Basment wall |  | 1142
GF plan - Dims' take-off
General building |  | 2217.1383
Swimming pool incl surrounding walkways |  | 1270.2
Pool store |  | 138.1675
Plant room |  | 116.5748
Changing rooms |  | 692.196
Tennis courts |  | 1286
Club house GF |  | 830
Club house 1st Fl |  | 800
Changing facilities / Gym |  | 1394
Studio areas

## Takeoff Quantities
2023-01-10
Concept design 6
| Object Title | Area (m²) | Perimeter of Original Areas (m)
GROUND FLOOR | Swimming Pool | 856.73 | 137.29
| Pool store | 142.69 | 54.87
| Plant room | 113.55 | 51.68
| Changing rooms (Pool) | 772.04 | 152.86
| Office | 27.75 | 21.14
| Staff rom | 24.01 | 19.65
| Reception/foyer area | 228.35 | 91.12
| Pool walkways/surround | 449.52 | 307.59
| Office | 13.17 | 14.52
| Lift shaft | 5.8 | 10.12
| Corridor | 5.29 | 15.35
| Toilets | 59.93 | 43.89
| First Aid | 16.07 | 17.63
| Toilets | 6.09 | 9.87
| TOTAL GF | 2759.28 | 233.45
FIRST FLOOR | Studio | 125.58 | 48.78
| Studio | 127.31 | 46.86
| Gym | 454.79 | 126.69
| Changing rooms (Gym) | 185.39 | 77.13
| Toilets | 99.47 | 47.01
| Gallery / stand | 89.87 | 50.12
| Corridors | 272.19 | 235.9
| Store | 11.23 | 13.77
| Store | 14.91 | 22.8
| Store | 11.98 | 14.14
| Store | 11.04 | 17.95
| Store | 3.31 | 9.19
| Stairwell | 18.43 | 17.17
| Store | 16.11 | 18.64
| Disabled toilets/changing | 14.99 | 17.32
| Emergency access | 13.64 | 17.19
| TOTAL 1st F | 1483.62 | 220.58
OTHER | GIFA Total |  | 4242.9

## Take-off Quantities (hidden)
TA Building Consultancy LTD
LEVEL 6 QUANTITY SURVEYING [UWTSD]
[12 empty] | PILING SCHEDULE | [5 empty] | BOREHOLE INFORMATION
| External wall face length |  |  | Total trench length |  |  | GROUND SLAB
| A-E |  |  | Total trench area |  |  | Volume | 124.423 | m3
|  | 6.3 |  | A-E |  |  | Area | 829.4868 | m2 |  |  | P1 | 5.925 | P43 | 5.925 | P85 | 5.075
|  | 3.75 |  |  | 6.3 | [6 empty] | P2 | 5.925 | P44 | 5.925 | P86 | 5.925
|  | 3.75 |  |  | 3.95 |  | Plus Working Space | 956.2228 | m2 |  |  | P3 | 5.925 | P45 | 5.925 | P87 | 5.925
|  | 6.3 |  |  | 2.35 | [6 empty] | P4 | 5.925 | P46 | 5.925 | P88 | 5.925
|  |  | 20.1 |  | 3.75 | [6 empty] | P5 | 5.925 | P47 | 5.925 | P89 | 5.925
[5 empty] | 3.75 |  | REVOLVING DOOR |  |  |  |  | P6 | 5.925 | P48 | 5.925 | P90 | 5.925
[5 empty] | 3.95 |  | Volume | 2.3 | m3 |  |  | P7 | 5.925 | P49 | 5.925 | P91 | 5.925
| 1-9' |  |  |  | 2.35 |  | Area | 11.5 | m2 |  |  | P8 | 5.925 | P50 | 5.925 | P92 | 5.475
|  | 3.95 |  |  | 6.3 | [6 empty] | P9 | 5.925 | P51 | 5.925 | P93 | 5.475
|  | 2.35 |  |  |  | 32.7 | [5 empty] | P10 | 5.925 | P52 | 5.925 | P94 | 5.475
|  | 3.95 |  |  |  |  | MASS PILE CAPS |  |  |  |  | P11 | 5.925 | P53 | 5.925 | P95 | 5.475
|  | 6.3 |  | 1-9' |  |  | AREA 1 | 7.9 |  |  |  | P12 | 5.925 | P54 | 5.925 | P96 | 5.925
|  | 6.3 |  |  | 3.95 |  |  | 6.575 |  |  |  | P13 | 5.925 | P55 | 5.925 |  | 68.45
|  | 6.3 |  |  | 2.35 |  |  |  | 51.9425 |  |  | P14 | 5.925 | P56 | 5.925
|  | 6.3 |  |  | 3.95 |  | AREA 2 | 7.9 |  |  |  | P15 | 5.925 | P57 | 5.925
|  | 5.818 |  |  | 6.3 |  |  | 5.5 |  |  |  | P16 | 5.925 | P58 | 5.925
|  |  | 41.268 |  | 6.3 |  |  |  | 43.45 |  |  | P17 | 5.925 | P59 | 5.925
[5 empty] | 6.3 |  |  | 5.365 |  |  |  | P18 | 5.925 | P60 | 5.925
| A-E 2 |  |  |  | 6.3 |  |  | 6.3 |  |  |  | P19 | 5.925 | P61 | 5.925 |  | 0.082521
|  | 6.3 |  |  | 5.818 |  |  |  | 33.7995 |  |  | P20 | 5.925 | P62 | 5.925
|  | 3.75 |  |  |  | 41.268 |  |  | 129.192 | m2 |  | P21 | 5.925 | P63 | 5.075
|  | 3.75 |  | A-E 2 | [7 empty] | P22 | 5.925 | P64 | 5.075
|  | 6.3 |  |  | 6.3 | [6 empty] | P23 | 5.925 | P65 | 5.075
|  |  | 20.1 |  | 1.981 | [6 empty] | P24 | 5.925 | P66 | 5.075
[5 empty] | 3.686 |  | SHEER WALLS |  |  |  |  | P25 | 5.925 | P67 | 5.475
[5 empty] | 3.75 |  | AREA 1 |  |  |  |  | P26 | 5.925 | P68 | 5.475
[5 empty] | 3.75 |  |  | 1.172 |  |  |  | P27 | 5.925 | P69 | 5.475
| 1-9' 2 |  |  |  | 1.981 |  |  | 0.428 |  |  |  | P28 | 5.925 | P70 | 5.475
|  | 3.95 |  |  | 3.686 |  |  | 1.6 |  |  |  | P29 | 5.925 | P71 | 5.075
|  | 2.35 |  |  | 6.3 |  |  | 5.53 |  |  |  | P30 | 5.925 | P72 | 5.075
|  | 3.95 |  |  |  | 31.434 |  | 5.53 |  |  |  | P31 | 5.925 | P73 | 5.075
|  | 6.3 |  | 1-9' 2 |  |  |  | 5.13 |  |  |  | P32 | 5.925 | P74 | 5.075
|  | 6.3 |  |  | 3.95 |  |  | 6.3 |  |  |  | P33 | 5.925 | P75 | 5.475
|  | 6.3 |  |  | 2.35 |  |  | 25.69 | m |  |  | P34 | 5.925 | P76 | 5.475
|  | 6.3 |  |  | 3.95 | [6 empty] | P35 | 5.925 | P77 | 5.475
|  | 5.818 |  |  | 6.3 |  | AREA 2 |  |  |  |  | P36 | 5.925 | P78 | 5.475
|  |  | 41.268 |  | 6.3 |  |  | 2.68 |  |  |  | P37 | 5.925 | P79 | 5.925
[5 empty] | 6.3 |  |  | 3.58 |  |  |  | P38 | 5.925 | P80 | 5.925
[5 empty] | 6.3 |  |  | 6.3 |  |  |  | P39 | 5.925 | P81 | 5.925
[5 empty] | 5.818 |  |  | 6.3 |  |  |  | P40 | 5.925 | P82 | 5.075
[6 empty] | 41.268 |  | 0.9 |  |  |  | P41 | 5.925 | P83 | 5.075
[8 empty] | 19.76 | m |  |  | P42 | 5.925 | P84 | 5.075
[13 empty] | 248.85 |  | 235.9
Steel Reinforcement to Piles
WEIGHT CALCULATION
[7 empty] | DIA | No | LENGTH |  | 16
[9 empty] | mm |  | mm
[7 empty] | 16 | 288 | 1400 |  | 636.6528

## Index Factors (hidden)
TA Building Consultancy LTD
LEVEL 6 QUANTITY SURVEYING [UWTSD]
Index Factors
| SPONS - Original Tender Index - SPONS 2020 book TPI | 124 | Time Factor | =Submission/Original
| SPONS Current Tender Index - Q2 2022 (PROJECT COMMENCEMENT) | 125.6 |  | 1.0887
| SPONS Tender Index - Movement | 1.6
| BCIS Tender Index - in line with SPONS 2020 book TPI | 344
| BCIS Tender Index - Q2 2022 (PROJECT COMMENCEMENT) | 355
| BCIS Tender Index - Movement | 11
| SPONS TPI with BCIS accurate index movement | 135
| Original Location Index - Outer London (Spon’s 2020) | 1 | Location Factor | =Current/Original
| Current Location Index - Wales | 0.86 |  | 0.86
| Reference Description | Page
| Spon's A&B 2020 has been model calculated to give a book TPI | SP - pg. 44
| Outer London (Spon’s 2020) | SP - pg. 46
BCIS All-in TPI - Last updated 22-Dec-2021

## BCIS Indices (hidden)
Series: | BCIS All-in TPI
Series number: | 101 |  | quarterly
Base: | 1985 mean = 100
Last updated: | 2021-12-22
Downloaded: | 2022-02-08 01:01
Date | Index | Status | Equivalent sample | Percentage change
|  |  |  | On year | On quarter
2000-02-01 | 158 |  | 66 | 7.5 | 2.6
2000-05-01 | 158 |  | 56 | 6 | 0
2000-08-01 | 162 |  | 68 | 6.6 | 2.5
2000-11-01 | 167 |  | 59 | 8.4 | 3.1
2001-02-01 | 170 |  | 82 | 7.6 | 1.8
2001-05-01 | 171 |  | 64 | 8.2 | 0.6
2001-08-01 | 177 |  | 60 | 9.3 | 3.5
2001-11-01 | 177 |  | 73 | 6 | 0
2002-02-01 | 182 |  | 56 | 7.1 | 2.8
2002-05-01 | 189 |  | 59 | 10.5 | 3.8
2002-08-01 | 188 |  | 51 | 6.2 | -0.5
2002-11-01 | 190 |  | 63 | 7.3 | 1.1
2003-02-01 | 196 |  | 64 | 7.7 | 3.2
2003-05-01 | 198 |  | 75 | 4.8 | 1
2003-08-01 | 198 |  | 65 | 5.3 | 0
2003-11-01 | 195 |  | 66 | 2.6 | -1.5
2004-02-01 | 200 |  | 73 | 2 | 2.6
2004-05-01 | 215 |  | 68 | 8.6 | 7.5
2004-08-01 | 213 |  | 65 | 7.6 | -0.9
2004-11-01 | 225 |  | 80 | 15.4 | 5.6
2005-02-01 | 221 |  | 67 | 10.5 | -1.8
2005-05-01 | 228 |  | 66 | 6 | 3.2
2005-08-01 | 221 |  | 65 | 3.8 | -3.1
2005-11-01 | 226 |  | 63 | 0.4 | 2.3
2006-02-01 | 228 |  | 76 | 3.2 | 0.9
2006-05-01 | 231 |  | 85 | 1.3 | 1.3
2006-08-01 | 228 |  | 75 | 3.2 | -1.3
2006-11-01 | 232 |  | 61 | 2.7 | 1.8
2007-02-01 | 239 |  | 73 | 4.8 | 3
2007-05-01 | 241 |  | 66 | 4.3 | 0.8
2007-08-01 | 248 |  | 69 | 8.8 | 2.9
2007-11-01 | 251 |  | 65 | 8.2 | 1.2
2008-02-01 | 249 |  | 66 | 4.2 | -0.8
2008-05-01 | 247 |  | 68 | 2.5 | -0.8
2008-08-01 | 246 |  | 54 | -0.8 | -0.4
2008-11-01 | 240 |  | 50 | -4.4 | -2.4
2009-02-01 | 223 |  | 64 | -10.4 | -7.1
2009-05-01 | 216 |  | 53 | -12.6 | -3.1
2009-08-01 | 216 |  | 62 | -12.2 | 0
2009-11-01 | 212 |  | 64 | -11.7 | -1.9
2010-02-01 | 209 |  | 63 | -6.3 | -1.4
2010-05-01 | 218 |  | 45 | 0.9 | 4.3
2010-08-01 | 219 |  | 42 | 1.4 | 0.5
2010-11-01 | 220 |  | 49 | 3.8 | 0.5
2011-02-01 | 219 |  | 45 | 4.8 | -0.5
2011-05-01 | 223 |  | 33 | 2.3 | 1.8
2011-08-01 | 220 |  | 33 | 0.5 | -1.3
2011-11-01 | 223 |  | 38 | 1.4 | 1.4
2012-02-01 | 215 |  | 42 | -1.8 | -3.6
2012-05-01 | 230 |  | 30 | 3.1 | 7
2012-08-01 | 223 |  | 33 | 1.4 | -3
2012-11-01 | 224 |  | 36 | 0.4 | 0.4
2013-02-01 | 234 |  | 36 | 8.8 | 4.5
2013-05-01 | 236 |  | 31 | 2.6 | 0.9
2013-08-01 | 232 |  | 32 | 4 | -1.7
2013-11-01 | 239 |  | 37 | 6.7 | 3
2014-02-01 | 247 |  | 37 | 5.6 | 3.3
2014-05-01 | 259 |  | 39 | 9.7 | 4.9
2014-08-01 | 257 |  | 32 | 10.8 | -0.8
2014-11-01 | 259 |  | 31 | 8.4 | 0.8
2015-02-01 | 266 |  | 134 | 7.7 | 2.7
2015-05-01 | 272 |  | 125 | 5 | 2.3
2015-08-01 | 271 |  | 125 | 5.4 | -0.4
2015-11-01 | 270 |  | 120 | 4.2 | -0.4
2016-02-01 | 275 |  | 121 | 3.4 | 1.9
2016-05-01 | 282 |  | 122 | 3.7 | 2.5
2016-08-01 | 281 |  | 125 | 3.7 | -0.4
2016-11-01 | 291 |  | 123 | 7.8 | 3.6
2017-02-01 | 301 |  | 122 | 9.5 | 3.4
2017-05-01 | 307 |  | 117 | 8.9 | 2
2017-08-01 | 306 |  | 112 | 8.9 | -0.3
2017-11-01 | 317 |  | 106 | 8.9 | 3.6
2018-02-01 | 326 |  | 98 | 8.3 | 2.8
2018-05-01 | 326 |  | 94 | 6.2 | 0
2018-08-01 | 327 |  | 90 | 6.9 | 0.3
2018-11-01 | 330 |  | 85 | 4.1 | 0.9
2019-02-01 | 331 |  | 74 | 1.5 | 0.3
2019-05-01 | 335 |  | 66 | 2.8 | 1.2
2019-08-01 | 335 |  | 62 | 2.4 | 0
2019-11-01 | 333 |  | 56 | 0.9 | -0.6
2020-02-01 | 335 | Provisional |  | 1.2 | 0.6
2020-05-01 | 335 | Provisional |  | 0 | 0
2020-08-01 | 330 | Provisional |  | -1.5 | -1.5
2020-11-01 | 328 | Provisional |  | -1.5 | -0.6
2021-02-01 | 328 | Provisional |  | -2.1 | 0
2021-05-01 | 331 | Provisional |  | -1.2 | 0.9
2021-08-01 | 339 | Provisional |  | 2.7 | 2.4
2021-11-01 | 344 | Provisional |  | 4.9 | 1.5
2022-02-01 | 350 | Forecast |  | 6.7 | 1.7
2022-05-01 | 355 | Forecast |  | 7.3 | 1.4
2022-08-01 | 355 | Forecast |  | 4.7 | 0
2022-11-01 | 356 | Forecast |  | 3.5 | 0.3
2023-02-01 | 362 | Forecast |  | 3.4 | 1.7
2023-05-01 | 367 | Forecast |  | 3.4 | 1.4
2023-08-01 | 367 | Forecast |  | 3.4 | 0
2023-11-01 | 370 | Forecast |  | 3.9 | 0.8
2024-02-01 | 377 | Forecast |  | 4.1 | 1.9
2024-05-01 | 382 | Forecast |  | 4.1 | 1.3
2024-08-01 | 382 | Forecast |  | 4.1 | 0
2024-11-01 | 385 | Forecast |  | 4.1 | 0.8
2025-02-01 | 392 | Forecast |  | 4 | 1.8
2025-05-01 | 397 | Forecast |  | 3.9 | 1.3
2025-08-01 | 397 | Forecast |  | 3.9 | 0
2025-11-01 | 400 | Forecast |  | 3.9 | 0.8
2026-02-01 | 407 | Forecast |  | 3.8 | 1.8
2026-05-01 | 412 | Forecast |  | 3.8 | 1.2
2026-08-01 | 412 | Forecast |  | 3.8 | 0