## PERT
Earliest Possible Start | Duration | Earliest Possible Finish
Activity
Latest Possible Start | Float | Latest Possible Finish
ES | Duration | EF
Activity
LS | Float | LF
[9 empty] | 60 | 60 | 120
C
[9 empty] | 80 | 20 | 140
|  |  | 0 | 30 | 30 | 30 | 30 | 60
|  |  | A |  |  | B | [11 empty] | 140 | 10 | 150 | 150 | 10 | 160 | 160 | 60 | 220 | 220 | 30 | 250
|  |  | 0 | 0 | 30 | 30 | 0 | 60 | [9 empty] | G |  |  | H |  |  | I |  |  | J
[9 empty] | 60 | 10 | 70 | 70 | 60 | 130 | 130 | 10 | 140 | 140 | 0 | 150 | 150 | 0 | 160 | 160 | 0 | 220 | 220 | 0 | 250
[9 empty] | D |  |  | E |  |  | F
[9 empty] | 60 | 0 | 70 | 70 | 0 | 130 | 130 | 0 | 140

## Analysis
|  | Preceding Activities | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | Critical Path? |  |  | Expected Time
A | Set up the 3 wet and dry stations, retrieve 3 tables from the Galley, get the coveralls from Stores, and prepare the food and drinks |  | 20 | 30 | 40 | 30 | 11.1111 | Y
B | Lead troops to the stations and brief them, afterwards, they change out of their dirty uniforms to clean coveralls | A | 20 | 30 | 40 | 30 | 11.1111 | Y
C | Troops to eat, drink and rest | B | 50 | 60 | 70 | 60 | 11.1111 | N |  |  | Variance
D | Dirty uniform transferred from Hangar to Laundryroom | B | 10 | 10 | 20 | 11.6667 | 2.7778 | Y
E | Washing and drying process | D | 50 | 60 | 70 | 60 | 11.1111 | Y
F | Clean uniform transferred from Laundryroom to Hangar | E | 10 | 10 | 20 | 11.6667 | 2.7778 | Y
G | Troops change to clean uniform, dirty coveralls to be placed to one side, to be cleaned once the Project has finished. Clean wet and dry stations to prepare for the next cycle - Repeat until completion of Project | C & F | 10 | 10 | 20 | 11.6667 | 2.7778 | Y |  |  | Project Variance (PV)
H | Dirty coveralls transferred from Hangar to Laundry room | G | 10 | 10 | 20 | 11.6667 | 2.7778 | Y |  |  | The sum of the Critical Path Variance(s)
I | Washing and drying process | H | 50 | 60 | 70 | 60 | 11.1111 | Y
J | Clean coveralls transferred from Laundry room to Stores, move tables back to the Galley, and clean Hangar | I | 20 | 30 | 40 | 30 | 11.1111 | Y |  |  | Project Standard deviation
|  |  | Optimistic | Most Likely | Pessimistic
|  |  | 200 | 250 | 340
|  |  |  | Project Variance |  |  | 66.6667
|  |  |  | Project Standard Deviation |  |  | 8.165
|  |  |  | Complete by minutes: | Z score | probability of completion | % chance of completion
|  |  |  | 260 | 1.2247 | 0.88966 | 88.97%
|  |  |  | 280 | 3.6742 | 0.99988 | 99.99%
[9 empty] | Z | 0 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09
|  |  |  | Total estimated time: 4 hours 40 minutes |  |  |  |  | 0 | 0.5 | 0.50399 | 0.50798 | 0.51197 | 0.51595 | 0.51994 | 0.52392 | 0.5279 | 0.53188 | 0.53586
[9 empty] | 0.1 | 0.53983 | 0.5438 | 0.54776 | 0.55172 | 0.55567 | 0.55962 | 0.56356 | 0.56749 | 0.57142 | 0.57535
[9 empty] | 0.2 | 0.57926 | 0.58317 | 0.58706 | 0.59095 | 0.59483 | 0.59871 | 0.60257 | 0.60642 | 0.61026 | 0.61409
[9 empty] | 0.3 | 0.61791 | 0.62172 | 0.62552 | 0.6293 | 0.63307 | 0.63683 | 0.64058 | 0.64431 | 0.64803 | 0.65173
[9 empty] | 0.4 | 0.65542 | 0.6591 | 0.66276 | 0.6664 | 0.67003 | 0.67364 | 0.67724 | 0.68082 | 0.68439 | 0.68793
[9 empty] | 0.5 | 0.69146 | 0.69497 | 0.69847 | 0.70194 | 0.7054 | 0.70884 | 0.71226 | 0.71566 | 0.71904 | 0.7224
[9 empty] | 0.6 | 0.72575 | 0.72907 | 0.73237 | 0.73565 | 0.73891 | 0.74215 | 0.74537 | 0.74857 | 0.75175 | 0.7549
[9 empty] | 0.7 | 0.75804 | 0.76115 | 0.76424 | 0.7673 | 0.77035 | 0.77337 | 0.77637 | 0.77935 | 0.7823 | 0.78524
[9 empty] | 0.8 | 0.78814 | 0.79103 | 0.79389 | 0.79673 | 0.79955 | 0.80234 | 0.80511 | 0.80785 | 0.81057 | 0.81327
[9 empty] | 0.9 | 0.81594 | 0.81859 | 0.82121 | 0.82381 | 0.82639 | 0.82894 | 0.83147 | 0.83398 | 0.83646 | 0.83891
[9 empty] | 1 | 0.84134 | 0.84375 | 0.84614 | 0.84849 | 0.85083 | 0.85314 | 0.85543 | 0.85769 | 0.85993 | 0.86214
[9 empty] | 1.1 | 0.86433 | 0.8665 | 0.86864 | 0.87076 | 0.87286 | 0.87493 | 0.87698 | 0.879 | 0.881 | 0.88298
[9 empty] | 1.2 | 0.88493 | 0.88686 | 0.88877 | 0.89065 | 0.89251 | 0.89435 | 0.89617 | 0.89796 | 0.89973 | 0.90147
[9 empty] | 1.3 | 0.9032 | 0.9049 | 0.90658 | 0.90824 | 0.90988 | 0.91149 | 0.91309 | 0.91466 | 0.91621 | 0.91774
[9 empty] | 1.4 | 0.91924 | 0.92073 | 0.9222 | 0.92364 | 0.92507 | 0.92647 | 0.92785 | 0.92922 | 0.93056 | 0.93189
[9 empty] | 1.5 | 0.93319 | 0.93448 | 0.93574 | 0.93699 | 0.93822 | 0.93943 | 0.94062 | 0.94179 | 0.94295 | 0.94408
[9 empty] | 1.6 | 0.9452 | 0.9463 | 0.94738 | 0.94845 | 0.9495 | 0.95053 | 0.95154 | 0.95254 | 0.95352 | 0.95449
[9 empty] | 1.7 | 0.95543 | 0.95637 | 0.95728 | 0.95818 | 0.95907 | 0.95994 | 0.9608 | 0.96164 | 0.96246 | 0.96327
[9 empty] | 1.8 | 0.96407 | 0.96485 | 0.96562 | 0.96638 | 0.96712 | 0.96784 | 0.96856 | 0.96926 | 0.96995 | 0.97062
[9 empty] | 1.9 | 0.97128 | 0.97193 | 0.97257 | 0.9732 | 0.97381 | 0.97441 | 0.975 | 0.97558 | 0.97615 | 0.9767
[9 empty] | 2 | 0.97725 | 0.97778 | 0.97831 | 0.97882 | 0.97932 | 0.97982 | 0.9803 | 0.98077 | 0.98124 | 0.98169
[9 empty] | 2.1 | 0.98214 | 0.98257 | 0.983 | 0.98341 | 0.98382 | 0.98422 | 0.98461 | 0.985 | 0.98537 | 0.98574
[9 empty] | 2.2 | 0.9861 | 0.98645 | 0.98679 | 0.98713 | 0.98745 | 0.98778 | 0.98809 | 0.9884 | 0.9887 | 0.98899
[9 empty] | 2.3 | 0.98928 | 0.98956 | 0.98983 | 0.9901 | 0.99036 | 0.99061 | 0.99086 | 0.99111 | 0.99134 | 0.99158
[9 empty] | 2.4 | 0.9918 | 0.99202 | 0.99224 | 0.99245 | 0.99266 | 0.99286 | 0.99305 | 0.99324 | 0.99343 | 0.99361
[9 empty] | 2.5 | 0.99379 | 0.99396 | 0.99413 | 0.9943 | 0.99446 | 0.99461 | 0.99477 | 0.99492 | 0.99506 | 0.9952
[9 empty] | 2.6 | 0.99534 | 0.99547 | 0.9956 | 0.99573 | 0.99585 | 0.99598 | 0.99609 | 0.99621 | 0.99632 | 0.99643
[9 empty] | 2.7 | 0.99653 | 0.99664 | 0.99674 | 0.99683 | 0.99693 | 0.99702 | 0.99711 | 0.9972 | 0.99728 | 0.99736
[9 empty] | 2.8 | 0.99744 | 0.99752 | 0.9976 | 0.99767 | 0.99774 | 0.99781 | 0.99788 | 0.99795 | 0.99801 | 0.99807
[9 empty] | 2.9 | 0.99813 | 0.99819 | 0.99825 | 0.99831 | 0.99836 | 0.99841 | 0.99846 | 0.99851 | 0.99856 | 0.99861

## Sheet3
|  | Preceding Activities | Optimistic | Most Likely | Pessimistic | Expected Time | Variance | Critical Path?
A | Design Survey |  | 9 | 10 | 11
B | Print questionnaire | A | 13 | 14 | 15
C | Engage interviewers | A | 4 | 5 | 6
D | Prepare interviewer instruction sheets etc | A | 6 | 7 | 8
E | Set up computer database | A | 7 | 8 | 9
F | Brief interviewers | C & D | 1 | 1 | 2
G | Test computer database | E | 1 | 2 | 3
H | Supervise fieldwork | B & F | 4 | 5 | 6
I | Analyse results | G & H | 12 | 13 | 14
J | Prepare report | I | 11 | 12 | 13
|  |  | Optimistic | Most Likely | Pessimistic
| Overall |  | 68 | 77 | 87
| On Critical Path |  | 49 | 54 | 59
|  |  |  | Project Variance |  |  | 0
|  |  |  | Project Standard Deviation |  |  | 0
|  |  |  | Complete by week: | Z score | probability of completion | % chance of completion
53
55