## M.E.S.S Queries
Stage Coach Theartre
M.E.S.S Construction Services Ltd - Query Tracker
Ref: | Element | Query / Description: | Date Raised: | Date Responded: | Response: | M.E.S.S Construction Services Ltd Review | Status
1 | Design | What RIBA Stages will / have the designs been developed up too? Further to this, are the design team going to be novated over or is this going to remain more of a traditional approach? |  |  | The designs will be taken up to RIBA 2, and the design team will remain with the client | Noted | Resolved
2 | Design | Who will be the Principal Designer on the scheme, is this part of your design teams comission? Likewise, MEP? |  |  | As above | Noted | Resolved
3 | Funding | Noting the funding is a 60/40 arrangement between yourselves and Welsh Government, is there a spend date on the WG funding? |  |  | No known spend date | Noted, if fund date becomes applicable can reflect in cash flow to make sure this element is spent first | Resolved
4 | Budget | Is there an indicative scheme budget? |  |  | No budget | Noted, budget estimate to be produced as part of feasibility report | Resolved
5 | Cost/Quality/Time Model | What is the clients aspirations in terms of cost, quality and time? |  |  | All considerations however, this will be a landmark building so quality would become apparent | Noted, consideration to be made | Resolved
6 | Funding | Are there any Welsh Government deliverables as part of the funding? |  |  |  |  | Open
7 | Masterplan | The current proposal provided by the client has an impact on the overall masterplan, we have costed this as per the current design - client to confirm that current proposal is acceptable? |  |  |  |  | Open
8 | Design | Currently proposal to landscape an area outside of the building area, this will give the client a landscaped area and also a additional car park, client to confirm this is acceptable? Option to VE out, two options will be proposed as part of feasbility report |  |  |  |  | Open