## Sheet1
Month | Week | Task / blocks | Holidays | Colour Code
Sep / Oct | 29th - 5th |  |  | Block on
| 6th - 12th | Plan, bibliography, gantt chart submission (11th) |  | Prep Week
| 13th - 19th | Prep Week |  | Holiday from University
| 20th - 26th | Block 2 |  | Block off
Oct / Nov | 27th - 2nd
3rd - 9th
10th - 16th
| 17th - 23rd | Prep Week / Finish defining terms
| 24th - 30th | Block 3
Dec | 1st - 7th
| 8th - 14th | Section 1 reading complete - start writing
| 15th - 21st |  | Christmas (20th Dec - 5th Jan)
| 22nd - 28th | Section 1 writing
Dec / Jan | 29th - 4th | Start preparing presentation
| 5th - 11th | Block 4
12th - 18th
19th - 25th
Jan / Feb | 26th - 1st
| 2nd - 8th | Prep Week - Presentation to be submitted (3rd)
| 9th - 15th | Block 5
| 16th - 22nd | Section 2 complete - to be approved by supervisor
23rd - 29th
Mar | 1st - 7th | Section 3 complete - to be approved by supervisor
| 8th - 14th | Prep Week
| 15th - 21st | Block 6
22nd - 28th
Mar / Apr | 29th - 4th
| 5th - 11th | Finalising introduction and conclusion | Easter (10th Arp - 11th May)
| 12th - 18th | Final Proof Reading and Conslutations
| 19th - 25th | Get dissertation printed and bound
Apr / May | 26th - 2nd | Dissertation Deadline (1st)