# LCDB7007 Pilot Study Assignment Schedule

Comprehensive Timeline and Task Breakdown for DBA Students

KEY PRINCIPLE: The work does not follow the linear order of the final report structure. Instead, you'll work iteratively, developing multiple components simultaneously whilst building towards your final submission.

Everything connects: your topic, research questions, literature, theoretical framework, ethics, interview questions, and findings must align coherently.

## PHASE 1: Foundation and Ethics (Weeks 1-5)

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 1 | TOPIC SELECTION AND INITIAL FRAMING |  |  |
|  | Decide your research topic (may be same as Semester 1 or new focus) |  |  |
|  | Formulate preliminary research aim (one overarching statement) |  |  |
|  | Draft initial research questions (2-3 open, exploratory, qualitative questions) |  |  |
|  | Begin literature scoping (find 10-15 key papers in your area) |  |  |
|  | DELIVERABLE: One-page document with topic, aim, and research questions for supervisor review |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 2 | ETHICS APPLICATION - FIRST DRAFT |  |  |
|  | Complete first draft of PG2 Ethics Form (all sections) |  |  |
|  | Draft Participant Information Sheet (PIS) in accessible language |  |  |
|  | Draft Consent Form with clear statements |  |  |
|  | Describe participant recruitment strategy |  |  |
|  | Detail data storage, anonymisation, and confidentiality procedures |  |  |
|  | DELIVERABLE: Complete first drafts of PG2, PIS, and Consent Form submitted to module lead and supervisor |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 3 | ETHICS REVISION - FIRST ITERATION |  |  |
|  | Review feedback from module lead/supervisor carefully |  |  |
|  | Revise all ethics documents addressing every point of feedback |  |  |
|  | Ensure consistency across PG2, PIS, and Consent Form |  |  |
|  | Refine research questions based on ethics review |  |  |
|  | Submit revised version with track changes |  |  |
|  | DELIVERABLE: Second draft of ethics materials submitted |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 4 | ETHICS REVISION - SECOND ITERATION & THEORETICAL FRAMEWORK |  |  |
|  | Further revise ethics documents addressing remaining feedback |  |  |
|  | Polish language and clarity; ensure all procedural details complete |  |  |
|  | Identify 2-3 relevant theories for your topic |  |  |
|  | Read key theoretical texts (not just how others applied them) |  |  |
|  | Map theory to research questions (preliminary) |  |  |
|  | DELIVERABLE: Final ethics documents ready for approval; theoretical framework outline (500 words) |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 5 | ETHICS FINALISATION & INTERVIEW DESIGN BEGIN |  |  |
|  | Submit for formal university ethics approval |  |  |
|  | Begin interview question development (8-12 initial questions) |  |  |
|  | Think about sequence: opening → core → theory-testing → closing |  |  |
|  | Start justification for each question (why asking? what will answer tell you?) |  |  |
|  | DELIVERABLE: Ethics approval pending; initial interview schedule draft ⚠️ STOP POINT: Cannot collect data until ethics approval granted. Use waiting time for literature review. |  |  |

## PHASE 2: Literature Review Development (Weeks 6-9)

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 6 | LITERATURE REVIEW FOUNDATIONS Context: Writing critical literature review at doctoral level is NOT a summary. It is critical analysis that synthesises sources, identifies debates, evaluates methods, and builds argument towards your research gap. |  |  |
|  | Expand literature collection (aim for 30-40 sources minimum) |  |  |
|  | Include seminal works and recent publications (last 5 years) |  |  |
|  | Create literature map/matrix (Author/Year, Key Argument, Methodology, Findings, Relevance, Strengths/Limitations) |  |  |
|  | Identify themes emerging from literature |  |  |
|  | DELIVERABLE: Literature matrix with 25-30 sources organised thematically |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 7 | LITERATURE REVIEW - FIRST WRITING PHASE Critical writing: Organise by themes (not author-by-author), compare perspectives, evaluate evidence, show development of ideas, synthesise multiple sources per paragraph. |  |  |
|  | Write first 1,000 words focusing on one or two major themes |  |  |
|  | Practice synthesising multiple sources in each paragraph |  |  |
|  | Use transitional phrases: 'However...', 'In contrast...', 'Building on this...' |  |  |
|  | Develop your critical voice: evaluate, don't just report |  |  |
|  | Submit to supervisor for feedback on critical approach |  |  |
|  | DELIVERABLE: First 1,000 words of literature review demonstrating critical synthesis |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 8 | LITERATURE REVIEW - SECOND WRITING PHASE |  |  |
|  | Review supervisor feedback carefully (understand what 'critical' means) |  |  |
|  | Revise initial section: deepen critical engagement, strengthen synthesis |  |  |
|  | Write next 1,000 words continuing thematic structure |  |  |
|  | Refine theoretical framework section with detailed explanation of each theory |  |  |
|  | Show how theories complement each other and connect to research context |  |  |
|  | DELIVERABLE: 2,000 words of literature review including theoretical framework |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 9 | LITERATURE REVIEW - COMPLETION |  |  |
|  | Write final 500 words: synthesise key debates and articulate research gap |  |  |
|  | Show how your study addresses this gap |  |  |
|  | Polish entire literature review (2,500 words total) |  |  |
|  | Ensure logical flow, check every paragraph synthesises (not lists) |  |  |
|  | Verify UK English spelling throughout |  |  |
|  | Write methodology justification (why qualitative? why this methodology fits?) |  |  |
|  | DELIVERABLE: Complete literature review (2,500 words) demonstrating doctoral-level critical engagement |  |  |

## PHASE 3: Interview Design Completion (Week 10)

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 10 | INTERVIEW QUESTIONS AND JUSTIFICATION By now you should have ethics approval. If not yet approved, continue refining literature whilst waiting. |  |  |
|  | Finalise interview questions (10-15 questions with careful sequencing) |  |  |
|  | Some questions must test/explore your theoretical framework |  |  |
|  | Create comprehensive justification table: Purpose ¦ RQ Link ¦ Theoretical Connection ¦ Position Rationale |  |  |
|  | Identify which questions directly test theoretical framework |  |  |
|  | Prepare interview protocol document (opening script, questions with prompts, closing script) |  |  |
|  | DELIVERABLE: Complete interview schedule with comprehensive justification table (3-4 pages) |  |  |

## PHASE 4: Data Collection and Analysis (Weeks 11-13)

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 11 | PILOT INTERVIEWS BEGIN |  |  |
|  | Recruit participants (3-5 people); send PIS in advance (48 hours before) |  |  |
|  | Obtain signed consent forms before interviews begin |  |  |
|  | Conduct first pilot interview (45-60 minutes) |  |  |
|  | Practice active listening and probing techniques |  |  |
|  | Record with participant permission; take detailed field notes immediately after |  |  |
|  | Review and adapt interview schedule based on what worked/didn't work |  |  |
|  | Begin transcription of first interview (verbatim) |  |  |
|  | DELIVERABLE: First interview completed, transcribed, and schedule adapted based on learning |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 12 | COMPLETE DATA COLLECTION AND BEGIN ANALYSIS |  |  |
|  | Conduct remaining interviews (2-4 more); continue detailed field notes |  |  |
|  | Complete all transcriptions (verbatim; include translated transcripts if needed) |  |  |
|  | Note non-verbal cues in square brackets [laughs], [long pause] |  |  |
|  | Choose analytical approach (thematic analysis? IPA? framework analysis?) |  |  |
|  | Must align with philosophical positioning in methodology |  |  |
|  | Begin initial coding: read all transcripts multiple times (immersion) |  |  |
|  | Start coding one transcript in detail (line-by-line or meaning unit coding) |  |  |
|  | DELIVERABLE: All interviews completed and transcribed; coding begun |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 13 | COMPLETE ANALYSIS |  |  |
|  | Complete coding across all transcripts; develop codebook |  |  |
|  | Create one fully coded transcript for appendix |  |  |
|  | Identify themes/patterns: group related codes, look for patterns across transcripts |  |  |
|  | Check themes answer your research questions |  |  |
|  | Connect findings to theoretical framework (support, challenge, extend?) |  |  |
|  | Map themes to theoretical concepts |  |  |
|  | Select illustrative quotes (powerful, clear, anonymised) |  |  |
|  | DELIVERABLE: Complete analysis with themes, coded transcript for appendix, theme-to-theory map |  |  |

## PHASE 5: Article Writing (Weeks 14-16)

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 14 | JOURNAL SELECTION AND METHODOLOGY SECTION |  |  |
|  | Research appropriate journals that publish pilot studies and qualitative methodology |  |  |
|  | Review journal scope, aims, and recent articles |  |  |
|  | Select target journal; note impact factor, acceptance rate |  |  |
|  | Review author guidelines in detail |  |  |
|  | Write journal justification (100 words) |  |  |
|  | Write Methodology section (1,750 words): paradigm, design, participants, data collection, analytical approach, ethics, quality criteria, reflexivity, limitations |  |  |
|  | DELIVERABLE: Part A (journal selection) completed; Methodology section drafted |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 15 | CORE ARTICLE SECTIONS |  |  |
|  | Write Introduction (500 words): hook, background, research gap |  |  |
|  | Write Aims, Objectives, Research Questions (300 words) |  |  |
|  | Write Findings section (1,750 words): present 3-5 themes systematically with analytical description, supporting quotes, connection to RQs, preliminary theoretical interpretation |  |  |
|  | Write Conclusion (750 words): summary, contribution to knowledge, practical implications, limitations, recommendations for full-scale study, future research |  |  |
|  | DELIVERABLE: Introduction, Aims/Objectives/Questions, Findings, and Conclusion sections completed |  |  |

| Week | Tasks and Deliverables | Done ✓ | Notes |
| --- | --- | --- | --- |
| 16 | FINALISATION AND SUBMISSION |  |  |
|  | Write Abstract (150 words): purpose, methods, key findings, implications |  |  |
|  | Write Reflective Commentary (500 words): learnings, module resonance, skills development, ethical challenges, growth as researcher |  |  |
|  | Prepare appendices: raw transcript, translated transcript (if applicable), coded transcript, interview schedule, PIS, consent form |  |  |
|  | Format and proofread: check citations, UK English spelling, word counts, academic tone, tables/figures, reference list |  |  |
|  | Final alignment check: RQs → interview questions → findings → conclusions; theoretical connections clear throughout |  |  |
|  | Upload approved ethics documents (PG2, PIS, Consent) |  |  |
|  | Compile final submission: Part A (journal), Part B (article), Part C (reflection), Appendices |  |  |
|  | DELIVERABLE: COMPLETE ASSIGNMENT UPLOADED TO MOODLE |  |  |

## CRITICAL ALIGNMENT CHECKS

Review these alignments every 2 weeks to ensure coherence across your work:

| Alignment | Check This | Done ✓ | Notes |
| --- | --- | --- | --- |
|  | Research questions → Interview questions (every interview question must connect) |  |  |
|  | Theoretical framework → Interview questions (some questions must test theory) |  |  |
|  | Research questions → Findings (findings must answer RQs) |  |  |
|  | Theoretical framework → Analysis and discussion (theory should illuminate findings) |  |  |
|  | Literature gap → Your study's contribution (gap must justify study) |  |  |
|  | Methodology → Analytical approach (approach must suit methodology/paradigm) |  |  |
|  | Aims → Conclusions (conclusions must address original aims) |  |  |

## QUALITY STANDARDS FOR LEVEL 8 WORK

| Standard | What This Means | Done ✓ | Notes |
| --- | --- | --- | --- |
|  | Methodological rigour: Systematic, transparent, well-justified decisions at every stage |  |  |
|  | Critical engagement: Questioning assumptions, evaluating evidence, acknowledging limitations honestly |  |  |
|  | Theoretical sophistication: Clear framework thoughtfully applied, not superficially mentioned |  |  |
|  | Analytical depth: Moving beyond description to interpretation, explanation, and theorisation |  |  |
|  | Ethical sensitivity: Demonstrating genuine care for participants and reflexive practice |  |  |
|  | Scholarly voice: Clear, precise, academically appropriate, avoiding colloquialisms |  |  |
|  | Original contribution: Generating new insights that advance knowledge (even if preliminary) |  |  |
|  | Reflexivity: Awareness of researcher influence and positionality throughout |  |  |

## COMMON PITFALLS TO AVOID

| Pitfall | Why It's a Problem / What to Do Instead | Done ✓ | Notes |
| --- | --- | --- | --- |
|  | ❌ Collecting data before ethics approval granted (serious violation) |  |  |
|  | ❌ Interview questions that can be answered yes/no (generates poor data) → Use open questions: 'How...?', 'Can you describe...?' |  |  |
|  | ❌ Literature review that lists studies without critical synthesis (descriptive, not analytical) → Synthesise, compare, evaluate in each paragraph |  |  |
|  | ❌ Literature review organised author-by-author (not thematic) → Organise by themes/concepts, not chronologically by author |  |  |
|  | ❌ Findings that only quote participants without analysis (journalism, not research) → Analyse what quotes mean, connect to theory |  |  |
|  | ❌ Weak connections between theories and interview questions (theory not integrated) → Ensure some questions directly test theoretical concepts |  |  |
|  | ❌ Methodology describing what you did but not why (lacks justification) → Justify every methodological choice |  |  |
|  | ❌ Using American spelling (analyze, behavior, organization) → Use UK English: analyse, behaviour, organisation |  |  |
|  | ❌ Forgetting to upload approved ethics documents to Moodle (incomplete submission) |  |  |
|  | ❌ Not seeking supervisor feedback during literature review development (missing crucial guidance) |  |  |

## THIS IS DOCTORAL-LEVEL RESEARCH

This is challenging work. The 16-week schedule is intensive and requires consistent effort, intellectual curiosity, methodological care, reflexive practice, and resilience.

Be patient with yourself as you develop doctoral-level skills. Seek feedback early and often.

You are doing doctoral-level research. You can do this.