## Data Entry
Process Function | Potential Failure Mode | Potential Effect(s) of Failure | Sev | Potential Cause(s)/ Mechanism(s) of Failure | Occur | Current Process Controls | Detec | RPN | Recommended Action(s) | Responsibility | Action Results
[11 empty] | Actions Taken | Sev | Occ | Det | RPN
Condition test assets | no grease in the friction fan bearing | bearing failure through wear and tear | 5 | technician forgot to grease | 6 | none | 10 | 300 | 2 man checking system, or quality control | technician and manager | 2 man checking system written into the process | 5 | 2 | 2 | 20
|  |  | 5 | run out of grease | 2 | purchasing | 4 | 40 | provide better access to grease or get longer lasting grease | storeman | better stocks of grease | 5 | 2 | 2 | 20
|  |  | 5 | didn’t know it needed greasing | 7 | training ineffective | 9 | 315 | rewrite process of maintenance | maintenance manager | process re written and review by multiple members from the test and maintenance teams | 5 | 1 | 2 | 10
| not enough grease in the friction fan bearing | overheating of the bearing causing failure | 5 | carelessness | 6 | training/management | 6 | 180 | put on an action pan and retrain | technicians manager | technician was retrained and made aware of the importance of his work | 5 | 1 | 2 | 10
| delayed maintenance | bearing failure through age | 5 | state of the bearing wasn’t known | 5 | inspection | 5 | 125 | process written for inspection | maintenance manager | inspection process was written | 5 | 4 | 3 | 60
|  |  | 5 | focused too much on output for customer | 6 | planning | 6 | 180 | better communication: explaining the situation to the customer and the risks/cost involved | project manager | customers now understand the importance of maintenance | 5 | 3 | 2 | 30
| defect on the bearing | bearing failure | 5 | bearing not checked before installation | 6 | none | 10 | 300 | qualifty control of new purchases before installation | storeman | all new items are checked and certification of quality is required from the manufacturer | 5 | 2 | 2 | 20
|  |  | 5 | bearing not checked when maintained | 5 | training ineffective | 7 | 175 | rewrite process of maintenance | maintenance manager | inspection process was written | 5 | 4 | 2 | 40
| fault code on machine wasn’t known | bearing failure after wearing | 5 | lack of training | 6 | none | 10 | 300 | training on fault codes | maintenance manager | full attendance for the training on fault codes | 5 | 3 | 3 | 45
| heating in the plant room containing the conditioning unit had failed | bearing failure from higher work rate | 5 | delay to repair/replace heater | 4 | tiered system with safety dependant jobs at the top | 4 | 80 | better communication with test team | maintenance manager | test team leader and maintenance manager have set up weekly communication | 5 | 4 | 2 | 40
| machine running at peak capacity | bearing failure from higher work rate | 5 | test engineer lack of training | 7 | training | 5 | 175 | training to include max operatng temperatures | test team leader | test team leader trained his team on max operating temperatures | 5 | 3 | 3 | 45
FAILURE MODE AND EFFECTS ANALYSIS
Item: | Fixed Conditioning Unit |  |  | Responsibility: |  | Facility Manager |  |  |  | FMEA number: | 1
Model: | Clive Hurley 1 |  |  | Prepared by: |  | JTyrrell |  |  |  | Page : | N/A
Core Team: | Maintenance, Planning, Test and Stores Teams | [8 empty] | FMEA Date (Orig): | 2018-01-14 | Rev: |  | in 1 year

## About This Template
This template was written for the American Society for Quality by
Stat Aids
Your feedback is welcome and encouraged. Please e-mail to:
Stat_Aids@yahoo.com