Sean Dugay

P149833

Assignment 2

Contract Practice & Procedures

M5X01878

Administration within contracts

Lara Hopkinson

Contents

Contract Administrator	1

Contract Administrator Authority	1

Process of variation	2

The Contract administration Process	3

References	4

Scenario 1 - There is a significant variation within the contract that impacts on the delivery timeframe of the project and cost.

# Contract Administrator

The Contract administrator is usually appointed by the client from a consultancy agency and will act as the main point of contact for the contractor.  One of the primary duties of the contract administrator to issue instructions of any variations throughout the contracts. A variation is a change to the contract this can be a change to the scope of works, change to quantities, quality or programme. “On a construction management contract, the role of contract administrator might be attributed to the construction manager” (Designing Buildings Wiki, 2019). Variations are also known as change orders, variation instructions but are more commonly called variation orders (VO’s). The contract administrator may receive requests for variation orders from the client, site managers, architects, quantity surveyors, engineers and other senior staff. Throughout most construction projects there are a number of variation orders most of them are small alterations, for example a change of roof tile quantities or material prior to installation. These small alterations may slightly change the price but are unlikely to effect the construction programme. Larger variations can drastically change a projects programme, cost and quality for example a change to the foundation design after the foundations have been put in, this would delay the programme significantly with added costs.

# Contract Administrator Authority

The Contract administrator’s authority is limited and defined under subheading 11 of the RICS Standard Form of Consultant’s Appointment (England and Wales)

“The Consultant has no authority to do any of the following on the Client’s behalf without the Client’s prior written consent:

- Vary the agreed design or specification of work or materials or their quality or quantity from that described in the Building Contract;

- Subject to any greater limit of expenditure stated in the Appendix, issue any instruction or notice under the Building Contract or any Client Contract that either delays completion of the Project or increases the cost of the Project (per item or in the aggregate); or

- Terminate the Building Contract or any Client Contract or the appointment of any other member of the Professional Team, agree any amendment of their contract terms or waive compliance by the Contractor or any party to any Client Contract or any other member of the Professional Team with their respective obligations.” (RICS, 2018).

Under these conditions the contract administrator cannot approve all variations without the clients express consent. However under clause 11.2 of the RICS Standard Form of Consultant’s Appointment the contract administrator may approve variations without the clients consent provided the variation will prevent danger to any persons on or around the site or to the materials on site.

“In the event of an emergency, the Consultant has authority to issue any instruction reasonably required to prevent danger to persons on or adjacent to the Site or material damage to the Project. The Consultant promptly notifies the Client of any such instruction and of its cost implications and effect on the Programme” (RICS, 2018).

If the contract administrator approves a variation without the clients consent or authority then the contract administrator is in breach of their contract with the client and is liable to any extra costs incurred to the client by the contractor. In most cased amicable resolution can be found between the parties however there are cases that are taken to the courts, William Clark Partnership Ltd v Dock St PCT Ltd (2015).

Under clause 16 of most NEC contracts is clearly defines that an early warning notice must be issued if any party becomes of aware of an event that may;

- Delay the timeframe of completion

- Increase the cost of the project

- Impair the performance of works

- Change a key meeting date

Under this clause a EWN (Early Warning Notice) should be provided prior to the variation stage.

# Process of variation

- Identification of the need of a variation

During this step the need for a variation is identified this could be a way to save money or a problem that has been overlooked.

- Identification of the resolution

In this step a resolution to the problem is identified which will become the variation.

- Write up of variation including impact and value

Variation orders will typically include the following; Submission date, variation order number, description, cost, extra time request. Valuing a variation is typically done by the quantity surveyor but can also be done by an Estimator, Cost Consultant or through quotations.

- Submission of the variation to the contract administrator

This is where the variation order is submitted to the contract administrator.

- Meeting to discuss variation

Clients/Contract Administrators generally like to meet in person to discuss larger variation, smaller ones can be resolved over email or telephone.

- Approval of variation

Client approves the variation and the Contract Administrator actions the variation.

- Implementation of variation

Programme, bill of quantities, cost are amended.

- Continuation of works

Once the programme has been amended and reissued then works can resume with each person on site having clear instructions to follow.

If the need for a variation is of nobody’s fault this will become a compensation event and should be found under clause 60.1 of the standard NEC contract. A compensation event will allow the appropriate amendments to be made to the programme.

# The Contract administration Process

Typically the contract administrator will receive a variation order, this may be from the client or contractor. A compensation event notification (Early Warning Notice) will come from the contractor directly to the contract administrator.

The contract administrator may say “no” if the event is not detailed under clause 60.1. Usually they will request a quotation for the works required.  The contractors in most cases has 3 weeks to submit a quotation.

The contract administrator will then take it into consideration and discuss it with the client if required.

Dependent on the size and impact of the variation a meeting may be held. During the meeting the contractor, contract administrator and sometimes the client will all be present to discuss the following questions;

- Why is there a need for the variation?

- Why was this not foreseen prior to the commencement of work?

- Who is liable to receive the costs?

- Is there anything else that can be done?

- Will the implementation of the variation cause further issues?

They will also discuss;

- Any disputes that may arise

- Progression of work

The contract administrator is always present at these meetings as they are required to know of any changes to the schedule of works or amendments to the contract.

Once the meeting has been concluded the Contract Administrator is to action the variation if approved by the client. If the variation is declined then it is up to the contractor to find a different solution to the problem that will satisfy the contract administrator and the client.

A substantial variation that has a negative effect on the contract sum and programme will require amendment to the contracts programme and cost.  As the programme is a key part of an NEC contracts and is legally binding then it is the programme that is updated.

Programme is key to NEC and is contractually obligating

“It is important to recognise the distinction between the accepted programme regime, found in clauses 31 and 32, and the procedure for adjusting the completion date under the compensation event machinery in clause 60.” (BURTON, 2018).

# References

BURTON, A., 2018. Additional time in ECC – a practical approach. [Online] 
Available at: https://www.neccontract.com/About-NEC/News-Media/Additional-time-in-ECC-%E2%80%93-a-practical-approach
[Accessed 16 07 2019].

Designing Buildings Wiki, 2019. Contract administrator for construction contracts. [Online] 
Available at: https://www.designingbuildings.co.uk/wiki/Contract_administrator_for_construction_contracts
[Accessed 15 07 2019].

RICS, 2018. consultations. [Online] 
Available at: https://consultations.rics.org/gf2.ti/f/929794/37080357.1/PDF/-/1_RICS_Standard_Form_of_Consultants_Appointment.pdf
[Accessed 16 07 2019].