| Student Name: | Rajwinder Kaur |  |  |
| --- | --- | --- | --- |
| Student ID: | 2214604 |  |  |
| Programme: | BA (Hons) Business Management |  |  |
| Module: | Project Management |  |  |
| Module code: | LCBB6006 | ## Submission Date | 17 October 2025 |
| Lecturer: | Dr Said Usman | Internal Verifier: | Dr Anupam Mazumdar |
| Assignment Title: | Component 1: Coursework: Essay | Word count (or equivalent): | 2072 |

Contents Page

Introduction …………………………………………………………………………….. 3

- Company overview

- Market context and problem statement

- Selected project and rationale

Project Definition ………………………………………………………………………… 4

- Project Aim

- SMART objectives (month 3 and month 12)

- Scope in and scope out

- Benefits and success criteria

Theoretical Frame……………………………………………………………………………5

- PRINCE2-7 governance (people, sustainability, stages)

- Resource-Based View strategy and implications

Project Outputs (Deliverables and Direct Results) ……………………………………… 5

Activities Required to Deliver the Outputs …………………………………………….. 6

Work Breakdown Structure ………………………………………………………… 8

Dependency chart ………………………………………………………………………… 9

Milestones by month ……………………………………………………………….. 9

Stakeholders and Governance …………………………………………………………  10

Resources & Cost Management …………………………………………………. 10

- Roles and effort summary (who, when)

- Cost Accounts

Run-Up, Handover & Benefits …………………………………………………………… 12

References …………………………………………………………………………………. 13

Appendices ………………………………………………………………………………… 15

Introduction

Company: Alex Gooch Artisan Baker is a Welsh, plant-based artisan bakery known for long-fermentation sourdough and sustainable ingredients, supplying cafés, restaurants and Waitrose across Wales and England and operating cafes in Cardiff (Whitchurch Road) and Monmouth (Company website; Instagram bio). The brand emphasises craft, provenance and animal-free baking—strengths that create clear differentiation in a market where “sourfaux” (fake sourdough) and quality concerns have become mainstream topics of debate and reporting (The Guardian, 2023; The Times, 2025; FT, 2024).

Market context: Wales’ food and drink sector grew nearly 10% in 2023 with turnover reaching £9.3bn and targets exceeded early creating favourable conditions for scale-ups (Welsh Government/Business Wales, 2024). At same time, national craft bakery chains are expanding aggressively and these raising competitive pressure (British Baker, 2024; FT, 2024). Consumers increasingly want transparency and proof of authenticity in fresh foods (Deloitte, 2023; EIT Food Trust Report, 2024).

Problem The bakery has an excellent reputation and can reach a lot of people through wholesale but it does not have enough direct customer relationships, recurring income, or proof-of-impact messages for these changes in the market.

Target project: This plan proposes a twelve-month growth programme combining three workstreams:1) Direct-to-Consumer e-commerce with two subscription bundles to create recurring revenue and first-party data; 2) structured wholesale expansion in Wales to add scale and physical presence; 3) a measured community initiative, “Real Bread for Wales,” to publish transparent monthly impact and strengthen trust.

The three streams reinforce one another: D2C deepens loyalty and insights; wholesale builds reach and throughput; the campaign provides credible proof in a category prone to misinformation about real sourdough (The Guardian, 2023; The Times, 2025; FT, 2024). Thus, targeted combination addresses competitive and trust gaps while preserve bakery’s artisan quality and plant based ethos.

Project Aim, Objectives and Scope

Project Aim: The aim of the project is to grow revenue and loyalty without diluting artisan quality by launching D2C service with subscriptions, adding 20 Welsh wholesale doors and running one transparent, cause-led campaign.

SMART Objectives.

By Day 90:

- Online shop live with eight to twelve best sellers and delivery across Wales.

- Two subscription bundles live called Bread Basics and Weekend Treats with at least one hundred and fifty paying subscribers.

- 5 new wholesale accounts live.

- On-time-in-full (OTIF) must be at least 92%, the monthly online run-rate must be at least £20,000 and Net Promoter Score must be at least 55.

By Month 12:

- 1000 active subscribers; 20 net new wholesale doors.

- OTIF ≥95%; returns ≤2%; repeat purchase ≥35%; NPS ≥60.

- Publish 12 monthly impact updates; 10,000 loaves equivalent donated.

Scope in and scope out

In scope: Set up a simple online shop, add an easy subscription option, send helpful automated emails, use recyclable insulated packaging, agree courier service rules, create a wholesale guide, produce campaign materials, build a small performance dashboard, and train staff on new tools and processes.

Out of scope: New bakery sites or shop build outs, next day delivery across the whole United Kingdom, and implementation of a complex enterprise resource planning system.

Benefits and success criteria: Benefits include recurring revenue, stronger loyalty, wider reach in Wales, and transparent community impact. Success is measured by the month three and month twelve targets above, with a tolerance of plus or minus ten percent for time and cost, and by readiness to operate evidenced through signed service levels, training completion, and live dashboards.

Theoretical framework: Why this plan should work

PRINCE2-7 (project governance): PRINCE2-7 focusses on people, sustainability, and data, and it is based on customisation and outcomes (PeopleCert, 2025).  The project will set clear roles, hold short weekly meetings and have monthly steering to help people and decisions flow. It will also publish easy to understand sustainability KPIs like how is the recyclable packaging and how quickly deliveries are made. It will also manage by stages at the first, third, sixth, and ninth months with time and cost tolerances of plus or minus ten percent and quality standards that include on-time-in-full, returned and Net Promoter Score (PeopleCert, 2025; PMI, 2024).  This observation is in line with research that shows that hybrid and adaptive governance leads to better delivery outcomes (PMI, 2024).

The Resource-Based View (RBV) (strategies):  RBV contends that valuable, rare, inimitable and non-substitutable (VRIN) resources and competencies provide a long term advantage.  Distinctive assets for this bakery include long-fermentation expertise and quality, plant-based positioning, trusted provenance and supplier relationships and community credibility (Helfat et al., 2023; Lubis, 2022; Komakech et al., 2025). Implications of this framework are Monetise VRIN capabilities via D2C subscriptions to build recurring revenue and first-party data (Helfat et al., 2023) and protect inimitability by codifying fermentation practice, supplier stories and transparency content while enforcing cold-chain and OTIF standards (Lubis, 2022) and invest in hard-to-copy capabilities such as analytics, email automation and packaging performance; avoid broad nationwide roll-out until service reliability is proven (Komakech et al., 2025). Overall, this framing links governance discipline to the strategic use of scarce capabilities, ensuring growth without eroding artisan quality.

Project Outputs (Deliverables and Direct Results)

| Deliverable | Done-When (acceptance) | Evidence / Owner |
| --- | --- | --- |
| D2C Storefront (Wales) | 8–12 SKUs live; payments, tax, delivery set; five test orders; speed baseline | Test logs / E-commerce Lead |
| Two Subscription Bundles | “Bread Basics” and “Weekend Treats” launched; churn and MRR baselined | Live plans / E-commerce Lead |
| Wholesale Enablement Pack | Pricing, shelf cards, onboarding issued; five doors onboarded; first POs OTIF | Pack, invoices / Wholesale Lead |
| Packaging and Cold-Chain | 24–48h tests pass; recyclable insulation; courier SLA; labels and allergens approved | Reports / Operations Lead |
| Lifecycle Marketing Automations | Welcome, abandoned checkout, reorder, win-back live | ESP proofs / Marketing Lead |
| Customer Service and Returns | Helpdesk live; SLAs, macros, routing; returns linked to finance | Dashboard / Customer Service Lead |
| Operational Analytics Dashboard | Orders, AOV, Subscribers, OTIF, Returns, NPS automated; alerts configured | Dashboard / Data and CRM Analyst |
| Compliance Artefacts | HACCP, allergen matrix, SOPs updated; staff trained; audit recorded | Records / Quality Assurance Lead |
| Transparency Communications | Monthly “Real Bread for Wales” update with UTM tracking | URLs / Marketing Lead |
| Benefits and Handover Pack | Lessons captured; SOPs and contracts transferred; benefits confirmed at Gate 5 | Sign-off / Project Manager |

Direct results: By Month 3 the project achieves a revenue run-rate of at least £20,000 per month, at least 150 subscribers, on-time-in-full of at least 92 percent, returns no greater than 2.5 percent, and a Net Promoter Score of at least 55. By Month 12 it reaches at least 1,000 subscribers, at least 20 wholesale doors, on-time-in-full of at least 95 percent, returns no greater than 2 percent, repeat purchase of at least 35 percent, and a Net Promoter Score of at least 60.

Activities Required to Deliver the Outputs

The feasibility appraisal compared three options which are remaining wholesale led, launching full UK D2C at once, or staging a Wales-first D2C with two subscriptions, disciplined wholesale, and transparent monthly updates. The staged route is adopted to prove reliability before scaling. Governance applies stage gates and tolerances aligned to PRINCE2 7 and outcome-based planning in PMBOK 7 (PeopleCert, 2025; PMI, 2024).

Establish control and gates. Approve the charter, scope, and ±10% time/cost tolerances. Set cadence (weekly stand-ups; monthly steering) and Gate 1/3/4/5 decision points (PeopleCert, 2025; PMI, 2024).

De-risk last-mile and packaging. Run 24–48-hour temperature trials, select recyclable insulated packaging, and sign a courier SLA covering cut-offs and liabilities. Finalise labels and allergen data per UK guidance, then capture OTIF and damage baselines.

Launch minimum viable D2C and subscriptions. Configure catalogue, tax, shipping, and payments. Publish two packages to make sure the checkout works and then after that fill five end-to-end test purchases to get recurring income and first-party data (PMI, 2024).

Activate targeted wholesale. Issue pricing and onboarding packs, conduct sampling, and open five doors by Month 3 to extend reach while D2C stabilises (PMI, 2024).

Build lifecycle communications with deliverability assurance. Map welcome, abandonment, reorder, and win-back flows.

Returns and stand up service are required because protecting margin and experience requires implementation of helpdesk, service level agreements (SLAs), macros, routing and finance linked returns flow (PMI, 2024).

Set up the dashboard and notifications.  Set up automatic weekly reports for Orders, AOV, Subscribers, OTIF, Returns and NPS.  As important factors, track the courier's performance, the packaging's specifications, and the health of the email (PMI, 2024).

Publish monthly reports on the effects that are clear because when releasing findings of "Real Bread for Wales" with UTM proof, it gain confidence throughout planned growth (PeopleCert, 2025).

Maintain and develop is key activity because when determining the extent and pace of the roll-out in the United Kingdom, gate reviews should be compared to the goals for Month 3 and Month 12 (PeopleCert, 2025; PMI, 2024).

Work Breakdown Structure

Dependency Chart

Milestones by month

| ID | Month | What happens | Depends on |
| --- | --- | --- | --- |
| M1 | Month one | Charter approved, gates set, baselines fixed, platform chosen | 1.1 to 1.6 |
| M2 | Month two | Packaging tests passed and courier service level signed | 2.2 |
| M3 | Month three | Shop live, two bundles live, five doors opened; revenue run rate at least twenty thousand pounds; at least one hundred and fifty subscribers; on time in full at least ninety two percent; net promoter score at least fifty five | 2.1, 2.3, 2.4, 2.5, 2.6 |
| M6 | Month six | Scale decision and account reviews | 2.7 and wholesale performance |
| M9 | Month nine | Start of full operation and peak plan approved | 2.8 |
| M12 | Month twelve | Benefits sign off and handover completed | 3.1 to 3.3 |

Stakeholders and Governance

Stakeholder map and engagement

- Internal: Sponsor Managing Director, Project Lead, E-commerce Lead, Operations Lead, Wholesale Lead, Marketing Lead, Data and CRM Analyst, Finance, Customer Service Lead, Café managers.

- External: Courier and packaging suppliers, website and CRM vendors, charity partner for Real Bread for Wales, wholesale customers, retail shoppers, UK regulators and assurance bodies including Trading Standards, the Food Standards Agency and local Environmental Health for HACCP and allergen controls and the Information Commissioner’s Office for GDPR.

- Engagement approach: Weekly thirty-minute huddle for workstream leads, monthly steering with the Sponsor, a weekly KPI dashboard to all leads, a monthly stakeholder update, and formal partner check-ins each quarter. Customer feedback loops include post-purchase surveys for Net Promoter Score and service tickets review.

Resources & Cost Management

Roles and effort (who, when)

- Project lead (M1–M12): governance, RAID, benefits.

- E-commerce lead (M1–M3, M4–M12): storefront, subscriptions, payments.

- Marketing lead (M2–M3, M4–M12): automations, launch, “Real Bread” updates.

- Operations lead (M2–M3, M4–M12): packaging, courier SLA, returns.

- Wholesale lead (M1–M3, M4–M12): target list, sampling, new doors.

- Data lead (M2–M12): dashboard, data quality, KPI cadence.

- Customer service lead (M3–M12): SLAs, macros, CSAT/NPS.

- QA/HACCP (M2–M3): HACCP, allergen matrix, audits.

- Specialist support (as needed): web developer, photographer, email deliverability, packaging supplier, courier account manager.

Cost model
Rates and detailed cost accounts are in Appendix 1: Cost Account. The table below gives the roll-up used for approval.

| WBS | Cost account | One-off £ | per month £ | Notes |
| --- | --- | --- | --- | --- |
| 1.0 | Project setup and governance | 1,500 | 50 | PM tools and stage packs |
| 2.1 | Storefront and subscriptions | 7,500 | 650 | Theme, apps, payments |
| 2.2 | Packaging and cold chain | 4,500 | 2,800 | Boxes, liners, tests |
| 2.3 | Wholesale enablement | 3,500 | 500 | Sampling, travel |
| 2.4 | Marketing and communications | 3,000 | 500 | ESP plan and assets |
| 2.5 | Customer service | 2,000 | 180 | Helpdesk licences |
| 2.6 | Analytics and data | 2,500 | 120 | Dashboard hosting |
| 2.7 | Compliance and training | 2,000 | 100 | HACCP refresh |
| 2.8 | Retention and peak planning | 2,500 | 600 (months nine to twelve) | Seasonal packs, labour |
| 3.0 | Evaluation and handover | 1,000 | 0 | Benefits report |

Totals: one-off £30,000; twelve-month £60,600; base total £90,600; contingency ten percent £9,060; authorised budget £99,660.

Run-Up, Handover & Benefits

From months nine to twelve, operational readiness covers retention playbooks, seasonal bundles and confirmed capacity for stock, labour and courier routes; dry-run fulfilment verifies pick, pack and temperature rules; helpdesk macros and rota are checked against peak hours; data alerts confirm feeds for OTIF, returns and NPS; contingency van and shift plans are signed. Gate five closes with a benefits review comparing actuals to targets: one thousand active subscribers, twenty wholesale doors, OTIF at least ninety five, returns at most two percent, repeat purchase at least thirty five percent, Net Promoter Score at least sixty and delivery of twelve public impact updates. Variances have documented causes and actions. Handover transfers SOPs, dashboards and vendor contracts to named BAU owners (E-commerce, Operations, Marketing, Data) with access rights updated and a 30-day hyper care window. Lessons learned are captured by the project lead, prioritised and embedded into SOPs and the next annual plan.

References

Alex Gooch Artisan Baker (2025) Website. Available at: https://www.alexgoochbaker.com/ @alexgoochbaker (2025) Instagram bio. Available at: https://www.instagram.com/alexgoochbaker

British Baker (2024) Gail’s Bakery targeting 35 new stores in 2024, reveals MD Marta Pogroszewska. https://bakeryinfo.co.uk/retail/gails-bakery-managing-director-reveals-expansion-plans-for-2024/690504.article.

Business Wales (2024) Welsh food and drink industry grows by 10%. Available at: https://businesswales.gov.wales/news-and-blog/welsh-food-and-drink-industry-grows-10

Deloitte (2023) Hungry for Fresh Food: Trust and Transparency in Fresh Food. Available at: https://www.deloitte.com/us/en/insights/industry/retail-distribution/fresh-food-trends-produce-traceability-concerns.html

EIT Food (2024) Trust Report 2024. Available at: https://www.eitfood.eu/reports/trust-report-2024

Financial Times (2024). Rise of Gail’s shows big British appetite for craft bakery. Available at: https://www.ft.com/content/8a68a240-a6bc-4370-8773-dea2063b4e69

Helfat, C.E., Kaul, A., Ketchen, D.J., Barney, J.B., Chatain, O. and Singh, H. (2023) “Renewing the resource‐based view: New contexts, new concepts, and new methods.” Strategic Management Journal 44(6), pp. 1357–1390. Available at: https://sms.onlinelibrary.wiley.com/doi/abs/10.1002/smj.3500.

Komakech, R.A., Ombati, T.O., Kikwatha, R.W. and Wainaina, M.G. (2025) “Resource-based view theory and its applications in supply chain management: A systematic literature review.” Management Science Letters 15(4), pp. 261–272. Available at: https://www.researchgate.net/publication/387946639_Resource-based_view_theory_and_its_applications_in_supply_chain_management_A_systematic_literature_review

Lubis, N.W. (2022) “Resource Based View (RBV) in improving company strategic capacity.” Research Horizon 2(6), pp. 587–596. Available at: https://www.researchgate.net/publication/367501298_Resource_Based_View_RBV_in_Improving_Company_Strategic_Capacity

Mustafa, M.F.M.S., et al. (2024) ‘Food cold-chain logistics and management: a review of trends’, Sustainable Chemistry and Pharmacy. Available at: https://doi.org/10.1016/j.jafr.2024.101343

PeopleCert (2025) PRINCE2 Project Management Foundation (Version 7). Available at: https://www.peoplecert.org/browse-certifications/project-programme-and-portfolio-management/PRINCE2-2/prince2-7-foundation-3579

PeopleCert (2025) The new PRINCE2 7 is here! Best practice made better. Available at: https://www.peoplecert.org/products/prince2-certification-family

PMI (2024) Pulse of the Profession 2024: The Future of Project Work. Available at: https://www.pmi.org/learning/thought-leadership/future-of-project-work

Riley, D. (2024) Gali’s Bakery managing director reveals expansion plans for 2024. Available at: https://bakeryinfo.co.uk/retail/gails-bakery-managing-director-reveals-expansion-plans-for-2024/690504.article

Shi, H., et al. (2024) Cold-chain logistics and joint distribution: a review’, Systems, 12(7), 264. Available at: https://www.mdpi.com/2079-8954/12/7/264

The Guardian. (2023) “The sourfaux scandal: what is actually in your supermarket sourdough?” The Guardian 6 December. Available at: https://www.theguardian.com/food/2023/dec/05/sourfaux-scandal-what-is-in-supermarket-sourdough.

The Times. (2025) “The rise of fake sourdough — how to tell if your loaf is the real deal.” The Times 22 February. Available at: https://www.thetimes.com/uk/society/article/fake-sourdough-sourfaux-how-tell-loaf-real-deal-kmt0dmcj0.

Welsh Government (2024). Welsh food and drink industry grows 10%. Available at: https://www.gov.wales/welsh-food-and-drink-industry-grows-10

Appendices

Appendix 1: Cost Account

| WBS | Work package | Labour days (PM, Ecom, Mktg, Ops, Whsl, Data, CS, QA) | Labour subtotal | Expense – material | Expense – other | Expense subtotal | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Project setup & governance | 3,0,0,0,0,0,0,0 | £1,440 | £0 | £60 | £60 | £1,500 | Stage packs, PM tooling |
| 2.1 | Storefront & subscriptions | 3,10,2,0,0,1,0,0 | £7,120 | £1,600 (theme, apps) | −£1,220 credit | £380 | £7,500 | Dev config, payments, subs |
| 2.2 | Packaging & cold chain | 1,0,0,6,0,0,0,3 | £3,240 | £900 (tests, liners) | £360 (labels, probes) | £1,260 | £4,500 | 24–48h tests, SLA, artwork |
| 2.3 | Wholesale enablement | 1,0,1,0,6,0,0,0 | £2,880 | £900 (sampling) | −£280 credit | £620 | £3,500 | Pack, shelf cards, travel |
| 2.4 | Marketing & launch comms | 1,0,7,0,0,0,0,0 | £2,760 | £700 (photo kit) | −£460 credit | £240 | £3,000 | Press kit, assets |
| 2.5 | Customer service & returns | 1,0,0,2,0,0,3,0 | £1,880 | £250 (helpdesk) | −£130 credit | £120 | £2,000 | SLAs, macros, routing |
| 2.6 | Analytics & dashboard | 1,1,0,0,0,4,0,0 | £2,800 | −£400 credit | £100 (API connector) | £100 | £2,500 | Scorecard build |
| 2.7 | Compliance & training | 1,0,0,2,0,0,0,2 | £2,160 | −£260 credit | £100 (materials) | £100 | £2,000 | HACCP, allergen matrix |
| 2.8 | Retention & peak planning | 1,0,3,1,0,1,0,0 | £2,320 | £500 (gift inserts) | −£320 credit | £180 | £2,500 | Bundles, gifting, capacity |
| 3.0 | Evaluation & handover | 1,0,0,0,0,1,0,0 | £880 | £120 (report layout) | £0 | £120 | £1,000 | Benefits report |
|  | One-off subtotal |  | £27,480 | £4,370 | −£3,770 | £600 | £30,000 | Rounded to target |

Appendix 2: Deliverables & Acceptance

| Month | Deliverable | Done-when | Roles Lead | Evidence and KPI check | Risk and fix |
| --- | --- | --- | --- | --- | --- |
| 1 | Online shop Wales | Store live with 8 to 12 SKUs; pay, tax, delivery work | E-commerce | Five test orders; conversion baseline; page-speed audit | Scope creep; fix by freezing MVP and using a weekly change window |
| 1 | Wholesale starter pack | Price list, shelf cards, sampling plan and onboarding pack issued | Wholesale | Pack PDF; outreach list; leads in CRM | Slow leads; fix by trial stock and tastings |
| 1 | Governance cadence | RACI agreed; risk, issue and decision logs active; weekly huddle on time | Project | Minutes; live logs; on-time meetings | Decision drift; fix by using stage gates and tolerances |
| 2 | Subscriptions two plans | Bread Basics and Weekend Treats live | E-commerce | Subscriber count; churn baseline; monthly recurring revenue | Low uptake; fix by simple launch offer and clear FAQ |
| 2 | Email automations | Welcome, abandoned checkout, reorder reminder and win-back send | Marketing | Test matrix; deliverability pass; open and click rates | Spam risk and list hygiene |
| 2 | Packaging and cold chain | Twenty four to forty eight hour tests pass; courier service level signed; labels and allergens signed | Operations | Test report; SLA copy; sign-off sheet; OTIF and damage baselines | Breakage; fix by stronger inserts and a backup carrier |
| 2 | HACCP and training | HACCP, allergen matrix and SOPs updated; staff trained | Operations | Audit pass; training logs | Staff turnover; fix by buddy system and micro-lessons |
| 2 to 12 | Performance dashboard weekly | Orders, average order value, subscribers, on time in full, returns, Net Promoter Score reported | Data | Four consecutive weekly reports; action log | Missing feeds; fix by temporary manual sheet then automate |
| 2 to 12 | Marketing impact monthly | “Real Bread” update posted each month | Marketing | Post URL; referral sessions with UTM tags | Tokenism; fix by publishing numbers and partner quotes |
| 1 to 12 | Governance and compliance | Cadence holds; logs current | Project | Percent meetings on time; issues closed | Slippage; fix by escalation at gates |
| 3 | Customer service and returns | Rules, macros and routing live; SLAs set | Operations | Helpdesk dashboard; first reply time, resolution time, customer satisfaction | Volume spike; fix by rota and canned replies |
| 3 | Five wholesale doors live | First purchase orders shipped on time in full | Wholesale | Signed onboarding forms; invoices; door count | Missed windows; fix by route review and earlier cut-offs |
| 3 | Launch communications | Press note, founder angles, photo kit, posts and launch email scheduled | Marketing | Clippings; sessions from UTM tags | Low pickup; fix by partner amplification and founder outreach |
| 3 | Month three checkpoint | Online run-rate at least twenty thousand pounds; at least one hundred fifty subscribers; on time in full at least ninety two; Net Promoter Score at least fifty five | Project | KPI snapshot; steering minutes | Gaps; fix by corrective actions with owners and dates |
| 4 to 8 | Quality and repeat uplift | Page speed and checkout improved; service tighter | Cross-function | On time in full trend up; returns at or below two percent; repeat rate rising | Rework risk; fix by root cause and updated SOPs |
| 6 | Month six review | Scale decision; account reviews completed | Project | Review pack; actions assigned | Stalling; fix by removing blockers and re-prioritising |
| 9 | Retention and peak plan | Nudges, gifting, seasonal bundles; capacity for stock, labour and courier booked | Project | Retention playbook; capacity plan; supplier confirmations | Capacity shortfall; fix by buffers, flexible shifts and backup routes |
| 9 | Month nine readiness | Peak plan approved | Steering | Sign-off note | Gaps; fix by additional shifts and extra vans |
| 10 to 11 | Execute peak plan | Fulfilment meets plan | Operations | Hit rate versus plan; on time in full at least ninety five | Strain; fix by flexible shifts and rerouting |
| 12 | Benefits review and handover | Targets verified; lessons captured; SOPs updated; named owners accept | Project | Signed benefits report | Benefit drift; fix by remedial plan and accountable owners |

Appendix 3: Responsibility Matrix

| Work item | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| D2C shop go-live | E-commerce Lead | Sponsor | Operations, Marketing, Data, Finance | Team, Vendors |
| Subscriptions | E-commerce Lead | Sponsor | Operations, Marketing, Data | Team |
| Packaging and cold chain | Operations Lead | Sponsor | Courier, Packaging, QA | Team |
| Wholesale pack and onboarding | Wholesale Lead | Sponsor | Operations, Finance | Team, Key accounts |
| Campaign Real Bread for Wales | Marketing Lead | Sponsor | Charity partner, E-commerce | Team, Customers |
| Email automations | Marketing Lead | Sponsor | Data, E-commerce | Team |
| Customer service and returns | Customer Service Lead | Operations Lead | E-commerce, Marketing | Team |
| KPI dashboard | Data and CRM Analyst | Project Lead | All leads | Sponsor, Team |
| Governance and compliance HACCP GDPR | Project Lead | Sponsor | Operations, Legal, E-commerce, CS | Team, Regulators |