## Data Entry
FAILURE MODE AND EFFECTS ANALYSIS
Item: | Poundland Torch |  |  | Responsibility: |  | Status Int |  |  |  | FMEA number: | 1
Model: | 1 |  |  | Prepared by: |  | Josh and Amelia |  |  |  | Page : | 1
Core Team: | Josh and Amelia | [8 empty] | FMEA Date (Orig): |  | Rev:
Process Function | Potential Failure Mode | Potential Effect(s) of Failure | Sev | Potential Cause(s)/ Mechanism(s) of Failure | Occur | Current Process Controls | Detec | RPN | Recommended Action(s) | Responsibility and Target Completion Date | Action Results
[11 empty] | Actions Taken | Sev | Occ | Det | RPN
Main Body | Physical deformation | Components no longer assemble correctly | 8 | Deformation by physical force | 3 | Rigid material choice | 1 | 24 | Choose stronger material | Bob from Accounting |  |  |  |  | 0
|  | Battery cell cell no longer replaceable | 8 |  | 2 | Dual access for replacement of battery | 1 | 16 | Choose stronger material | Bob from Accounting
Bulb unit | Stripped or damaged Thread | Components no longer assemble correctly | 7 | Deformation by physical force | 1 | Caution while assembly is required, audible and visible controls | 4 | 28 | Closer inspection, Tighter tolerance | Bob from Accounting |  |  |  |  | 0
| Soldering Inconsistency | Power loss | 8 | Manufacturing error | 1 | Template from chip | 3 | 24 | Visual inspection | Bob from Accounting
Cell Cell | Damage to contacts | Power loss | 8 | Usage | 9 | Minimise surface area | 3 | 216 | Design ammendments | Bob from Accounting |  |  |  |  | 0
| Battery mis-alignment |  |  | Manufacturing, design error | 7 | Expected fit of components in assembly, visual | 3 | 168 | Design ammendments, Poka Yoke | Bob from Accounting
Button with handle | Inconsistent knurling | Loss of Grip, visual inconsistencies | 2 | Tool wear, quality control inconsistency | 8 | No quality control | 2 | 32 | Visual inspection | Bob from Accounting |  |  |  |  | 0
| Rubber wear | Visual insonsistencies, increase in difficulty to use | 6 | Improper usage, incosistent material depth | 4 | No quality control | 5 | 120 | Tolerances | Bob from Accounting |  |  |  |  | 0
| Different hole sizes | Visual insonsistencies | 2 | Quality control inconsistency, drill bit wear, drill float | 8 | No quality control | 2 | 32 | Tolerances | Bob from Accounting |  |  |  |  | 0
| Surface finish inconsistency | Visually and tactically inconsistent | 2 | Quality control inconsistency, tool wear | 9 | No quality control | 2 | 36 | Tighter Tool Maintenance. | Bob from Accounting |  |  |  |  | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0

## About This Template
This template was written for the American Society for Quality by
Stat Aids
Your feedback is welcome and encouraged. Please e-mail to:
Stat_Aids@yahoo.com