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Task Name < |Duaton v St v Fnsh v Predece~ Succetw
4 ETC Schedule 99 days Mon 27111117 Tue 24/04/18
4 Active Trials S9days  Mon 27117 Tue 24/04/18
4 Smal Scale Weapons trial S9days  Mon 27117 Tue 24104118
Start Date T day|_ Won 271117 on 2711117 B
< Documentation and. days  Tue2sMiM7  Tue 230118
Preparation
Trial Risk Assessments 21 days|  Tue 28117 Wed 0301118[3) =
Procedures 20ays|  Tue28117]  Wed 08112117 585 7ss
CTC Vaidation 3days|  Tue28M1M7[  Thu30i1i17]sss sss
=3 25days|  Tue 281117 Tue 09/01/18[75S g
Safety Certfcates Sdays| Wes 100118 Tue 18/01/1a[8 0
Trial nstructon & Briefing Notes| S days| Wed 17101118 Tue 23/01/18[3. 15
Vibration Rig Design 22days|  Tue28M1M7|  Thu 040118 3 2
Vibration Rig Manufacture. f0days  FriOSIOU18  Thu1si01/18/11 £
4 Inspections. 49days  Tue2sM1M7  Mon 1202i18
Defivery of Test tems. tday  Tue2sMiAT Tue2sninT3 1
Reciept nspection 20ays| Wed2401/18|  Thu2s01i8[1014 |16
Precursor Radiography tday|  Frzsotis]  Fnizsoisis 7
‘Acceptance of Radography Sdays| Mon290ing|  Fr020213[16 e
Technique
Radiography 1 day|  Mon 0102/18] Mo 0810271817 1821
X-Ray Approval Sdays|  Tue 002718 ton 12/0213[18 B
4 Cold Diurnal Cycling 18days  Mon0SI02M8  Thu 01103i18
Precursor 4Bhrs Mon0SIO2/18|  Wed 07102713 18 2
14 Cycles 3Whrs| Wed 0710218 Wed 21102118 21 £
Post Test Visual Inspection tday  Thuzo1s  Thu2202/18 22 202
Test Certfcate Sdays|  Fri2a021s  Thuo0as 23
4 Handiing Drop. Sdays  Friz30218  Wed 0710318
Test CellPrep. tday  F2uouis 230218 23 El
Precursor fday  Mon26002/18  Mon 26102118 26 »
Precondtioning +71°C. 48hrs Mon2602/18  Wed 28002/18 29551 day
Drops. tday  Tue2rio1s  Tue 27218 27 2855148
Precondtioning 46°C 4Bhrs Tue27io21s| ThuO1O31B 31SS-1 day
Drops. fday  Wed28002/18  Wed 28002118 29 2055148
Test Certfcate Sdays|  ThuOMON1B  Wed 0710318 31 s
4 Transport Vibration Gtdays  Fri901M8  Tue 17/04/18
Logbook, nstrumentatin, Test | 14days|  Fri19/0118|  Wed 07102018 12 =
CellPrep
‘Ambient Precursor “days|  Tuela01s|  Frife02is41s  |TFs-ida
Precondtioning 46°C 48hrs Mon 1902018 Wed 21/02/18 37551 day
Cold Temperature precursor Tday|  Tue2002/18|  Tue 20102/18 35751 day 36551 da
Precondtioning +71°C. 4Bhrs Wed2102/18  Friza02/1s 39551 day
ot Temperature Precursor Tday|  Thuza0zfa|  Thu22i02/1s 37751 day |40,3855-1
Customer approval and setup. 190ays|  Frizaio2is|  wwed 211031838 s
‘Condition Cold 48hrs ThuZ20318|  Sat24003/18 42551 day
Test Cold Axis 3 Tday|  Fizanats|  FriZainais 407S-1 day 41551 da
‘Condition Cold 48hrs Mon2603/18  Wed 28003/18 44551 day
Test Cold Axis 1, Axis change. Tday|  Tue270A1E|  Tue 2710313 42FS-1 day 43551
to Axis 2, Reconditon, Test day 46Fs-
a2 gay
‘Conditon Hot 4Bhrs Wed 280318 Fri3003/18 4651 day
Test Hot Axis 1, Axis Change fo Tday|  ThUZSNATE|  Thu 29103/13 44751 day 45551
Axis 2, Reconditon, Test Axis 2| gay.4aFs-,
‘Conditon Hot fday  Tue0304/18|  Tue 03104118 46551 day
Test Hot Axis 3 Tday| Wed 04/04/18|  Vied 04/04/18 46751 day 48,4751
Contingency “days|  Thuosi0e/1s|  Tue 1010471828 5052
Test Certicate Sdays| wed 110418 Tue 17i041[49 £
4 Post-Trial Inspections and 10days  Wed 11104118 Tue 24/04/18
Dispatch
Post Testng Visual Inspecton 2days Wed 110418 Thu 12004118 4 s
Dispateh of Test tems tday  Fri13041s  Fi130418 52
Completion of Test Cerlfcates. Sdays| Wed 180418 Tue 26/041[3250





