## Sheet1
0 | 0 | 35 | 35 | 0 | 49 |  | 49 | 0 | 67 |  | 67 | 20 | 76
Documentation & Prep |  |  | Inspection |  |  |  | Cold Diurnal Cycling |  |  |  | Handling Drop
0 | 35 | 35 | 35 | 14 | 49 |  | 49 | 18 | 67 |  | 87 | 9 | 96
Start
0 | 0 | 32 | 32 | 3 | 46 |  | 49 | 0 | 96 |  | 96 | 0 | 98 | 98 | 19 | 99 | 118
Vibration Rig Design & Manufacture |  |  | Logbook, Setup & Test Cell Prep |  |  |  | Vibration |  |  |  | Post Inspection |  |  | Dispatch |  |  | End of Trial
0 | 32 | 32 | 35 | 14 | 49 |  | 49 | 47 | 96 |  | 96 | 2 | 98 | 117 | 1 | 118
[11 empty] | 98 | 0 | 118
Test Certs & Report Completion
[11 empty] | 98 | 20 | 118
Key: | [7 empty] | Float
|  |  | Critical Path Analysis (CPD) |  |  | Early start |  |  |  | Early finish
Activity
[6 empty] | Late start |  |  |  | Late finish
Duration