## Slide 1
Managing Projects in the Organisation
Individual Presentation
on
Proposed Project Management Plan
Name: Bikash Roy
Module Code: BMSW5104-LON
Term & Group: T-2 G-1
Teacher’s Name: Dr Rexon Nting

## Slide 2
River-Side Cool Cold Storage
Introduction: As Bangladesh is an agrarian society based country. The people Bangladesh are depend on their various product of agriculture. However they do not have a good and enough storage system. Investment to build a good cold storage could be a right choice. People will be helpful, when they find a proper place to preserve their fruits, vegetables as well as processed food.
A Range of Benefits
Customisable Sizes and Settings
Freeing up Space
Backup Capabilities and Accessibility
Saving Money

## Slide 3
25th of June 2022 the Bangladesh celebrated inauguration of Padma Bridge, one of the largest bridge in south the Asia. This bridge connected the southwest of the country to the northern and eastern regions Louhajong in Munshiganj district to Shariathpur and Madaripur districts. If we build cold storage south side of the bridge, people will be benefited by storing their cultivated fruits and vegetables on their transit period. The benefited parties are:
Businessman related with these product
Employees those will connected with those cold storage
Government by getting tax/toll
Foreigner all over the world getting test of their preferable items
Location and its Business Value

## Slide 4: Cost and product Needs to Build a Cold Storage
To build a cold storage in Bangladesh, its generally need around 600000 to 10000000 TK(BD currency) (£ 51,975.00 to £86,625.00). However it depends on the dimensions of the cold storage.(Natural Storage Solutions Pvt Ltd, Mr V. Dahiya, 2021)
Moreover could be fulfil some basic requirements:
Insurances and Promotions
Eligibility and Criteria
Design of a normal infrastructure

## Slide 5
Products:
Cold Chain Solution
Cold Storage
Pack House
Ripening Chambers
Frozen Storage & Blast Freezer
Sorting & Grading Line
Individual Quick Freezing-IQF
Refrigeration Plants Maintenance
ICE Plants
Services:
CNC Bending job work
VMC Machine job work
Fabrication work
Metal rolling job work
Laser cutting job work
Electrical panel work
Project Execution
Shot Blasting Machine job work Glass Beading
Benefits of a Local Cold Storage

## Slide 6
Pros: Cons:
Rewarding work 1. Crowded space
Meaningful business connections 2.Find the right supplier and customer customer
Daily physical activity 3.Motivation of Employees
Amazing perks and discounts 4.Taxes
Local Community 5 . Time commitment
Location 6.High employee turnover
Face to Face interaction 7. High overhead expenses
Easy to do business
Pros and Cons of the Project

## Slide 7
 | Sample Stakeholder Analysis forProject |  |  |  |  |  |  |  | 
 |  | Communications |  |  |  |  |  |  | 
Stakeholders |  | Document |  | Document |  | Contact |  | Due | 
 |  | Name |  | Format |  | Person |  |  | 
Shareholders |  | Monthly |  | Hardcopy & |  | Director |  | 1st Friday of | 
 |  | Report |  | Meeting |  |  |  | Month | 
Customer business |  | Weekly |  | Email |  | Manager |  | Thursday | 
staff |  |  |  |  |  |  |  |  | 
Internal business |  | Daily |  | Email |  | Responsible |  | Daily | 
& Technical staff |  |  |  |  |  | Person |  |  | 
Training & software |  | Directly |  | Email |  | Contractor |  | Timely | 
Contractor |  |  |  |  |  |  |  |  | 
Sample Stakeholder Analysis for Project Communications
Stakeholders Document Name Document Format Contact Person Due Duration
 | Sample Stakeholder Analysis forProject | Sample Stakeholder Analysis forProject |  |  |  |  |  |  |  | 
 |  |  | Communications |  |  |  |  |  |  | 
Stakeholders |  |  | Document |  | Document |  | Contact |  | Due | 
 |  |  | Name |  | Format |  | Person |  |  | 
Shareholders |  |  | Monthly |  | Hardcopy & |  | Director |  | 1st Friday of | 
 |  |  | Report |  | Meeting |  |  |  | Month | 
Customer business |  |  | Weekly |  | Email |  | Manager |  | Thursday | 
staff |  |  |  |  |  |  |  |  |  | 
Internal business |  |  | Daily |  | Email |  | Responsible |  | Daily | 
& Technical staff |  |  |  |  |  |  | Person |  |  | 
Training & software |  |  | Directly |  | Email |  | Contractor |  | Timely | 
Contractor |  |  |  |  |  |  |  |  |  | 

## Slide 8
 |  |  |  | Gantt Chart |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task Name |  |  |  |  |  | Duration |  |  | Start |  | End |  |  |  |  |  |  |  | 
Build a Cold Storage |  |  |  |  |  | 5 months |  |  | 25/03/2023 |  | 24/08/2023 |  |  |  |  |  |  |  | 
1. Preaper Land for Constraction |  |  |  |  |  | 5 days |  |  | 25/03/2023 |  | 30/03/2022 |  |  |  |  |  |  |  | 
2. Construction of cold storage |  |  |  |  |  | 5 months |  |  | 31/03/2023 |  | 24/08/2023 |  |  |  |  |  |  |  | 
3. Foundation |  |  |  |  |  | 30 days |  |  | 31/03/2023 |  | 30/04/2023 |  |  |  |  |  |  |  | 
 | 3.1 Excavate |  |  |  |  | 15 days |  |  | 31/03/2023 |  | 14/04/2023 |  |  |  |  |  |  |  | 
 |  | 3.1.1 Pour Concrete |  |  |  | 8 days |  |  | 15/04/2023 |  | 22/04/2023 |  |  |  |  |  |  |  | 
 |  | 3.1.2 Cure & strip Forms |  |  |  | 7 days |  |  | 23/04/2023 |  | 30/04/2023 |  |  |  |  |  |  |  | 
 | 3.2 Steel Erection |  |  |  |  | 3 months |  |  | 01/05/2023 |  | 30/07/2023 |  |  |  |  |  |  |  | 
 |  | 3.2.1 Steel Columns |  |  |  | 45 days |  |  | 01/05/2023 |  | 15/06/2023 |  |  |  |  |  |  |  | 
 |  | 3.2.2 Beams |  |  |  | 46 days |  |  | 16/05/2023 |  | 30/07/2023 |  |  |  |  |  |  |  | 
4. Internal |  |  |  |  |  | 2 months |  |  | 05/05/2023 |  | 04/07/2023 |  |  |  |  |  |  |  | 
 | 4.1 Plumbing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 4.1.1 Rough-in Plumbing |  |  |  | 1 month |  |  | 05/05/2023 |  | 04/06/2023 |  |  |  |  |  |  |  | 
 |  | 4.1.2 Set Plumbing Foctur |  |  |  | 20 days |  |  | 05/06/2023 |  | 24/06/2023 |  |  |  |  |  |  |  | 
 |  | 4.1.3 Test and Clean |  |  |  | 10 days |  |  | 25/06/2023 |  | 04/07/2023 |  |  |  |  |  |  |  | 
 | 4.2 Electrical |  |  |  |  | 2 months |  |  | 14/06/2023 |  | 15/08/2023 |  |  |  |  |  |  |  | 
 |  | 4.2.1 Rough-in Electrical |  |  |  | 10 days |  |  | 14/06/2023 |  | 23/06/2023 |  |  |  |  |  |  |  | 
 |  | 4,2,2 Install and Terminate |  |  |  | 40 days |  |  | 24/06/2023 |  | 03/08/2023 |  |  |  |  |  |  |  | 
 |  | 4.2.3 HVAC Equipment |  |  |  | 10 days |  |  | 04/08/2023 |  | 15/08/2023 |  |  |  |  |  |  |  | 
5. Preaperation of Refrigeration |  |  |  |  |  | 9 days |  |  | 16/08/2023 |  | 24/08/2023 |  |  |  |  |  |  |  | 
 |  |  |  | Gantt Chart |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task Name |  |  |  |  |  | Duration |  |  | Start |  | End |  |  |  |  |  |  |  | 
Build a Cold Storage |  |  |  |  |  | 5 months |  |  | 25/03/2023 |  | 24/08/2023 |  |  |  |  |  |  |  | 
1. Preaper Land for Constraction |  |  |  |  |  | 5 days |  |  | 25/03/2023 |  | 30/03/2022 |  |  |  |  |  |  |  | 
2. Construction of cold storage |  |  |  |  |  | 5 months |  |  | 31/03/2023 |  | 24/08/2023 |  |  |  |  |  |  |  | 
3. Foundation |  |  |  |  |  | 30 days |  |  | 31/03/2023 |  | 30/04/2023 |  |  |  |  |  |  |  | 
 | 3.1 Excavate |  |  |  |  | 15 days |  |  | 31/03/2023 |  | 14/04/2023 |  |  |  |  |  |  |  | 
 |  | 3.1.1 Pour Concrete |  |  |  | 8 days |  |  | 15/04/2023 |  | 22/04/2023 |  |  |  |  |  |  |  | 
 |  | 3.1.2 Cure & strip Forms |  |  |  | 7 days |  |  | 23/04/2023 |  | 30/04/2023 |  |  |  |  |  |  |  | 
 | 3.2 Steel Erection |  |  |  |  | 3 months |  |  | 01/05/2023 |  | 30/07/2023 |  |  |  |  |  |  |  | 
 |  | 3.2.1 Steel Columns |  |  |  | 45 days |  |  | 01/05/2023 |  | 15/06/2023 |  |  |  |  |  |  |  | 
 |  | 3.2.2 Beams |  |  |  | 46 days |  |  | 16/05/2023 |  | 30/07/2023 |  |  |  |  |  |  |  | 
4. Internal |  |  |  |  |  | 2 months |  |  | 05/05/2023 |  | 04/07/2023 |  |  |  |  |  |  |  | 
 | 4.1 Plumbing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 4.1.1 Rough-in Plumbing |  |  |  | 1 month |  |  | 05/05/2023 |  | 04/06/2023 |  |  |  |  |  |  |  | 
 |  | 4.1.2 Set Plumbing Foctur |  |  |  | 20 days |  |  | 05/06/2023 |  | 24/06/2023 |  |  |  |  |  |  |  | 
 |  | 4.1.3 Test and Clean |  |  |  | 10 days |  |  | 25/06/2023 |  | 04/07/2023 |  |  |  |  |  |  |  | 
 | 4.2 Electrical |  |  |  |  | 2 months |  |  | 14/06/2023 |  | 15/08/2023 |  |  |  |  |  |  |  | 
 |  | 4.2.1 Rough-in Electrical |  |  |  | 10 days |  |  | 14/06/2023 |  | 23/06/2023 |  |  |  |  |  |  |  | 
 |  | 4,2,2 Install and Terminate |  |  |  | 40 days |  |  | 24/06/2023 |  | 03/08/2023 |  |  |  |  |  |  |  | 
 |  | 4.2.3 HVAC Equipment |  |  |  | 10 days |  |  | 04/08/2023 |  | 15/08/2023 |  |  |  |  |  |  |  | 
5. Preaperation of Refrigeration |  |  |  |  |  | 9 days |  |  | 16/08/2023 |  | 24/08/2023 |  |  |  |  |  |  |  | 

## Slide 9
Government stability
Tax policy
Competition regulation
Trad blocks
Inflation rate
Interest rate
Consumer spen7ding trends
Unemployment trends
Demographics
Education
Family size and structure
Health consciousness
Technological infrastructure
Internet penetration
Use of social media
Investment in R & D
Health and safety law
Employment laws
Anti-discrimination law
Recycling
Waste management
Green consumption
Renewable energy investments
PESTLE Analysis of a Cold Storage
Political Economical Social Technological Legal Environmental

## Slide 10: Post COVID-19 opportunities for cold storage
At the beginning of COVID-19, the business of cold storage was impacted with slowdown but as demand of retail sector the impact is likely not last longer.
There are some post-pandemic opportunities:
Inventory levels may be growing
Frozen foods get a chance
Growing omni channel adoption

## Slide 11: Conclusion:
As Bangladesh has a remarkable development to reduce poverty. It reached lower-middle income status in 2015 and now on track to graduate from the UN’s Least Developed Countries(LDC) list in 2026.
My vision is to help people to improve their cultivation capacity. When they will secured that after their long procedure of cultivation of fruits and vegetables, they can store those, sell those and earn profit. They will gainer, state will benefited and impressed others to be in productive way.
Not only people of Bangladesh but also people like us who are living out of Bangladesh and wanted to test their favourite things with proper conservative way.
Hopefully The Governing body of Bangladesh Bank will realise the aim of my proposed project and approve it.

## Slide 12: References’: 1. Fundamentals of project management.( Heagney & Joseph, 2012;2016)( Access, Aug 8th, 2022) 2. Making things happen: mastering project management.( Berkun & Scott, 2008)( Access, Aug, 8th, 2022) 3. Local private sector partnerships; cold chain Bangladesh alliance.( Jan, 2016)( Access, Aug 8th, 2022) ( Access, Aug 8th, 2022) 4. Natural Storage Solution Pvt Ltd.(Mr V. Dahiya. 2021)

## Slide 13
Thank you
Any Question ?