## Final
Blueprint Construction
PRELIMINARY SCHEDULE OF VALUATIONS (MONTHLY EXPENDITURE ANALYSIS)
Client | ACE Capital Project | [23 empty] | Date | 25th April 2024
Contract | Phase 1: Port Talbot Cultural Quarter, National Steel Museum of Wales - Amgueddfa Dur Cymru | [23 empty] | Revision | Rev A
[25 empty] | Programme No | James Lloyd - QS (1900878)
ITEM | ELEMENT | ACTUAL | PROV | TOTAL | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | Comments
[5 empty] | 2024-03-28 | 2024-04-25 | 2024-05-23 | 2024-06-20 | 2024-07-18 | 2024-08-15 | 2024-09-12 | 2024-10-10 | 2024-11-07 | 2024-12-05 | 2025-01-02 | 2025-01-30 | 2025-02-27 | 2025-03-27 | 2025-04-24 | 2025-05-22 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 2025-09-11 | 2025-10-09 | 2025-11-06
1 | DESIGN FEES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
1.01 | N/A | 0 |  | 0
0
2 | PRELIMINARIES | 2221000 | 0 | 2221000 | 104954.5455 | 95554.5455 | 90554.5455 | 90554.5455 | 93154.5455 | 90554.5455 | 90554.5455 | 90554.5455 | 90554.5455 | 90554.5455 | 100954.5455 | 97054.5455 | 125654.5455 | 125654.5455 | 125654.5455 | 125654.5455 | 109654.5455 | 93654.5455 | 93654.5455 | 93654.5455 | 93654.5455 | 108554.5455
0
2.01 | Defects After Competion | 17000 |  | 17000 | 2025-01-30: 3400; 2025-11-06: 13600
2.02 | Management and Staff | 490000 |  | 490000 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273 | 22272.7273
2.03 | Site Accommodation | 33000 |  | 33000 | 5500 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 5500
2.04 | Site Consumables | 123000 |  | 123000 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091 | 5590.9091
2.05 | Temporary Services | 100000 |  | 100000 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545 | 4545.4545
2.06 | Security | 24000 |  | 24000 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091 | 1090.9091
2.07 | Safety and Environmental Protection | 17000 |  | 17000 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273 | 772.7273
2.08 | Control and Protection | 10000 |  | 10000 | 2025-01-30: 1000; 2025-02-27: 1000; 2025-03-27: 1000; 2025-04-24: 1000; 2025-05-22: 1000; 2025-06-19: 1000; 2025-07-17: 1000; 2025-08-14: 1000; 2025-09-11: 1000; 2025-10-09: 1000
2.09 | Mechanical Plant | 385000 |  | 385000 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500
2.1 | Temporary Works | 167000 |  | 167000 | 10590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 32590.9091 | 32590.9091 | 32590.9091 | 32590.9091 | 16590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091 | 590.9091
2.11 | Fees and Charges | 26000 |  | 26000 | 2024-04-25: 5000; 2025-01-30: 2100; 2025-02-27: 2100; 2025-03-27: 2100; 2025-04-24: 2100; 2025-05-22: 2100; 2025-06-19: 2100; 2025-07-17: 2100; 2025-08-14: 2100; 2025-09-11: 2100; 2025-10-09: 2100
2.12 | Insurance, Bonds, Guarantees and Warranties | 13000 |  | 13000 | 2024-07-18: 2600; 2025-01-02: 10400
2.13 | OH&P | 816000 |  | 816000 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091 | 37090.9091
0
3 | SUBSTRUCTURE | 407548.9 | 0 | 407548.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203774.45 | 203774.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
3.01 | Substructures | 407548.9 |  | 407548.9 | 2025-01-30: 203774.45; 2025-02-27: 203774.45
0
3 | SUPERSTRUCTURE | 3813509.9 | 0 | 3813509.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115074.85 | 625445.8357 | 897934.3157 | 1330416.9157 | 800831.5829 | 43806.4 | 0 | 0 | 0 | 0 | 0
0
3.02 | Frame | 937500.5 |  | 937500.5 | 2025-03-27: 267857.2857; 2025-04-24: 267857.2857; 2025-05-22: 267857.2857; 2025-06-19: 133928.6429
3.03 | Upper Floors | 246840 |  | 246840 | 2025-02-27: 24684; 2025-03-27: 49368; 2025-04-24: 74052; 2025-05-22: 74052; 2025-06-19: 24684
3.04 | Roof | 542645.4 |  | 542645.4 | 2025-04-24: 108529.08; 2025-05-22: 379851.78; 2025-06-19: 54264.54
3.05 | Stairs | 370480 |  | 370480 | 2025-02-27: 37048; 2025-03-27: 148192; 2025-04-24: 74096; 2025-05-22: 74096; 2025-06-19: 37048
3.06 | External Walls | 1066857 |  | 1066857 | 2025-02-27: 53342.85; 2025-03-27: 160028.55; 2025-04-24: 373399.95; 2025-05-22: 266714.25; 2025-06-19: 213371.4
3.07 | Windows & External Doors | 197505 |  | 197505 | 2025-05-22: 79002; 2025-06-19: 118503
3.08 | Internal Walls & Partitions | 438064 |  | 438064 | 2025-05-22: 175225.6; 2025-06-19: 219032; 2025-07-17: 43806.4
3.09 | Internal Doors | 13618 |  | 13618 | 2025-05-22: 13618
0
4 | FINISHES | 426782.35 | 0 | 426782.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168.464 | 113880.533 | 212806.943 | 98926.41 | 0 | 0 | 0 | 0 | 0
0
4.01 | Wall Finishes | 5842.32 |  | 5842.32 | 2025-04-24: 1168.464; 2025-05-22: 2336.928; 2025-06-19: 2336.928
4.02 | Floor Finishes | 329754.7 |  | 329754.7 | 2025-05-22: 65950.94; 2025-06-19: 164877.35; 2025-07-17: 98926.41
4.03 | Ceiling Finishes | 91185.33 |  | 91185.33 | 2025-05-22: 45592.665; 2025-06-19: 45592.665
0
5 | FIXTURES & FITTINGS | 77002.75 | 357000 | 434002.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74500 | 0 | 233102.75 | 126400 | 0 | 0 | 0
0
5.01 | Bessemer Converter | 74500 |  | 74500 | 2025-06-19: 74500
5.02 | Musuem Exhibition Equipment |  | 275000 | 275000 | 2025-08-14: 165000; 2025-09-11: 110000
5.03 | Restaurant Fittings |  | 82000 | 82000 | 2025-08-14: 65600; 2025-09-11: 16400
5.04 | Playarea to basement | 2502.75 |  | 2502.75 | 2025-08-14: 2502.75
0
6 | SERVICES | 2030888.25 | 0 | 2030888.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419741.375 | 579417.1 | 492298.875 | 321417.3875 | 107827.775 | 110185.7375 | 0 | 0 | 0
0
6.01 | Plumbing, Heating and Ventilation Installations | 779784 |  | 779784 | 2025-04-24: 311913.6; 2025-05-22: 311913.6; 2025-06-19: 116967.6; 2025-09-11: 38989.2
6.02 | Electrical Installations | 1078277.75 |  | 1078277.75 | 2025-04-24: 107827.775; 2025-05-22: 215655.55; 2025-06-19: 323483.325; 2025-07-17: 269569.4375; 2025-08-14: 107827.775; 2025-09-11: 53913.8875
6.03 | BWIC | 172826.5 |  | 172826.5 | 2025-05-22: 51847.95; 2025-06-19: 51847.95; 2025-07-17: 51847.95; 2025-09-11: 17282.65
0
7 | EXTERNAL WORKS | 1404144.28 | 0 | 1404144.28 | 0 | 171006 | 119988 | 35904 | 60778.6667 | 181930.8333 | 181930.8333 | 139104.1667 | 165462.8067 | 178642.1267 | 139104.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 15975.608 | 7717.072 | 0 | 0
0
7.01 | Site Strip & Clearance (Including site preparation, demolitions, disposal etc.) | 285010 |  | 285010 | 2024-04-25: 171006; 2024-05-23: 114004
7.02 | New Road Layout and Associated works | 59840 |  | 59840 | 2024-05-23: 5984; 2024-06-20: 35904; 2024-07-18: 17952
7.03 | Adoptable Roads & Paths | 128480 |  | 128480 | 2024-07-18: 42826.6667; 2024-08-15: 42826.6667; 2024-09-12: 42826.6667
7.04 | Soft Landscaping, Planting and Irrigation Systems | 8292.68 |  | 8292.68 | 2025-09-11: 4975.608; 2025-10-09: 3317.072
7.05 | Fencing, Railings and Walls | 65896.6 |  | 65896.6 | 2024-11-07: 26358.64; 2024-12-05: 39537.96
7.06 | External Fixtures | 22000 |  | 22000 | 2025-08-14: 6600; 2025-09-11: 11000; 2025-10-09: 4400
7.07 | Split Level Boardwalk | 636625 |  | 636625 | 2024-08-15: 106104.1667; 2024-09-12: 106104.1667; 2024-10-10: 106104.1667; 2024-11-07: 106104.1667; 2024-12-05: 106104.1667; 2025-01-02: 106104.1667
7.08 | Corten Steel Structure | 198000 |  | 198000 | 2024-08-15: 33000; 2024-09-12: 33000; 2024-10-10: 33000; 2024-11-07: 33000; 2024-12-05: 33000; 2025-01-02: 33000
0
0
8 | Risk Contingency | 939564.19 | 0 | 939564.19 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 42707.4632 | 0
0
8.01 | Design Contingency | 134223.46 |  | 134223.46 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664 | 6101.0664
8.01 | Construction Risk | 268446.91 |  | 268446.91 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323
8.01 | Employers Change | 268446.91 |  | 268446.91 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323
8.01 | Other Misc. Risks | 268446.91 |  | 268446.91 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323 | 12202.1323
9 | Variations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
TOTALS - MONTHLY GROSS APPLICATION |  | 11320440.62 | 357000 | 11677440.62 | 147662.0086 | 309268.0086 | 253250.0086 | 169166.0086 | 196640.6753 | 315192.842 | 315192.842 | 272366.1753 | 298724.8153 | 311904.1353 | 282766.1753 | 343536.4586 | 487211.3086 | 793807.8444 | 1487206.1634 | 2192076.5574 | 1732799.4095 | 600512.2061 | 483892.5336 | 388923.3541 | 144079.0806 | 151262.0086
TOTALS - RETENTION (5%) |  |  |  |  | -4429.8603 | -15463.4004 | -12662.5004 | -8458.3004 | -9832.0338 | -15759.6421 | -15759.6421 | -13618.3088 | -14936.2408 | -15595.2068 | -14138.3088 | -17176.8229 | -24360.5654 | -39690.3922 | -74360.3082 | -109603.8279 | -86639.9705 | -30025.6103 | -24194.6267 | -19446.1677 | -7203.954 | -4537.8603
TOTALS - MONTHLY NETT APPLICATION |  |  |  |  | 143232.1484 | 293804.6082 | 240587.5082 | 160707.7082 | 186808.6415 | 299433.1999 | 299433.1999 | 258747.8665 | 283788.5745 | 296308.9285 | 268627.8665 | 326359.6357 | 462850.7432 | 754117.4521 | 1412845.8552 | 2082472.7295 | 1646159.439 | 570486.5958 | 459697.907 | 369477.1864 | 136875.1266 | 146724.1484
TOTALS - CUMULATIVE GROSS (Excl VAT) |  |  |  |  | 147662.0086 | 456930.0173 | 710180.0259 | 879346.0345 | 1075986.7098 | 1391179.5518 | 1706372.3938 | 1978738.5691 | 2277463.3844 | 2589367.5197 | 2872133.695 | 3215670.1536 | 3702881.4623 | 4496689.3066 | 5983895.47 | 8175972.0273 | 9908771.4368 | 10509283.643 | 10993176.1766 | 11382099.5307 | 11526178.6114 | 11677440.62
NOTES:
Includes Contract Instructions as identified above