Module Title: Problem Solving and Decision Making

Module Code: LCLM 4004

Assessment: Component 2 Report

Student Name: Marius Ciuculescu

Student Number: 2505372

Lecturer’s Name: Mucahit Ozden

Table of Contents

Contents                              			    Page Number

Task 1: 	Overview of Case-study							3

# Task 2:	Two proposed solutions 							3

# Task 3b): 	Evaluation Results and Justifications					3

# Task 4b): 	Risk Analysis Results and Justifications 					4

# Task 5b): 	Justifications for the Implementation Plan				4

# Task 6b): 	Justifications for the KPI and SMART objectives			4

# Task 7: 	Key Findings  				                       		4

Reference List                                                                                                          5

# Appendices

# Appendix 1: Task 3a) Grid or PMI Analysis Table……………………………………7/8

# Appendix 2: Task 4a) Risk Analysis Table…………………………………………….10

# Appendix 3: Task 5a) Implementation Plan……………………………………………11

# Appendix 4: Task 6a) KPI and SMART Table…………………………………………12

Task 1: Overview of Case-study

Green Haven Florists, a small independent shop in Norwich, has seen a 30% drop in in-store sales over the past year as customer habits shift and costs rise. The main issue is that the business hasn’t kept up with how people now prefer to buy flowers—mainly online, with quick delivery and competitive prices. Several factors add to this, including an outdated website, limited online services, and weak digital marketing. At the same time, stronger competitors and higher supply costs are putting pressure on profits. While customers still value the quality, the business is struggling to stay visible, convenient, and competitive in a changing market

# Task 2: Two Proposed Solutions

## Solution A Proposal

Digital Transformation Strategy

This solution focuses on upgrading Green Haven’s online presence. It includes redesigning the website to make it modern, mobile-friendly, and easy to navigate, while adding features such as online ordering, flexible delivery options, and subscription services. It would also involve consistent social media marketing and basic SEO to increase visibility. This directly addresses the root problem of poor digital alignment by making the business more accessible and convenient for customers who prefer to shop online. As a result, Green Haven can attract new customers, improve online sales, and better compete with larger and more digitally advanced rivals.

## Solution B Proposal

Differentiation through Sustainability and Experience

This solution builds on Green Haven’s existing strengths by emphasising its eco-friendly ethos and personalised service. It could include promoting locally sourced flowers, offering workshops, and creating unique in-store experiences such as custom bouquet consultations. Marketing would highlight sustainability and community values to appeal to environmentally conscious consumers. This helps resolve the root problem by clearly positioning the business as a premium, experience-led alternative rather than competing on price or convenience alone. By strengthening its unique identity, Green Haven can build customer loyalty, justify higher prices, and stand out from both chain retailers and trend-focused competitors.

# Task 3b) Evaluation Results and Justifications

Based on the PMI analysis, Solution A: Digital Transformation Strategy is the most appropriate option, scoring slightly higher overall and directly addressing the root problem of poor digital alignment. The key criteria used were impact on sales, ability to address the root problem, and feasibility. Greater weighting was given to impact and problem resolution, as reversing declining sales is the business’s most urgent priority. While Solution B strengthens branding, it does not fully solve the convenience gap. Therefore, Solution A is justified as it improves accessibility, increases online sales potential, and aligns Green Haven with current consumer behaviour, making it the most effective and sustainable choice.

# Task 4b) Risk Analysis Results and Justifications

The main risks associated with Solution A include high setup costs, limited digital skills within the business, and uncertain customer uptake of the new online system. The criteria used to assess risk were likelihood and impact, as these best measure both how often an issue may occur and how severely it would affect the business. Greater weighting was given to impact, because even low-probability issues could significantly affect revenue or reputation. Despite these risks, the solution is still reliable as they can be reduced through phased implementation, staff training, and targeted marketing. Overall, the risks are manageable and do not outweigh the long-term benefits.

# Task 5b) Justifications for the Implementation Plan

The implementation plan is structured in a logical sequence to ensure the solution is introduced smoothly and effectively. Task 1 is prioritised first as it identifies current weaknesses and informs all future improvements. Tasks 2 and 3 are scheduled next to build the new website and supporting services, as these form the core of the digital transformation. Task 4 follows and continues alongside development to generate awareness and drive traffic. Responsibilities are assigned based on expertise, with the web developer handling technical work and Liam, Priya, and a marketing freelancer managing operations and promotion. This sequencing reduces risk, ensures efficiency, and supports a controlled rollout of change.

# Task 6b) Justifications for the KPI and SMART Objectives

The KPI of increasing online sales by 40% within 6 months is appropriate because it directly measures the success of the digital transformation strategy and reflects the business’s shift towards online purchasing. It is a strong indicator of whether the new website, delivery service, and marketing efforts are working effectively. The SMART objectives are justified as they are specific (focused on online sales), measurable (percentage increase), achievable (based on current growth trends), relevant (addresses declining in-store revenue), and time-bound (6-month period). This ensures clear tracking of progress and allows Green Haven to evaluate performance in a structured and realistic way.

# Task 7) Key Findings

- Green Haven’s main issue is a decline in in-store sales caused by a shift towards online shopping and reduced high street footfall.

- The business has a weak digital presence, including an outdated website and limited online marketing, reducing competitiveness.

- Strong competitors are outperforming Green Haven through better pricing, delivery options, and stronger online visibility.

- Rising operational costs, especially for sustainable materials and imported flowers, are reducing profit margins.

- Despite challenges, Green Haven still has strong potential due to its high product quality, loyal customer base, and strong brand reputation, meaning improvements could quickly boost performance.

Reference List

Doran, G. T. (1981) ‘There’s a S.M.A.R.T. way to write management’s goals and objectives’, Management Review, 70(11), pp. 35–36.

Hopkin, P. (2018) Fundamentals of Risk Management. 5th edn. London: Kogan Page.

Project Management Institute (PMI) (2021) A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edn. Newtown Square, PA: PMI.

Kotler, P. and Keller, K. L. (2016) Marketing Management. 15th edn. Harlow: Pearson.

Porter, M. E. (2008) ‘The five competitive forces that shape strategy’, Harvard Business Review, 86(1), pp. 78–93.

Chaffey, D. and Ellis-Chadwick, F. (2019) Digital Marketing. 7th edn. Harlow: Pearson.

Appendices

Appendix 1 – Task 3a

PMI Analysis Table

| Solution A |  |  |
| --- | --- | --- |
| Plus | Minus | Interesting |
| Increases online visibility and reach (5) | High initial cost (3) | Enables subscription services (4) |
| Improves customer convenience (5) | Requires digital skills (3) | Attracts younger customers (4). |
| Competes with online retailers (4) | Time to see results (3) | Provides customer data insights (4) |
| Boosts potential sales growth (4) | Ongoing maintenance needed (3) | expansion beyond local area (4) |
| TOTAL: 18 | TOTAL: 12 | TOTAL: 16 |

Therefore: Overall Total for Solution A = 46

| Solution B |  |  |
| --- | --- | --- |
| Plus | Minus | Interesting |
| Strong brand identity (4) | Limited appeal to some customers (3) | Premium positioning (4) |
| Builds customer loyalty (4) | Doesn’t fix online gap (4). | Workshops create income (4) |
| Aligns with eco trends (4) | Higher costs (3) | Community partnerships (4) |
| Differentiates from competitors (4) | Niche market reliance (3) | Strong word-of-mouth (4) |
| TOTAL: 16 | TOTAL: 13 | TOTAL: 16 |

Therefore: Overall Total for Solution B = 45

Appendix 2 – Task 4a

Risk Analysis Table

|  | What could cause a risk? | What is the likelihood of the risk occurring? (1 – 5) | What is the impact of this risk? (1 – 5) | Risk Factor = Likelihood X Impact | What can you do to reduce this risk from happening? | If it happens – what can you do to minimise the impact? |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | High cost of website development | 3 | 4 | 12 | Set a clear budget and use phased implementation | Prioritise essential features and delay extras |
| 2 | Lack of digital skills | 4 | 4 | 16 | Provide training or hire external experts | Outsource tasks temporarily |
| 3 | Low online customer uptake | 3 | 5 | 15 | Invest in marketing and user-friendly design | Offer promotions/discounts to attract users |

Appendix 3 – Task 5a

Implementation Plan

Name the problem you are solving:

Declining in-store sales due to weak digital presence, low convenience, and increased online competition.

Name the solution you are implementing:

Digital Transformation Strategy (website upgrade, online ordering, delivery options, and digital marketing).

|  | Task | WHAT | WHEN | WHO | Done |
| --- | --- | --- | --- | --- | --- |
| 1 | Review current website | Audit current website and customer needs to identify key improvements | Week 1 | Liam, Priya + web consultant | Website issues identified and plan approved |
| 2 | Build and launch. A new website | Design and launch new mobile-friendly website with online ordering system | Weeks 2–5 | External web developer | New website fully launched and working |
| 3 | Introduce new features to attract more customers | Introduce delivery upgrades and subscription flower service | Weeks 5–7 | Operations team + Liam & Priya | Delivery and subscription service active |
| 4 | Promote the website | Launch digital marketing campaign (social media, SEO, local ads) | Weeks 6–8 (ongoing) | Marketing freelancer + Priya | Campaign launched and generating traffic |

Appendix 4 – Task 6a

The Key Performance Indicator is:

| Specific | Measurable | Attainable | Relevant | Time-Bound |
| --- | --- | --- | --- | --- |
| online sales growth | tracked through website analytics and sales data | based on current growth trends | directly addresses declining in-store sales and shifting customer behaviour | 6-month period |