Event Report

Beans On Toast back on the road 2023

Description of the event and the concept of the event- (timing and location)

Beans on toast

The event will be called “Beans on Toast, back on the road”. The goal of the event is for Jay McAllister to continue to display his messages to his fans, his messages are about politics, drugs and love. The event will take place at the Bunkhouse bar, 24 Park Street, Swansea, SA1 3DJ on Wednesday 22nd March 2023. The doors are open from 7-11pm and tickets are £15 in advance and age 14+ (Under 16s must be accompanied by an adult) Research on beans on toast prior to the event is crucial to know his popularity and audience. He has released seven studio albums, all dealing with the topics of politics, drugs and love.

(Genius, n/d)

Tech and stage set up

-1 DL for guitar and 1 stand for microphone

- Power drop needed to be provided

Catering/ Rider

-£30 buyout to be paid by bank transfer

-Bananas, apples, multi-packed crisps risps, bread (white and brown), 2 types of hummuses and pre- bagged salad

-4 cans of Guiness

12 bottled beers – Peroni, Estrella and Corona

(Need to make sure all beers come in and ice bucket)

Tour support

-Support for the show will be Ann Lui Cannon they will be travelling solo on public transport

-Beans will invoice for the support fee and pay directly

Merch

-30 Minutes is to be allowed for beans to meet his fans and sell merch after he comes off stage.

| Aims | Objectives |
| --- | --- |
| To produce a profit | By selling all our tickets |
| Increase awareness of the event and ‘Beans on Toast’ | Post about the event, making sure to tag ‘Beans on Toast.’ Encourage participants to use the hashtag #beansontoast |
| Sell out all the tickets | Get all our friends and family to share the posts Encourage ‘Beans on toast’ fans to share about the event. |
| Establish relationships and to network | Try to talk to all work colleagues |

A few different project planning techniques were used prior to the event, “project management reviews the steps in organizing and managing projects, from how to build a realistic schedule to how to measure both success and failure.”(Heerkens, G.R., 2002.)

Running order;

| Time | Description | Location |
| --- | --- | --- |
| 2:30pm | Calypso and Emily collect rider items requested | Lidl |
| 3:15pm | Calypso and Emily collect list of door collections/ ticket holders for the event | Derrick’s music |
| 4:15pm | Calypso, Emily and Will have final meeting | The Bunkhouse |
| 5pm | Debbie (lecturer) to arrive | The Bunkhouse |
| 5pm | Load in | The Bunkhouse |
| 5:30pm | Soundcheck for Beans | The Bunkhouse |
| 6pm | Sound check for supporting act | The Bunkhouse |
| 7pm | Fans due to arrive at the venue | The Bunkhouse |
| 8pm | Support act performs | The Bunkhouse |
| 9pm | Beans performs | The Bunkhouse |
| 10:30pm | Beans will sell merch and meet fans | The Bunkhouse |
| 11:30pm | Beans and support act due to depart | The Bunkhouse |
| 12am | Most guests due to depart | The Bunkhouse |
| 2am | Venue will close | The Bunkhouse |
|  | Clean up | The Bunkhouse |

Gantt chart

“A Gantt chart is one of common and popular way of showing activities/ tasks/ events against time. Gantt charts establish a time-phased network, which links project activities to a project schedule baseline.” (Pinto,2007)

Our Roles

Prior to the event

-The aims and objectives- Both

- Planning side- e.g. running order and itinerary for the day- Emily

- Marketing- Both had access to the page and could both reply to comments and edit posts

-Ticket sales- Calypso

- Emergency procedures-, safety and licenses- Emily

-Risk assessment- both

Day of the event

When we arrived, we were briefed and shown how to run the ticketing and had to download the ticketing app called Gig Scan.

Emily and Calypso are to meet and welcome Beans on toast and all his tour supporters and ensure they have everything needed

We will take turns to do registration desk to ensure all of beans supporters come in smoothly

When event is running, we will be walking back around to ensure everything is going according to plan and if anyone needs anything we are there to help

Belbin’s Team roles

Source: adapted from Belbin (2006, 2007); reproduced by kind permission of Belbin Associates

Contingency planning

“A plan sets a course for an organisation. It provides a guide to the future, a framework to describe how the organisation expects to achieve its goals.” (Bloom, MJ & Menefee, MK, 1994)

| Problem | Plan |
| --- | --- |
| Key equipment failure | -Soundchecks - Beans on Toast has support people with him |
| Injuries | -First aider on site always |
| ‘Beans on Toast’ arriving late | - Ask him to come early |

Meetings

It was crucial that we had many meetings to do with the event to ensure everyone understood the event in more detail and what our individual roles were and to also ensure all the planning is running smoothly and everything is organised. “Meetings are hugely important. They help forge relationships, are the birthplace of cutting-edge ideas and have the power to transform whole businesses and industries. They’re where the big decisions are made.” (Team D,2023)

- Date: Monday 20th February 2023

Time: 1:15 pm - 2:30pm

Attendees: Emily, Calypso, Dan and Jordan

Subject: Introductions

Location: Costa coffee

2.    Date: Monday 27th February 2023

Time: 12pm – 1pm

Attendees: Calypso, Dan and Jordan

Subject: Going though itinerary for the day of event also sorting out Marketing/                                  advertisements

Location: The bunkhouse bar

3.    Date: Tuesday 7th March 2023

Time: 10am – 11:30

Attendees: Emily, Calypso and Dan

Subject: Marketing/ Advertising. Beans on toast Catering and stage set up

Location: University of Wales Trinity Saint David

4.  Date: Tuesday 14th March 2023

Time: 7:00pm – 8:00

Attendees: Emily, Calypso and Jordan

Subject: introduced to staff, given a tour of behind the scenes

Location: The bunkhouse bar

5. Date: Monday 20th March 2023

Time: 6:00-8:00

Attendees: Emily, Calypso, Dan and Will

Subject: Going over the itinerary for the 22nd

Location: The Bunkhouse bar

6. Date: Wednesday 22nd March 2023

Time: 4:15-5:00

Attendees: Emily, Calypso and Will

Subject: Last minute checks

Location: The Bunkhouse bar

Marketing

- Facebook and Instagram are the social medias being used for Marketing.

- Posters and videos were created and turned into advertisements for IBA Events and The Bunkhouse Bar on Facebook.

- The posters and videos created for IBA Events reached 1358 people and engaged 94 people, significantly increasing ticket sales.

poster;

IBA Facebook advertisement:

The Bunkhouse Swansea Facebook post:

The Bunkhouse Swansea Instagram post:

Market research (the event consumers/market segments)

Having a marketing plan is crucial to ensure the event runs smoothly and it is a success. Knowledge of target is very important- the demographics, age group and past events experience for the beans on toast. ICCE/ESOMAR (www.esomar.org) in its international code on market and social research (2007) defines research (market, social and opinion research) as the systematic gathering and interpretation of information about individuals or organisations using the statistical and analytical methods and techniques of the applied social sciences to gain insight or support decision makign. The event is aimed for ‘Beans on Toast’ fans, who typically are a mix of female and male. Anyone 16 or under must be accompanied by an adult. Based on prior events and ticket sales, many guests are expected to be between the ages of 20-30 and to live in South Wales. ‘Beans on Toast’ usually attracts hippies because of the style of his music.

Market selection

The amount of people expected for the event is 160 as that is how many tickets a have been sold however the capacity of the venue is 190 so 30 more tickets are available to buy on the door on the night via card or cash.

The expected spending for customers is entry, merchandise and drinks when they are there.

Expenditure and income

Final fee payments via BACS after show settlement has been received

Any required licences

- Public liability/license was covered by the venue

- No external suppliers needed

Emergency plans 3.Emergency Plan

Theory

- Emergencies plans are very important as they ensure a plan is put in place for everyone if an emergency occurs and makes sure everyone is safe.

- It also ensures that the responsibility of emergency response is sorted to.

Emergency Procedures

- Raising the alarm

- Inform all public

- Call emergency services

- Crowd management- evacuation and control

- Provide 1st aid and medical assistance

- Help evaluate disabled or injured.

(Copies of the procedures and floor plan, including a map are located all over the venue and include where anyone can find any first aid kits, fire extinguisher and any other safety equipment's.)

Safety procedures

Security will be on the door, searching people for any items on them that could be a harm to others or people trying to bring their alcohol into the building. Also, the bar will be checking people’s ID’s if they look underage to ensure no one underage is served.

Risk Assessment

“Risk assessment must evolve for addressing the existing and future challenges, and considering the new systems and innovations that have already arrived in our lives and that are coming ahead.” (Zio and Zio, 2018)

| Area of concern | Hazards focused | Existing control measures | Further controls to reduce risks | Rating of possibility |
| --- | --- | --- | --- | --- |
| Slips and any falls (wires) | Injuries- people tripping up The steep stairs | Cover the wires Any spillages are cleaned up as soon as possible to prevent slipping | Put a sign out Maintain good housekeeping standards Make sure all electrical cables are out of sight and covered | 5 |
| Toilets | Not enough for the people that attended | Form calm cues if needed |  | 7 |
| Small room | Overcrowded | Try and move people straight through onto the main floor as soon as possible | Ensure enough staff on bar so people can get their drink quickly and move on | 7 |
| Age requirement | Underage drinking or underage serving | All customers must be 18 or over that are purchasing alcohol Any staff that serve alcohol must be 18 or over | If any customers look under 21, ask for their ID to prevent serving any customers underage. All staff checked before working on bar that they are 18 or over by showing their passport and birth certificate. | 6 |
| Electrical | Music, lights, speakers | Regularly test and maintain electrical equipment | Sound checks and checks of all portable equipment's | 7 |

The Clean up

Calypso and I along with all the other staff members will be staying at the event until the end, to ensure the place is clean and everything is put away.

Evaluation

Evaluating the event is crucial for an event profile to be created, it provides a tool for analysis and improvement "Evaluation is concerned with judging the worth of a program.” (Robert. A. Wisher,1998) As an evaluation I would say the event ran smoothly with no major problems however there were few minor issues such as the app me and Calypso downloaded to scan the tickets on did not work for everyone’s tickets if they bought from a different website, this was a problem as Will had to come back and for to scan these tickets. Also, another problem that occurred was that the room that the customers first entered and got drinks from was small and got crowded very quickly. Also, a few people asked Calypso and I where the main floor was, this could have been prevented. There was not a card machine specifically just for me and Calypso on the entry, so we had to keep going to the busy bar to borrow their card machine.

Evaluation strategy

I would say that the bar should have been open in the main floor straight away and that would have moved people out of the first room and helped with the crowding and give more room for customers entering too.

Calypso and I should have had an app that scanned all the tickets, to prevent delays.

More clear signs to direct people up to the main floor would have prevented confusion as to where Beans on Toast was performing.

References

Anon, (n.d.). Beans on Toast – Back Out On The Road 2023. [online] Available at: https://beansontoastmusic.com/ [Accessed 30 Mar. 2023].

Baines, P., Fill, C. and Rosengren, S., 2017. Marketing. Oxford University Press.

Bloom, M.J. and Menefee, M.K., 1994. Scenario planning and contingency planning. Public Productivity & Management Review, pp.223-230.

Genius. (n.d.). Beans On Toast. [online] Available at: https://genius.com/artists/Beans-on-toast [Accessed 30 Mar. 2023].

Heerkens, G.R., 2002. Project management. McGraw Hill Professional.

Team, D. (2023) 4 ways that catering can enhance your business meetings, 30 Euston Square. Available at: https://30eustonsquare.co.uk/2023/01/25/4-ways-that-catering-can-enhance-your-business-meetings/ (Accessed: March 31, 2023).

McGivern, Y., 2009. The practice of market research: an introduction. Pearson Education.