## Slide 1: Strategic Planning Festivals, Conventions and Events
BMTP6017

## Slide 2: Power of thoughts

## Slide 3: A new debate on Economic impacts?
Economic and social regeneration
The circular economy…..
What are the implications for events management?
https://www.ellenmacarthurfoundation.org/circular-economy/concept

## Slide 4: This week
Bidding processes
The concept of the feasibility and the forces impacting on feasibility studies;
Leverage, legacy planning in terms of tourism development, economic and multiplier effect ,community impacts, economic and social regeneration.

## Slide 5: The strategic planning process and event organisation
Concept or intent to bid
Preliminary stage
Feasibility study
Formal analysis of the event’s potential
Crucial for public funding (grants)
Decision to proceed or cease
Directly determined by feasibility study
https://craftguildofchefs.org/news/wales-wins-bid-host-worlds-biggest-culinary-event-2026

## Slide 6: The Bidding Process
Step 1: Request For Proposals. Product owners or project teams first need to issue a request for proposal (RFP) or invitation to bid (ITB) to initiate the bidding process.
Step 2: Bid Preparation Of Interested Parties.
Step 3: Bid Evaluation And Selection.
Step 4: Contract Negotiation And Awarding.

## Slide 7: The bidding process
The bidding process for festivals, conventions, and events is a highly competitive and strategic activity, often involving cities, venues, or event organizers presenting proposals to host major events.
This process is critical because successful bids can generate significant economic benefits, enhance a city’s global profile, and promote tourism.
Let’s break down the key elements of the bidding process along with research and statistics.

## Slide 8: Understanding the Bidding Process
Involves several key stages:
Expression of Interest (EOI): Cities, venues, or event organizers submit a formal expression of interest to the event governing body. This phase identifies which cities are interested in hosting the event.
Proposal Development: The interested parties develop a comprehensive bid proposal.
The proposal usually includes aspects such as:
  Venue capabilities (size, infrastructure, technology).
  Transport and accommodation options.
  Economic, social, and environmental impact assessments.
  Safety and security plans.
  Legacy and sustainability strategies.
Evaluation: The event governing body (e.g., International Olympic Committee, FIFA, or large-scale festival organizers) reviews the bids based on a set of criteria, including the ability to meet logistical, financial, and infrastructural requirements.
Selection: A panel or committee makes the final decision, often announced through a public ceremony.

## Slide 9: Factors Influencing Successful Bids
Economic Impact: Host cities need to demonstrate the potential for strong economic returns, including job creation, tourism growth, and infrastructure investments. Studies have shown that large-scale events like the Olympics, Super Bowl, or major festivals (e.g., Glastonbury) can bring significant short-term economic boosts. For instance, the 2019 FIFA Women's World Cup in France generated an estimated $267 million in economic activity for the host cities .
Tourism Infrastructure: Cities must prove they can accommodate an influx of visitors in terms of hotels, transportation, and services. Research from the International Congress and Convention Association (ICCA) shows that cities with strong tourism infrastructure have higher success rates in winning convention and event bids. For example, Paris, Barcelona, and Vienna consistently rank among the top cities for hosting international conferences .
Environmental and Sustainability Plans: Increasingly, event organizers are focusing on sustainability in their bid selection process. Events like the Olympic Games and global conventions are under pressure to be eco-friendly and leave a positive legacy. The Paris 2024 Olympics, for example, is being marketed as one of the most sustainable Games, with 95% of venues already built or temporary and a significant reduction in the carbon footprint .
Cultural Appeal and Heritage: The cultural richness and uniqueness of the city also play a major role. For festivals like the Edinburgh Festival Fringe, the cultural significance of the location is vital to its global appeal. Edinburgh’s rich history and reputation as a cultural hub make it an ideal location for the event, which draws over 3 million visitors annually .

## Slide 10: Economic Statistics of Major Events
Olympic Games: The 2016 Rio Olympics generated $6.2 billion in direct economic impact but were also criticized for leaving large debts and unused infrastructure. However, more successful events like the 2000 Sydney Olympics reportedly generated over $5 billion in tourism revenues in the years following the event .
Convention and Exhibition Industry: According to the Global Association of the Exhibition Industry (UFI), the global exhibition industry generated more than $137 billion in economic output in 2019. Conventions and large-scale events such as CES (Consumer Electronics Show) in Las Vegas generate billions for host cities annually. CES alone contributes around $300 million per year to the local economy in Las Vegas .
Festival Industry: Large-scale music festivals like Coachella and Glastonbury generate significant local economic impacts. Coachella 2022 generated over $700 million for the local economy in the Coachella Valley, including spending on hotels, restaurants, and retail .

## Slide 11: Trends Shaping the Bidding Process
Digital and Hybrid Events: Due to the COVID-19 pandemic, many events shifted to a hybrid or fully digital model, which has influenced how cities bid for events. Future bids may need to demonstrate technological capabilities to host digital or hybrid events alongside physical gatherings.
Sustainability and Legacy: Cities are increasingly being judged on their ability to manage environmental impacts. Sustainable infrastructure, carbon offset programs, and long-term legacies for the local population are critical factors for winning bids. Statistics from the UNWTO indicate that 96% of event organizers believe sustainability is crucial in the post-pandemic event landscape .
Economic Multiplier Effect: Research shows that for every $1 spent on convention and festival hosting, there can be an economic multiplier effect of up to $2-$3, as visitors spend on accommodation, dining, and other services .

## Slide 12: How do you write a bid for an event proposal?
Preparing the Event Proposal - Writing a bid for an event proposal involves presenting a detailed and compelling case to the event’s decision-makers that your city, venue, or organization is the best choice to host the event.
A well-structured bid must highlight your capacity to deliver a successful event, while addressing the specific needs and objectives of the event organizers.
The Event Team. The proposal should provide information about the event management team in terms of the experience and qualifications of key team members.
Venue and Facilities. The reader of the proposal will want to know whether the venue is suitable for the event.
The Program- running order
The Budget – all costs

## Slide 13: Understand the Event and Bid Requirements
Step by step guide to crafting a competitive bid for an event proposal:
Before writing, you need to fully understand the event and the organizer's expectations. This often involves:
Researching the Event: Understand the history, scale, audience, and goals of the event. Whether it's a music festival, a convention, or a sports event, ensure you know the purpose and values of the event.
Request for Proposal (RFP): Read through the official RFP (Request for Proposal) or any guidelines provided by the event organizers. This document typically outlines what the organizers are looking for, including specific requirements for the venue, logistics, budget, and other criteria.

## Slide 14: Create a Structured Bid Proposal
A clear structure will help you communicate your message effectively.
A typical bid proposal includes the following sections:
a) Executive Summary
The executive summary is a high-level overview of your bid, summarising why venue or city is the ideal choice. Highlight the key benefits and capabilities of location. This section should be concise but persuasive, encouraging the reader to delve into the rest of the proposal.
Example: "Our city offers world-class infrastructure, a rich cultural heritage, and an experienced events management team, making it the perfect choice to host the 2026 World Expo."
b) Introduction and Background

## Slide 15
Provide background information about the city, venue, or organisation. Highlight your previous experience hosting similar events, your expertise in event management, and any relevant partnerships or collaborations.
Key Elements to Include:
  History of successful events.
  Your organization’s mission and values.
  Examples of working with local stakeholders and businesses.
Example: "Over the past decade, our venue has hosted numerous large-scale conventions and festivals, including the Global Technology Summit and the Music Fest 2023, which attracted over 50,000 attendees."

## Slide 16
Event Fit and Alignment
Here, demonstrate how hosting this event aligns with your city or venue’s goals and how it benefits both parties. Highlight the strategic fit between the event’s goals and your location's unique offerings.
Economic Impact: Estimate the financial benefits for the local economy, such as tourism, job creation, and local business engagement.
Cultural Fit: Emphasise any cultural significance your city holds in relation to the event.
Example: "Hosting the International Arts Festival would complement our city’s reputation as a hub of creativity and innovation, while delivering an estimated $30 million in economic impact.“

## Slide 17
Venue and Infrastructure
Provide detailed information on the venue’s capacity to handle the event, including:
Venue Specifications: Details about the event space, including size, seating capacity, breakout rooms, and accessibility features.
Technology and AV Capabilities: Highlight high-speed internet, AV systems, and broadcasting facilities for hybrid or virtual events.

## Slide 18
Accommodation: Explain the availability of hotels and alternative accommodations for attendees and participants.
Transport and Accessibility: Detail how visitors can easily access the venue, including proximity to airports, public transport options, and parking facilities.
Example: "Our convention centre offers 200,000 square feet of flexible event space, capable of hosting up to 10,000 attendees, with cutting-edge audiovisual capabilities."

## Slide 19
Logistics and Event Support
Outline the logistical plan for ensuring the smooth execution of the event:
Event Management: Detail your team’s event management expertise, including coordination of security, logistics, and crowd control.
Safety and Security: Provide information on the venue’s safety standards, emergency protocols, and partnerships with local law enforcement.
Sustainability Plan: If relevant, explain how you will manage the event sustainably, such as waste reduction, energy efficiency, and carbon offsetting.
Example: "Our venue has a dedicated events management team with over 20 years of experience, offering seamless coordination of transportation, security, and on-site catering."

## Slide 20
Marketing and Promotion
Demonstrate how you will help promote the event to attract more visitors, sponsors, and participants.
You can mention:
Partnerships: Potential partnerships with local tourism boards, media outlets, or influencers.
Marketing Channels: How you will leverage social media, digital platforms, and local advertising to boost attendance.
Engagement: Highlight community engagement strategies, such as involving local artists or businesses in the event.
Example: "We will partner with regional tourism organisations and use targeted social media campaigns to reach over 1 million potential attendees across Europe."

## Slide 21
Financial Proposal
This section should provide a clear budget and demonstrate financial feasibility. Include:
Costs: A breakdown of event hosting costs, including venue hire, staffing, equipment, and marketing.
Sponsorship: Potential sponsorship or revenue opportunities to offset costs.
Economic Impact: Detail the potential return on investment for the event organizers and the local economy.
Example: "Our financial proposal includes a competitive venue hire fee of $500,000 and projected sponsorship revenue of $1 million from local partners."

## Slide 22
Legacy and Sustainability
Many event organisers now focus on leaving a positive legacy and minimising the environmental impact of their events. In this section, describe how the event will benefit the local community in the long term and how you plan to implement sustainable practices.
Sustainability Initiatives: Outline waste reduction strategies, renewable energy use, and sustainable transport options.
Legacy Projects: Explain how the event can leave a lasting impact, such as improved infrastructure or social programs.
Example: "Our sustainability plan includes a zero-waste initiative and a focus on local sourcing for catering, while the event's legacy will include an upgraded public transportation system."

## Slide 23
Include Supporting Data and Case Studies
Wherever possible, use data and case studies to support your claims:
Economic Impact Data: Provide statistics from similar events that demonstrate the financial and tourism benefits.
Case Studies: Include case studies of previous events you’ve hosted successfully.
Statistics: Cite relevant statistics on visitor numbers, economic impact, or sustainability achievements.
Example: "Our previous event, the 2019 Global Innovation Summit, attracted over 30,000 attendees, generating $25 million in local spending and a 15% increase in hotel occupancy rates."
Design and Presentation
A professional presentation matters. Make sure your bid is:
Visually Engaging: Use infographics, charts, and images to make the document visually appealing.
Concise and Clear: Ensure clarity in language and avoid overloading the reader with excessive detail.
Polished: Proofread the document carefully to ensure there are no errors.

## Slide 24: Conclusion
Crafting a successful bid for an event proposal involves thorough research, strategic planning, and clear communication.
You need to align your city or venue’s strengths with the needs of the event, highlight your logistical capabilities, and demonstrate the economic, social, and cultural benefits of hosting the event.
A well-structured, data-supported, and professionally presented bid can significantly increase your chances of winning the bid.

## Slide 25: Risks
The risk associated at the bid phase can have a profound negative impact for the hosting community, causing not only financial problems but affecting the social, commercial and political life of the community itself.
To bid for and possibly host a small or a major single or multi-sports event, such as the Olympics or a World Cup or a World Championship, can be a complex, time-consuming process.
Detailed studies and robust financial information are necessary in order to maximize the opportunities that events of this nature present to host cities and countries.
Host cities and countries must plan for the event and ensure that the potential legacy benefits, such as the social and economic impact, urban regeneration and increased media profile, are not only both identified beforehand but are and also maximized.

## Slide 26: Addressing Risks:
In any event bid proposal, addressing risks is critical to demonstrating your ability to foresee and mitigate potential challenges. Event organizers want to be confident that your city or venue can handle unforeseen circumstances without jeopardizing the event’s success.
Financial Risks - Cost Overruns
Event budgets can easily exceed initial projections due to unexpected expenses such as venue upgrades, staffing, or logistics. This could negatively affect both the host city and the event organizers.
Risk Mitigation:
  Provide a detailed budget with built-in contingencies (usually 10-20% of total costs).
  Secure sponsorships or partnerships to offset some of the costs.
  Develop a cost-control plan with financial checks at different stages.

## Slide 27
Revenue Shortfalls
Lower-than-expected ticket sales, sponsorship, or vendor participation can result in a significant revenue shortfall.
Risk Mitigation:
  Conduct thorough market research to ensure demand for the event.
  Develop a robust marketing plan to drive ticket sales and sponsorship.
  Offer flexible ticket pricing and multiple sponsorship packages to increase participation.

## Slide 28
Operational and Logistical Risks
a) Venue Capacity and Infrastructure Issues
Overcrowding, insufficient facilities, or poor venue infrastructure could lead to logistical challenges, dissatisfaction, and even safety risks.
Risk Mitigation:
  Ensure the venue can comfortably accommodate expected attendees with clear plans for parking, seating, restrooms, and facilities.
  Conduct a venue audit well in advance to address any shortcomings.
  Set clear maximum attendee limits and implement crowd control measures.
b) Staffing and Volunteer Shortages
An insufficient number of staff or volunteers could lead to operational breakdowns, delays, and poor customer service.
Risk Mitigation: Partner with staffing agencies or volunteer ensure sufficient numbers.
  Implement training program for all event staff and volunteers.
  Create a backup staffing plan for key positions to ensure continuity.

## Slide 29
Health and Safety Risks
a) Public Health Crises
In a post-pandemic world, public health risks like disease outbreaks (e.g., COVID-19) are a serious concern for large gatherings.
Risk Mitigation:
  Develop a health and safety plan in line with current public health guidelines, including sanitation, contact tracing, and quarantine measures if needed.
  Provide adequate medical services on-site, and have protocols in place for dealing with health emergencies.
  Consider hybrid event options to reduce crowd density.
b) Safety and Security Threats
Security risks include terrorism, protests, theft, or general disorder, particularly for high-profile events.
Risk Mitigation:
  Collaborate with local law enforcement and security services to ensure comprehensive security measures.
  Implement surveillance systems, security checks, and emergency evacuation plans.
  Train staff on how to handle various emergency scenarios.

## Slide 30
Environmental and Sustainability Risks
a) Environmental Damage - Events, like large outdoor festivals, can have adverse environmental impacts such as pollution, waste, and damage to public spaces.
Risk Mitigation:
  Develop a sustainability plan that includes waste management (recycling, composting), energy efficiency measures (use of renewables), and water conservation.
  Partner with local environmental organizations to reduce the event’s carbon footprint.
  Implement an environmental monitoring system to minimize any lasting damage.
b) Extreme Weather Conditions - Weather-related disruptions, such as heavy rain, heatwaves, or storms, can cause event cancellations or interruptions, especially for outdoor events.
Risk Mitigation:
  Have a backup plan that includes indoor venue options or weather shelters for outdoor events.
  Invest in weather insurance for high-cost events.
  Use real-time weather monitoring tools and communicate contingency plans to attendees.

## Slide 31
Reputation and Brand Risks
a) Negative Media or Social Media Attention - Unfavourable media coverage or negative social media sentiment can harm both the event and the host city's reputation. Issues like poor organization, safety incidents, or unsatisfied attendees can quickly go viral.
Risk Mitigation:
  Have a dedicated public relations team to manage media relations and quickly address any negative narratives.
  Monitor social media channels during the event to respond to complaints or crises in real time.
  Establish a post-event evaluation process to address any concerns that arose.
b) Greenwashing Accusations - If a city or venue markets itself as "sustainable" but fails to meet those claims, it risks damaging its reputation through accusations of greenwashing.
Risk Mitigation:
  Ensure that any sustainability claims are backed by measurable actions, such as carbon offset programs, waste reduction efforts, and renewable energy use.
  Conduct regular audits and provide transparency in sustainability reporting.
  Engage with environmental advocacy groups for third-party validation.

## Slide 32
Legal and Compliance Risks
a) Non-Compliance with Local Regulations
Events need to comply with a wide range of laws, including health and safety, labor laws, and zoning regulations. Failing to do so can result in fines, legal disputes, or event cancellation.
Risk Mitigation:
  Work closely with local authorities and legal experts to ensure full compliance with regulations.
  Obtain all necessary permits, licenses, and insurance policies well in advance of the event.
  Conduct regular compliance checks throughout the planning and execution phases.
b) Contracts and Liability
Disputes with contractors, sponsors, or vendors can lead to legal battles, especially if contracts are unclear or broken.
Risk Mitigation:
  Develop clear and comprehensive contracts that outline the responsibilities and expectations of all parties.
  Ensure that you have robust insurance coverage for liability, cancellations, and damages.
  Include force majeure clauses in contracts to protect against unexpected events like natural disasters or pandemics.

## Slide 33
Political and Social Risks
a) Political Instability
Political unrest, changes in government policy, or protests can impact the safety and feasibility of hosting an event.
Risk Mitigation:
  Assess the political stability of the host city or country before placing a bid.
  Maintain open communication with local government officials to stay informed about any political

## Slide 34: Festival Example: Glastonbury Festival (UK)
Event Overview: Glastonbury Festival is one of the largest and most famous outdoor music festivals in the world, attracting over 200,000 attendees annually. Held on a farm in the UK, it features performances across multiple stages and spans several days.
Key Risks:
Weather-Related Risks (Extreme Rain/Flooding)
  Example: In 2005, Glastonbury experienced severe flooding that turned the festival grounds into a mud pit, disrupting performances and causing safety concerns.
  Risk Mitigation:
    The festival invested heavily in drainage systems after this event to manage potential flooding.
    Real-time weather monitoring is now used to adjust stage schedules and ensure safe evacuation plans.
    The festival also advises attendees to be well-prepared for rain, making recommendations on appropriate gear and footwear.

## Slide 35
Environmental Impact (Waste and Pollution)
  Example: Glastonbury faces ongoing criticism for the amount of waste left behind, with an estimated 2,000 tons of waste generated at the 2017 festival, including tents, plastic bottles, and litter.
  Risk Mitigation:
    Glastonbury has since implemented a strict zero-plastic policy and encourages festival-goers to bring reusable bottles.
    They also provide on-site recycling stations and have invested in post-festival clean-up efforts.
    The festival engages in environmental partnerships with organizations like Greenpeace to promote sustainability.
Health and Safety (Drug Use and Overcrowding)
  Example: The festival has had incidents related to drug use, overcrowding, and heat exhaustion in the past.
  Risk Mitigation:
    Increased security personnel, crowd management systems, and better on-site medical facilities have been implemented.
    Drug awareness campaigns and water stations are now common at Glastonbury to mitigate these risks.
Lessons Learned:
Glastonbury’s ability to manage risks effectively has contributed to its longevity. It has developed a robust framework for dealing with weather-related challenges, environmental sustainability, and health and safety concerns, making it a model for large outdoor festivals.

## Slide 36: Global Event Example: Olympic Games (Tokyo 2020)
Event Overview: The Olympic Games are the largest sporting event in the world, involving athletes and spectators from around the globe. The Tokyo 2020 Olympics were postponed to 2021 due to the COVID-19 pandemic, and the planning process involved numerous risks that had to be managed on a global scale.
Key Risks:
Pandemic and Public Health Risks (COVID-19)
  Example: The COVID-19 pandemic forced the postponement of the Tokyo Olympics from 2020 to 2021, causing significant logistical, financial, and public health risks.
  Risk Mitigation:
    The Tokyo 2020 organizing committee implemented strict health protocols, including daily COVID-19 testing for athletes, limited public attendance, and mask mandates.
    A "bubble" system was used to minimize contact between athletes and the general public.
    Many events were held without spectators, reducing the risk of viral transmission but significantly impacting ticket revenue.
Economic Risks (Cost Overruns and Revenue Shortfalls)
  Example: The cost of hosting the Tokyo Olympics ballooned to $15.4 billion, making it one of the most expensive Olympics in history. The absence of ticket sales due to restrictions on spectators contributed to this shortfall.
  Risk Mitigation:
    The Japanese government and the International Olympic Committee (IOC) had to revise their financial models to manage losses, relying on broadcast rights and sponsorships as the primary revenue sources.
    By leveraging digital platforms and streaming services, the organizers ensured strong global viewership, partially compensating for the lack of ticket sales.

## Slide 37
Sustainability and Environmental Risks
  Example: The Olympics typically leave a significant environmental footprint due to large-scale construction, energy use, and waste.
  Risk Mitigation:
    Tokyo 2020 promoted sustainability by using renewable energy sources and constructing several venues with recycled materials. For instance, the Olympic Village was built with timber donated by local Japanese regions.
    The Games also aimed to be carbon neutral, with carbon offsetting programs in place.
    Medal production for Tokyo 2020 involved recycling old electronic devices to source the metals.
Lessons Learned:
The Tokyo 2020 Olympics demonstrated the importance of adaptability in global events, particularly in response to an unprecedented crisis like the COVID-19 pandemic. Despite financial losses and the absence of spectators, Tokyo managed to deliver a successful Games with robust health protocols and innovative sustainability initiatives.

## Slide 38: Convention Example: CES (Consumer Electronics Show, Las Vegas)
Event Overview: CES is one of the largest and most influential technology conventions in the world, held annually in Las Vegas. It draws over 180,000 attendees and features over 4,500 exhibitors, showcasing the latest innovations in consumer technology.
Key Risks:
Logistical and Operational Risks (Crowd Management and Venue Capacity)
  Example: Given the size of CES, there are significant risks related to managing the flow of tens of thousands of attendees across multiple venues.
  Risk Mitigation:
    CES uses a multi-venue strategy, spreading out across several large venues in Las Vegas (e.g., Las Vegas Convention Center, Sands Expo, and hotels).
    CES utilizes a dedicated transportation plan, including shuttle buses, to reduce congestion.
    Pre-event digital registration and scheduling help alleviate long queues and overcrowding at the venue.

## Slide 39
Technological Infrastructure Risks
  Example: The event’s emphasis on cutting-edge technology means that Wi-Fi and internet connectivity must be flawless, particularly with demonstrations of virtual reality, live-streamed presentations, and AI-driven devices.
  Risk Mitigation:
    CES invests heavily in IT infrastructure to ensure that all exhibitors and attendees have reliable access to high-speed internet.
    Backup systems are also in place to minimize downtime and technical issues.
Reputation and Brand Risks (Security of Sensitive Technology)
  Example: Given that many of the world’s top tech companies showcase proprietary technology at CES, there is always a risk of corporate espionage, hacking, or the premature release of intellectual property.
  Risk Mitigation:
    CES enforces strict security protocols, including limiting access to certain areas and requiring NDAs (Non-Disclosure Agreements) for high-profile launches.
    On-site security, RFID badge tracking, and high-level data protection systems are in place to protect exhibitors.
  Lessons Learned:
CES has grown into a globally recognized tech event by focusing on logistical excellence, technological reliability, and stringent security protocols. Their ability to manage a large-scale event spread across multiple venues ensures continued success.

## Slide 40: Bidding
Business Events Growth Programme - VisitBritain promotes business event tourism
Business Events Growth Programme | VisitBritain.org
Bid Enhancement & Support - specifically supports the bidding process for an international business event not currently held in the UK.
UK City of Culture 2025: The five Welsh areas bidding for the title - BBC News

## Slide 41: Meet In Wales
Meet In Wales Homepage| Meet In Wales
promoting Wales as a destination for meetings, incentives, team building, events and conferences.
Tourism - UK breaks and family holiday destinations | Visit Wales
Events – The National Events Strategy for Wales 2022 to 2030 | GOV.WALES

## Slide 42: The strategic planning process and event organisation
Formation of a bidding body and bid preparation
Developing a timeline for the bid document
Responding to each of the bid criteria
Identifying key elements of past successful bids
Preparing the bid document
Presenting the bid
Lobbying in support of the bid
Evaluating reasons for a bid failure

## Slide 43: Contents of the event proposal
What should be included in an event proposal template?
Each event is unique, add a couple of extra sections that are specific to your vision/ event . But as a bare minimum, include:
An introduction
Event objectives
Event overview
Budget
Event marketing and promotion
Sponsorship
Evaluation and feedback
Each of these sections plays an important role in creating a holistic narrative around the event.
https://www.eventbrite.co.uk/blog/how-to-write-an-event-proposal-ds00/
(Source: O’Toole, 2004)

## Slide 44: The strategic planning process and event organisation
Establishment of an organisational structure
Simple structures
Functional structures
Program-based matrix structures
Multi-organisational or network structures

## Slide 45: What is strategic planning?
Define their long-term goals and objectives and develop a plan of action to achieve them.
It involves assessing the organization's current position, analysing external factors such as market trends and competition, and identifying strengths, weaknesses, opportunities, and threats (SWOT analysis).
Helps organisations make informed decisions about allocating resources, setting priorities, and defining strategies to achieve their desired outcomes.

## Slide 46: The strategic planning process and event organisation
(Source: adapted from Grant, 2005)

## Slide 47: Simple structure …..

## Slide 48
(Source: Roskilde Festival, 2006)

## Slide 49: 2006 Melbourne Commonwealth Games organisational structure
(Source: Office of Commonwealth Games, 2006)

## Slide 50: Structure of an event management team
(Source: Sloman, 2006)

## Slide 51: A network structure

## Slide 52: The strategic planning process and event organisation
Strategic plan
Purpose, vision and mission statements

## Slide 53
The Glastonbury Festival aims to encourage and stimulate youth culture from around the world in all its forms, including pop music, dance music, jazz, folk music, fringe theatre, drama, mime, circus, cinema, poetry and all the creative forms of art and design, including painting, sculpture and textile art.
https://www.glastonburyfestivals.co.uk/information/an-introduction-to-glastonbury-festival/the-festivals-objectives/
TASK:
Have a look at the mission statement of a local and an international festival
an event
A conference

## Slide 54
https://www.majorevents.govt.nz/about/strategy/
Vision
Our major events benefit all people who call Aotearoa New Zealand home.
Strategy
The government invests in major events that generate significant immediate and long-term benefits and align with wider government objectives through leverage and legacy opportunities.

## Slide 55: The strategic planning process and event organisation
Strategic plan
Goals and objectives
  economic
  attendance/participation
  quality
  awareness/knowledge/attitudes
  human resources
https://www.ifea.com/

## Slide 56: Examples...
Taste of London UK
Equality is creating an even platform to enable everyone to access the same opportunities and is backed by legislation to prevent discrimination based on prejudices against any group.
Diversity is understanding and valuing the differences in people and believing that harnessing these differences will create a productive working environment and an enriching life experience where talents are fully utilised and organisational goals are met.
Taste of London is an event that welcomes and can accommodate all visitors despite some of the challenges of being staged in a park and the temporary nature of the event.
https://london.tastefestivals.com/access-equality/

## Slide 57: SMART Objectives
Specific: focused on achieving an event goal or, if no goals have been developed, its purpose
Measurable: expressed in a way that is quantifiable
Agreeable: agreed on by those responsible for achieving them
Realistic: in terms of the event organisation having the human, financial and physical resources to achieve them
Time specific: to be achieved by a particular time

## Slide 58: The strategic planning process and event organisation
Strategic plan
Situation analysis
Identification of strategy options
Strategy evaluation and selection
Operational planning

## Slide 59: Situation Analysis
Consider your UK destination and the event

## Slide 60: Situational analysis 5 ‘C’s
(Corporate finance institute, 2022)
Notes: When approaching this section of your Situational analysis section of SOSTAC it is useful to consider the 5C’s
This is internal and external, today we look at the first two,

## Slide 61: Analysis
What do we sell?
USP?
How do we differ from competitors?
What are our sources of competitive advantage?
What are our current goals?
Are we meeting customer needs?

## Slide 62: Situation analysis
Political/legal
Economic
Social/cultural
Technological
Demographic
Physical/environmental
Competitive

## Slide 63: The strategic planning process and event organisation
Legacy
Legacy outcomes can include infrastructure improvements, increases in tourism, enhanced workforce skills etc

## Slide 64: Strategic planning for existing events
For recurring events (e.g. annual concerts), organisers:
  conduct an appraisal of current situation faced by the event
  review the organisational structure and previous strategic plan and make minor or major changes where needed

## Slide 65: Summary
Strategic planning process provides an event organisation with a systematic approach to the challenge of planning and delivering successful events.
Preliminary stages involve the decision to proceed or not to proceed with an event.
Appropriate organisational structure is needed
An event organisation following the strategic planning model would then progress to establish a strategic plan.
Flowing from the implementation , depending on its mission or purpose, will potentially be a range of legacies.

## Slide 66: References
Bath Festivals Trust (2005). About Us. (Internet) Available from: <http://www.bathmusicfest.org.uk/pages/about.php> (accessed 3 August 2005)
Boscombe Arts Festival (2006). About Us. (Internet) Available from <http://barfruit.co.uk/boscombeartsfestival/about.php> (accessed 16 April 2010)
Grant, R. (2005). Contemporary Strategy Analysis. Melbourne, Blackwell.
O’Toole, W. (2004). Event Project Management System. Sydney, EPMS.net. (Multimedia: CD-ROM).
Manchester 2002 (2003). 2002 Manchester The XVII Commonwealth Games: Post Games Report. London, Commonwealth Games Federation.
Salford Film Festival (2010). Mission Statement and Aims. (Internet) Available from <http://www.salfordfilmfestival.org.uk/p.asp?ID¼10> (accessed 12 March 2010).

## Slide 67: References (continued)
SeaBritain 2005 PressOffice (2004). SeaBritain 2005 e Take a Fresh Look at the Sea. Press Release, 1 October. <http://www.seabritain2005.com/server.php?show=ConWebDoc.116> (accessed 9 August 2005).
Sloman, J. (2006). Project Management (Course Notes). Major Event Management Program 9-14 June, Sydney, Sport Knowledge Australia.
Windsor Festival (2010). About Windsor Festival. (Internet). Available from <http://www.windsorfestival.com/about/> (accessed 12 April 2010).
Worcester Festival (2005). Welcome to Worcester Festival 2005. [Internet] Available from <http://www.worcesterfestival.co.uk/about_the_festival.asp/> (accessed 13 March 2010).