Managing Projects in the Organisation

Wedding Management Plan

Student name: Yana Asenova

Student number: 1919002

Module name : Managing Projects in the Organisation

Module code: BMSW 5104

Tutor’s name: Yajesh Kumar

Introduction

“Adore Agency” is small boutique agency, organizing different kind of events- weddings, private parties, cocktails and various of family gatherings. The agency offers full or partial event planning. The vision for organizing events is always created according to the values ​​of the client and based on the long experience of the team. As the manager of the organization, I am facing new challenges related to the changing Covid-19 situation. Which requires a change in the organization of management of our projects.

The purpose of this project is to organize a wedding event. The different stages that the organization goes through, what activities include the individual stages, what is their duration and others are considered. Graphically, this is presented through the development of network models and a Gantt chart of the project.

The presented project includes the most important activities in organizing a wedding event. The main points, their duration and content, approximate budget and other guidelines useful for the organization are indicated.