## Initial Risk Assessment templat
Category | Risk | Likelihood | Impact | RAG status | Risk Management Approach/ Mitigating Actions | Early Warning Signs
For larger risk assessments/ logs it may be useful to group risk together inmto categories | Presented in a structured format: - Condition - 'There is a risk that' - Cause - 'Caused by' - Consequence - 'Resulting in’ | What is the likelihood/ probability of the risk occurring? | What will the impact be if the risk occurs? | RAG (Red, Amber, Green) status, based on the product of the probability and impact | What are the agreed response actions? These may be broken into: preventative actions to mitigate the risk and the response action if the risk actually occurs. This is sometimes known as an 'Impact Plan' | What 'trigger' might alert you to the fact that the risk is about to occur? In some cases you may only choose to spend money on a response action once the trigger occurs.
Skills | Inadequate coverage of skills caused by inability to recruit suitably-qualified staff resulting in resourcing/scheduling issues | Low (2) | Very High (5) |  | Ensure remuneration is appropriate to skill level. | Low numbers of poorly-qualified applicants. Repeated advertisements.
Skills | Unable to retain staff due to unattractive prospects resulting in significant staff 'churn' | Medium (3) | Medium (3) |  | Motivation via contractual terms, good job design, good working environment and personal development opportunities. Consider contractual retention clauses for key staff. | Low morale. High staff turnover.
Management | Parties do not share understanding of purpose, due to lack of clarity, resulting in poor buy-in | Low (2) | High (4) |  | Definition of stakeholder needs and clear plan with well-defined deliverables. Use of sound project management methodology. | Differing views on forward plan. Confused messages in draft publications. Non-attendance at meetings
Management | Poor environment caused by lack of appropriate facilities, resulting in poor atmosphere/morale | Medium (3) | Very High (5) |  | Consider innovative use of space within accommodation constraints and possibilities of sharing resources with other offices. | Delay to work plans caused by lack of facilities.

## Risk Log template
Unique ID | Category | Risk | Likelihood | Impact | RAG status | Timescale | Cost | Owner | Risk Management Approach/ Mitigating Actions | Residual Risk | Early Warning Signs
This may be simply a title but some kind of alphanumeric coding may be useful where you are dealing with a large number of risks. | For larger risk assessments/ logs it may be useful to group risk together inmto categories | Presented in a structured format: - Condition - 'There is a risk that' - Cause - 'Caused by' - Consequence - 'Resulting in’ | What is the likelihood/ probability of the risk occurring? | What will the impact be if the risk occurs? | RAG (Red, Amber, Green) status, based on the product of the probability and impact | What is the 'Risk Window' when this risk may occur and when do you start to lose options as to how you respond? | What will the risk cost if it does occur? N.B. You can't assess this unless you know what your response action will be. | There should be a person nominated to 'own' the risk which means monitoring the situation and ensuring that necessary management actions are carried out. In a project situation this should be somebody within the project team and in all cases it should be somebody who will be impacted by the risk and who has a vested interest in addressing it. | What are the agreed response actions? These may be broken into: preventative actions to mitigate the risk and the response action if the risk actually occurs. This is sometimes known as an 'Impact Plan' | This is the expected level of risk once all the mitigating actions are complete. | What 'trigger' might alert you to the fact that the risk is about to occur? In some cases you may only choose to spend money on a response action once the trigger occurs.
EXAMPLE1 | Skills | Inadequate coverage of skills caused by inability to recruit suitably-qualified staff resulting in resourcing/scheduling issues | Low (2) | Very High (5) |  | Project start-up | Delays in project (could be costed with the right background info) | Senior Responsible Officer | Ensure remuneration is appropriate to skill level. | Risk of staff leaving at critical point later in the project should there be a lack of future prospects internally | Low numbers of poorly-qualified applicants. Repeated advertisements.
EXAMPLE2 | Skills | Unable to retain staff due to unattractive prospects resulting in significant staff 'churn' | Medium (3) | Medium (3) |  | Project duration | Delays in project (could be costed with the right background info) | Senior Responsible Officer | Motivation via contractual terms, good job design, good working environment and personal development opportunities. Consider contractual retention clauses for key staff. | Slight risk of poor performance for staff 'trapped' by contract retainer | Low morale. High staff turnover.
EXAMPLE3 | Management | Parties do not share understanding of purpose, due to lack of clarity, resulting in poor buy-in | Low (2) | High (4) |  | Project duration | Delays in project (could be costed with the right background info) | Senior Responsible Officer | Definition of stakeholder needs and clear plan with well-defined deliverables. Use of sound project management methodology. | Risk of key senior personnel in stakeholder departments changing during course of project | Differing views on forward plan. Confused messages in draft publications. Non-attendance at meetings
EXAMPLE4 | Management | Poor environment caused by lack of appropriate facilities, resulting in poor atmosphere/morale | Medium (3) | Very High (5) |  | Project start-up | Delays in project (could be costed with the right background info) | Senior Responsible Officer | Consider innovative use of space within accommodation constraints and possibilities of sharing resources with other offices. |  | Delay to work plans caused by lack of facilities.

## EXAMPLE1 Progress log
EXAMPLE1
Category | Risk
Skills | Inadequate coverage of skills caused by inability to recruit suitably-qualified staff resulting in resourcing/scheduling issues
Date | Progress
2012-09-14 | Requests for regrading submitted to HR