TOPIC: A Structure Project Management Approach to Scheduling, Risk and cost control for Four-Storey Residential Building Development

STUDENT: SMEETKUMAR PRAJAPATI (2505418)

PROJECT MANAGEMENT(ACHA7025)

2026

Table Of Content

1. INTRODUCTION AND BACKGROUND OT THE PROJECT	3

2.0 CONSTRUCTION OF A NETWROK DIAGRAM AND GANTT CHART	4

2.1 WORK BREAKDOWN STRUCTURE (WBS) AND ACTIVITY IDENTIFICATION	4

2.2 SECTION DETAIL ACTIVITY	4

2.3 CRITICAL PATH METHOD	5

2.4 NETWORK DIAGRAM	6

3.  APPLICATION OF PERT ANALYSIS AND RISK MANAGEMENT TECHNIQUES	7

3.1 PROGRAM EVALUATION AND REVIEW TECHNIQUE	7

3.2 RISK MANAGEMENT TECHNIQUES	8

3.3 RISK REGISTER	8

3.4 RISK RESPONSE STRATEGIES	10

3.5 MONITORING AND CONTROL OF RISKS	10

4 ROLE OF COMMUNICATION	11

4.1 IMPORTANCE OF COMMUNICATION IN CONSTRUCTION PROJECT MANAGEMENT	11

4.2 KEY STAKEHOLDERS AND COMMUNICATION REQUIREMENTS	11

4.3 COMMUNICATION METHOD AND TOOLS	12

4.4 COMMUNICATION PLAN	12

4.5 RESPONSIBILITY ALLOCATION (RACI APPROACH)	13

5.0 COST OF THE INDIVIDUAL ACTIVITIES AND TOTAL COST OF THE PROJECT	14

5.1 APPROACH TO COST ESTIMATION	14

5.2 ESTIMATED COST OF INDIVIDUAL ACTIVITIES	14

5.4 CRITICAL DISCUSSION & COST CONTROL METHOD	16

6.0 APPLICATION OF CRASH COSTING TECHNIQUE	17

6.1 PURPOSE AND CONTEXT OF CRASH COSTING	17

6.2 IDENTIFICATION OF CRASH CRITICAL ACTIVITIES	17

6.3 NORMAL AND CRASH DATA FOR SELECTED ACTIVITIES	18

6.4 COST SLOPE CALCULATION	18

6.5 CRASHING STRATEGY AND SCHEDULE REDUCTION	18

6.6 PROGRAMME DURATION AND PROJECT COST	19

6.7 CRITICAL EVALUATION OF CRASH COSTING	20

7.0 CONSIDERATION OF EFFECTIVE PROJECT HANDOVER ISSUES	21

7.1 IMPORTANCE OF EFFECTIVE PROJECT HANDOVER	21

6. Conclusion	23

References	24

Appendices	26

APPENDIX A:  ACTIVITY LIST (DURATION AND PREDECESSORS)	26

APPENDICES B	29

APPENDICES C:  COST SLOPE CALCULATION	32

# 1. INTRODUCTION AND BACKGROUND OT THE PROJECT

The delivery of a four-story residential building (926 sq.m) required planning because the construction sequence is strongly dependent on structural progress, access between floor and the coordination of multiple subcontractor packages. This report is covered all activities from early planning through to final completion and handover. The project scope includes site mobilization, excavation and foundation, structural frame construction across four levels, roof work, external walls and window installation to achieve a weather-tight building, first and second fix mechanical, electrical and plumbing works, internal partitions and finishes, testing and commissioning, statutory inspections and handover documentation.

The structural frame typically drives the overall programmed, as follow activities such as external envelope works and internal fit-out depend on floor-to-floor progress. Achieving a weather-tight milestone is particularly important because it enables internal trades to work efficiently and helps protect material and finished surfaces form damage. In addition, MEP first fix activities must be completed and inspected before drylining and plasterboard installation, while second fix works and commissioning can only be completed once finishes and equipment are installed. These dependencies create a high risk of delay if sequencing is not managed properly or if rework is required due to quality issues.

The purpose of this assessment is to demonstrate how project management techniques can be applied to produce a realistic baseline plan and support effective control during delivery. The report first develops a detailed activity schedule and logical dependencies, then produces a network diagram and Gantt chart to identify the critical path using the critical path method (CPM) and key duration is considered through the program evaluation and review technique (PERT), that identifies major project risk and suitable response action. The role of communication is also examined to show how progress reporting, coordination meeting and clear responsibility allocation improve site performance and reduce misunderstandings.

The assessment then allocates estimated costs to individual activities and calculates the total project cost. A time-cost trade-off analysis is carried out using crash costing to reduce the overall programmed by 7 days and focusing on selected critical activities that can be accelerated through additional resources or extended working hours.

# 2.0 CONSTRUCTION OF A NETWROK DIAGRAM AND GANTT CHART

# 2.1 WORK BREAKDOWN STRUCTURE (WBS) AND ACTIVITY IDENTIFICATION

A work breakdown structure is used to break the four-story residential building project into manageable packages so that activities can be planned, sequence and control.

- Pre-construction and approvals

- Site setup and enabling works

- Substructure (excavation, drainage, ground slab)

- Superstructure (frame construction across levels)

- External envelope and weather-tight milestone

- Mechanical, electronic and pluming service-first and second fix

- Internal partition and finishes

- Testing, commissioning, inspections and handover

# 2.2 SECTION DETAIL ACTIVITY

Section detailed activity is provided in Appendices A

# 2.3 CRITICAL PATH METHOD

The critical path method applies to determine the project duration and identify the activities that directly control completion. CPM uses two calculation a forward pass to calculate the earliest possible activity dates and a backward pass to calculate the latest allowable without delaying the project. The difference between these dates is used to calculate total float, which identifies the critical path.

the total project duration of 201 days and the critical path is defined by the activities with zero total float

Forward and backward pass calculations are provided in Appendices B

# 2.4 NETWORK DIAGRAM

# 3.  APPLICATION OF PERT ANALYSIS AND RISK MANAGEMENT TECHNIQUES

# 3.1 PROGRAM EVALUATION AND REVIEW TECHNIQUE

The PERT is used in project management to estimate activity durations when there is uncertainty. In construction projects, time estimates can very due to factors such as labour productivity, inspection delays, design clarification, material lead times and weather condition. PERT improves planning reliability by using OMP (optimistic time, most likely time, pessimistic time).

TE=O+4 ML+P6

O= Optimistic duration

M= most likely duration

P= pessimistic duration

For a four-story residential building project, activities affected by uncertainty include approvals, excavation, façade installation and MEP works.

| Activity | Optimistic | Most likely | Pessimistic | Expected time days |
| --- | --- | --- | --- | --- |
| A4- design coordination | 8 | 10 | 12 | (8+4x10+12)/6 =10 |
| C1- excavation | 8 | 10 | 12 | 10 |
| D1- Structural frame | 13 | 16 | 19 | 16 |
| E1- External cladding | 12 | 15 | 18 | 15 |
| F1- MEP first fix | 8 | 10 | 12 | 10 |

# 3.2 RISK MANAGEMENT TECHNIQUES

Risk management is a structured process used to identify, analyse and control uncertainties that may affect project objectives. In this project, Risk management focuses on achieving time performance, cost control, quality compliance, health and safety, client satisfaction and successful handover.

- Risk identification: recognizing possible issues that may occure

- Risk analysis: assessing probability and impact

- Risk response planning: selecting strategies to manage risks

- Monitoring and review: tracking risks through the project lifecycle.

# 3.3 RISK REGISTER

A risk register is used to record the key project risks, their causes, impacts and planned response strategies.

| Risk | Cause | Potential impact | probability | impact | Response strategy | owner |
| --- | --- | --- | --- | --- | --- | --- |
| Planning/ Approval delay | Extended review time | Delay mobilisation & start | Medium | High | Follow-up | Project manager |
| Unexpected Ground condition | Poor soil/hidden services | Cost increase & delay | Medium | High | Ground investigation & contingency | Site engineer |
| Supply chain delay | Material shortage | Delay to facade | Medium | High | Early ordering/ backup suppliers | Procurement lead |
| Severe weather | Rain/wind condition | Delay roof and envelope work | Medium | medium | Temporary protection, rescheduling | Project manger |
| Labour shortage | Limited skilled trades | Reduce productivity | Medium | High | Subcontractor support, overtime plan | Project manager |
| Health and safety incident | Unsafe practice | Work stoppage /investigation | Low | Very High | Supervision, toolbox talks | H&S officers |
| Design variation | Coordination change | Rework/additional cost | Medium | High | Formal change control | Project manager |
| Poor quality workmanship | Lack of inspection | Defects/rework | Medium | Medium | Inspection, hold point, | Site engineer |
| MEP clashes | Poor coordination | Rework behind finishes | Medium | High | Coordination drawing & checks | MEP coordinator |
| Final inspection failure | Incomplete work/ certificates | Delay to handover | Low | High | Pre-inspection & document tracking | Project manager |

# 3.4 RISK RESPONSE STRATEGIES

The main risk response strategies are considered as avoidance, mitigation, transfer and acceptance.

- Avoidance: changing the plan to remove the risk

- Mitigation: reducing the probability or impact of the risk

- Transfer: responsibility shifting through contractual or insurance method

- Acceptance: The risk is accepting while preparing contingency actions

The mitigation is the most relevant strategy because construction risks cannot be fully removed, but their effects can be reduced through planning and management controls. For instance, supply chain risks can be mitigated through early procurement of long-lead items while quality risks can be mitigated through inspection before works are closed.

# 3.5 MONITORING AND CONTROL OF RISKS

Risk monitoring is essential to ensure that risks remain controlled throughout the project. Practical action that supports risk control such as

- Weekly review of the risk register during progress meetings

- Tracking procurement and delivery dates for critical materials

- Mitigation actions updating when site condition change

- Maintain a snagging and inspection checklist

- Regular health conducting and safety briefings and audits

This approach ensure that project risks are manged proactively rather than reactively, supporting successful completion and handover.

# 4 ROLE OF COMMUNICATION

# 4.1 IMPORTANCE OF COMMUNICATION IN CONSTRUCTION PROJECT MANAGEMENT

Effective Communication is essential in construction project management because the project involves multiple stakeholders, parallel work packages and strict requirement for safety, quality and compliance. For a four-story residential building project, poor communication can lead to misunderstandings in drawing, delayed decision, rework, safety incidents and programmed slippage. In contrast, clear communication improves coordination between the project team and supply chain, support timely approvals, reduces the likelihood of disputes and helps ensure that the project meets client expectations.

Construction project typically require communication at different levels including strategy updates for the client, design coordination with consultants, daily instruction for subcontractors and formal reporting for statutory stakeholders.  Therefore, communication must be planned and controlled using structured method rather than relying on informal discussions.

# 4.2 KEY STAKEHOLDERS AND COMMUNICATION REQUIREMENTS

Client/developer: requires regular progress and cost updates

Project manager: responsible for overall delivery and decision making

Site engineer and site supervisors: responsible for daily coordination and quality checks

Subcontractors: requires clear work instruction and access planning

Suppliers: require delivery schedules and storage information

Design team:  Architect, structure engineer, service engineer require update on site constraints and technical queries

Building control: require inspection requests and compliance evidence

Health and safety personnel: require safety briefing and incident reporting

# 4.3 COMMUNICATION METHOD AND TOOLS

Meeting: Confirm scope, responsibilities and key constraints at the start

Daily briefing/toolbox talk: site meeting to allocate work and review safety controls

Weekly progress meeting: review programmed, risks, procurement status and key issues

Two-weekly design coordination meeting: resolve technical issues and design clashes

Email and formal written instruction: records approvals and avoids misunderstandings

Request for information: formal process to clarify drawing/specifications

Meeting minutes and action tracker: ensures accountability for decisions

Progress reporting: includes schedule updates, look ahead plans and issue logs

Change control communication: confirm that changes are approved before execution

These methods ensure that project communication is traceable, consistent and aligned with contractual and compliance requirements.

# 4.4 COMMUNICATION PLAN

A communication plan provides a structured approach to ensure the right information reaches the right stakeholders at the right time.

| Stakeholder | Information required | Format/method | Frequency | Responsible person |
| --- | --- | --- | --- | --- |
| Client/ developer | Progress, risk, cost, changes, milestone | Progress report & meeting | Weekly | Project manager |
| Design team | Design updates, coordination issues | RFI Log/meeting | Fortnightly | Pm/ site engineers |
| subcontractors | Daily tasks, access sequencing, safety | Site briefing/ toolbox talks | daily | Site supervisor |
| suppliers | Delivery dates, offloading needs, storage. | Email/ phone & delivery schedule | Weekly/ before delivery | Procurement lead |
| Building control | Inspection requests and compliance evidence | Inspection request/ checklist | As required | PM |
| H&S team | Audits, incident reporting, safety updates | H&S briefing, report | Weekly/ daily checks | H&S officer |

Communication matrix ensures that coordination is proactive and reduces the risk of delays due to missing information or late decisions.

# 4.5 RESPONSIBILITY ALLOCATION (RACI APPROACH)

To reduce confusion and improve accountability, responsibilities can be defined using the RACI matrix.

R= responsible A= accountable   C= consulted      I= informed

The project manager is typically accountable for programmed and cost control, while the site manager is responsible for technical execution and daily coordination. Subcontractors are responsible for delivering their packages safely and to specification, while the client is kept informed through formal progress reporting.

In this four-story residential building project, communication is a critical management function that support successful delivery by improving coordination, preventing errors, managing stakeholders and ensuring compliance. A structured communication plan, supported by formal documentation such as RFI, meeting minutes and progress reports, improve project transparency and reduces the rework, delay and disputes.

Cost of the individual activities and total cost of the project.

# 5.0 COST OF THE INDIVIDUAL ACTIVITIES AND TOTAL COST OF THE PROJECT

# 5.1 APPROACH TO COST ESTIMATION

Cost estimation is a key control function in construction project management because it supports budgeting, procurement decisions and financial monitoring throughout delivery. The project cost is developed using an activity- based costing approach, where estimated costs are allocated to each major activity in the programme. It aligns the cost model with the schedule structure and allows direct comparison between time performance and expenditure.

The cost values used are indicative allowances based on construction resource requirements and subcontract packages. They are not intended to represent a tender or final commercial quotation instead they provide a realistic baseline for demonstrating cost analysis techniques and supporting the later application of crash costing within the time-cost trade-off section.

The activity costs consider direct cost components such as labour, material, plant and subcontract services. Wider commercial factors such as developer profit, financing and long-term operational costs are outside the scope of this assessment and are therefore excluded.

# 5.2 ESTIMATED COST OF INDIVIDUAL ACTIVITIES

The estimated cost allocation across the key project activities. The cost have been structured to reflect realistic work packages typically found on a four-story residential building project, including pre-construction, substructure, superstructure, envelope, building services and finishes.

| NO | Activity | Estimated cost |
| --- | --- | --- |
| A4 | Design co ordination | 20,000 |
| A5 | Planning approval allowance | 12,000 |
| A7 | Procurement setup subcontract appointments | 5,000 |
| B1 | Mobilization & temporary services | 18,000 |
| B2 | Hoarding, welfare, H&S setup | 22,000 |
| C1 | Excavation | 45,000 |
| C3 | Foundation reinforcement & formwork | 60,000 |
| C4 | Foundation Concrete pour | 85,000 |
| C6 | Below ground drainage | 35,000 |
| C7 | Ground floor slab concrete | 70,000 |
| D | Structure frame (D1-D4 | 480,000 |
| D6 | Roof structure | 65,000 |
| E1 | External walls/cladding | 240,000 |
| E2 | Window & external door | 130,000 |
| E3 | Roof waterproofing | 20,000 |
| F | MEP first fix works(F1-F4) | 220,000 |
| G | Partitions, drylining, plastering, screed(G1-G4) | 180,000 |
| H | MEP second fix work (H1-H3 | 200,000 |
| H2 | Joinery, flooring, painting, kitchen, bathrooms (H4-H8) | 320,000 |
| I | Testing, commissioning, snagging & handover (I1-I5) | 85,000 |

Subtotal = 2,292,000

Contingency (5%) x 2292000 =114,600

Total cost =2,292,000 + 114600 = 2,406,600

The total baseline project cost is calculated by summing the estimated cost of the individual activities. This provides a cost baseline aligned with the schedule and support later time-cost trade-off analysis. A contingency allowance is added to reflect normal construction uncertainty and minor variation that may occur during delivery.

# 5.4 CRITICAL DISCUSSION & COST CONTROL METHOD

The cost model developed provides a structured estimate that support planning and decision-making. However, it should be recognized that construction costs are sensitive to programmed changes, productivity variance and procurement lead times. Accelerated programmed may increase labour costs due to overtime and additional supervision requirements, while extended duration can increase time-related site overheads such as temporary facilities and management costs.

To manage costs during project delivery, the project team would implement structured cost control measures such as,

- Monthly valuation and cost reporting aligned to work completed

- Procurement tracking against budget allowances

- Variation and change control to prevent uncontrolled scope growth

- Forecast-to-complete review to identify trends early

- Monitoring of labour productivity, especially during programme acceleration

These controls ensure that cost increases are identified early and managed proactively rather than being discovered late during project close-out.

# 6.0 APPLICATION OF CRASH COSTING TECHNIQUE

# 6.1 PURPOSE AND CONTEXT OF CRASH COSTING

Crash costing is a schedule compression technique used to reduce project duration by accelerating selected activities at an additional cost. It is typically applied when programme constraint exists, such as contractual deadlines or strategic requirements for early completion. Crash costing is applied to achieve a 7-day reduction in the overall project duration.

The baseline programme, developed using the critical path method, indicates a normal project duration of 201 working days, with a corresponding baseline cost of 2,406,600. Since only activities on the critical path influence the project completion date, the crash costing exercise is restricted to critical path activities. This ensures that schedule reduction directly translate into overall programme savings rather than consuming available float on non-critical activities.

# 6.2 IDENTIFICATION OF CRASH CRITICAL ACTIVITIES

Following CPM analysis, the critical path includes key construction activities that govern project completion, such as substructure works, structural frame progression, external envelope installation, internal drylining and finishing, and final testing and commissioning. Not all critical activities are suitable for crashing. Therefore, only those that can be realistically accelerated through additional labour resources, extended working hours, parallel task execution or increased plant utilization.

Activities constrained by technical sequencing, statutory inspection or curing requirements are not reduced beyond safe and practical limits. This approach ensures that acceleration decision remain realistic and do not compromise construction quality or safety.

# 6.3 NORMAL AND CRASH DATA FOR SELECTED ACTIVITIES

| Activity | Normal duration | Crash duration (days) | Normal cost £ | Crash cost £ |
| --- | --- | --- | --- | --- |
| Excavation | 6 | 5 | 45,000 | 50,000 |
| Foundation/reinforcement & formwork | 6 | 5 | 60,000 | 68,000 |
| Structure frame | 8 | 7 | 120,000 | 135,000 |
| Windows & external doors | 8 | 7 | 130,000 | 145,000 |
| Drylining & plasterboard | 10 | 9 | 100,000 | 110,000 |
| Painting & decorating | 10 | 9 | 90,000 | 100,000 |
| Testing & commissioning | 6 | 5 | 85,000 | 95,000 |

# 6.4 COST SLOPE CALCULATION

Cost slope calculation is provided in appendices C

# 6.5 CRASHING STRATEGY AND SCHEDULE REDUCTION

To minimize the increase in project cost, activities with the lowest cost slope are crashed first and remain on the critical path after each reduction. The programme is reviewed following each time reduction to confirm that no alternative critical path emerges.

| Activity | Days | Additional cost £ | Cost slope £/day |
| --- | --- | --- | --- |
| Excavation | 1 | 5,000 | 5,000 |
| Foundation reinforcement & formwork | 1 | 8,000 | 8,000 |
| Drylining & plasterboard | 1 | 10,000 | 10,000 |
| Painting & decorating | 1 | 10,000 | 10,000 |
| Testing & commissioning | 1 | 10,000 | 10,000 |
| Window & external doors | 1 | 15,000 | 15,000 |
| Structure frame | 1 | 15,000 | 15,000 |

# 6.6 PROGRAMME DURATION AND PROJECT COST

Original duration = 201 days

Revised duration = 201 – 7 = 194 days

Total additional crash cost = 73,000 £

Crash project cost = 2,406,600 + 73,000 = 2,479,600 £

# 6.7 CRITICAL EVALUATION OF CRASH COSTING

The application of crash costing in this project successfully achieves the required 7-day reduction; however, this reduction is not achieved without significant implications for cost, labour management, safety and quality control. This four-story residential building project, the acceleration strategy relies primarily on additional labour resources, overtime working and parallel task execution. While these measures reduce activity durations, they also increase direct labour costs and place additional pressures on site supervision and coordination.

From cost perspective, the crash costing exercise results in an additional 73,000 £ representing a noticeable increase over the baseline cost. Although this increase may be considered acceptable to meet programme requirement, it highlights that time savings are achieved at a disproportionately higher marginal cost per day as the project approaches completion and that further compression beyond the 7-day target would likely become increasingly inefficient, as remaining activities would have higher cost slopes and greater operational constraints.

Health and safety implication are significant when programme acceleration is present also overtime and parallel working increase the risk of fatigue related incidents particularly finishing and commissioning stages where multiple trades operate concurrently in confined internal spaces. In result additional site supervision, stricter permit to work control and enhanced coordination would be required to prevent safety non-compliance.

# 7.0 CONSIDERATION OF EFFECTIVE PROJECT HANDOVER ISSUES

# 7.1 IMPORTANCE OF EFFECTIVE PROJECT HANDOVER

Project handover represents the transition from confirmation completion to client occupation and operation. In this four-story residential building project, ineffective handover could undermine the benefits gained through programme acceleration by delaying occupation, increasing post- completion defects or damaging client satisfaction. Therefore, handover must be treated as a controlled management process rather than a single end-stage activity.

2.TESTING, COMMISSIONING AND COMPLIANCE

Before handover, all mechanical, electrical and plumbing system must be fully tested and commissioned to demonstrate safe and compliant operation. Accelerate programs can compress commissioning window, the risk that incomplete testing or unresolved defects are carried forward into occupation. To mitigate this risk, commissioning activities must be planned early, sequenced logically with second fix works and supported by inspection checklists and certification tracking.

3.SNAGGING, DEFECTS AND QUALITY CONTROL

Snagging and defect rectification are critical handover activities, particularly in residential projects where finish quality is highly visible. Programme acceleration increases the risk of defects due to overlapping trades and reduced curing or drying periods. In this project a phased snagging strategy, combined with early by are inspection would reduce the concentration of defects at the final stage and improve overall quality outcomes.

4. DOCUMENTATION AND CLIENT ACCEPTANCE

Successful handover requires the delivery of complete and accurate documentation, including operations and maintenance manual, warranties, test certificate and as-built drawings, inadequate document control can delay client acceptance even if physical works are complete. Therefore, documentation preparation should progress in parallel with construction activities rather than being left until the final stage.

Formal client acceptance should be based on predefined completion criteria, including system performance, defect closure and certification completeness. This structured approach reduces the risk of disputes and supports a smoother transition into occupation.

5. CRITICAL EVALUATION

The benefits gained through schedule acceleration could be compromised if handover activities are treated as secondary priorities. Crash costing increases pressure on finishing and commissioning stages, making early quality checks and documentation control essential. A failure to manage handover effectively could result in delayed occupation, reputational impact and additional post-completion costs, offsetting the advantages of early completion.

# 6. Conclusion

This report has demonstrated how structured project management technique can be applied to plan, control and optimize the delivery of four-story residential building project. The development of a logically sequenced programme using the critical path method enabled identification of activities that directly govern project completion and provided a realistic baseline decision.

The integration of PERT analysis and risk management highlight the uncertainty inherent in construction activities and reinforced the importance of proactive planning, particularly for works affecting the critical path. Activity based cost planning established a practical financial baseline aligned with the programme allow meaningful evaluation of time-cost trade-off rathe than isolated schedule or cost decision.

The application of crash costing achieved the required 7-day programme reduction, but the analysis demonstrated that acceleration is accompanied by increased cost, labour pressure and heightened safety and quality risk. This confirm that schedule compression should be applied selectively and supported by enhanced supervision, safety control and quality management. The consideration of handover requirements further emphasized that early completion only delivers value when commissioning, documentation and defect management control.

Overall, the successful construction management depends on balancing time cost, safety and quality through informed professional judgement. The approach adopted provides a realistic framework for managing a multi-story residential project and support effective decision making across the project lifecycle.

# References

- Maylor, H. and Turner, N. (2022) Project management. Fifth edition. Harlow: Pearson.

- Li, L. et al. (2025) “Meta-knowledge triple driven multi-modal knowledge graph construction method and application in production line control with Gantt charts,” Journal of manufacturing systems, 80, pp. 224–242. Available at: https://doi.org/10.1016/j.jmsy.2025.03.002. (Accessed: 28 December 2025).

- Liu, M. (2013) “Program Evaluation and Review Technique (PERT) in Construction Risk Analysis,” Applied Mechanics and Materials, 357–360, pp. 2334–2337. Available at: https://doi.org/10.4028/www.scientific.net/AMM.357-360.2334. . (Accessed: 02 January 2026).

- Health and Safety Executive (HSE) (2024) Construction: Managing health and safety. Available at:
https://www.hse.gov.uk/construction/index.htm (Accessed: 05 January 2026).

- Gov.uk – Planning and building regulations (n.d.) Building Regulations Approval. Available at:
https://www.gov.uk/building-regulations-approval (Accessed: 9 January 2026).

- Taroun, A. (2014) ‘Towards a better modelling and assessment of construction risk: Insights from a literature review’, International Journal of Project Management, 32(1), pp. 101–115. Available at: Towards a better modelling and assessment of construction risk (Accessed: 12 January 2026.)

- Harvard Business Review (1963) The ABCs of the Critical Path Method. Available at: https://hbr.org/1963/09/the-abcs-of-the-critical-path-method (Accessed: 15 January 2026).

- Geraldi, J. and Lechler, T. (2012) ‘Gantt Charts Revisited: A Critical Analysis of Its Roots and Implications to the Management of Projects Today’, International Journal of Managing Projects in Business, 5(4), pp. 578–594. Available at: https://www.researchgate.net/publication/263571905_Gantt_charts_revisited_A_critical_analysis_of_its_roots_and_implications_to_the_management_of_projects_today (Accessed: 20 January 2026).

- British Standards Institution (BSI) (2020) BS EN ISO 9001: Quality Management Systems. Available at:
https://www.bsigroup.com/en-GB/iso-9001-quality-management/ (Accessed: 22 January 2026).

- Harris, R.B. and Ioannou, P.G. (1998) ‘Scheduling Projects with Repeating Activities’, Journal of Construction Engineering and Management, 124(4), pp. 269–278.

- Institute Project Management (2022) Work Breakdown Structure (WBS): A Comprehensive Guide. Available at: https://instituteprojectmanagement.com/blog/work-breakdown-structure/ (Accessed: 23 January 2026).

- Prakash, J.J. and Vidjeapriya, R. (2020) ‘Critical Path Method and Time-Cost Tradeoff Analysis – A Review’, International Journal of Engineering Research and Development, 16(7),pp.49–58.Availableat:https://www.ijerd.com/paper/vol16issue7/G16074958.pdf (Accessed: 26 January 2026).

- Jones, C. (2008) Moving from the WBS to a Critical Path Schedule, PMI Global Congress Proceedings. Available at: https://www.pmi.org/learning/library/moving-work-breakdown-structure-critical-path-6978 (Accessed: 27 January 2026).

# Appendices

# APPENDIX A:  ACTIVITY LIST (DURATION AND PREDECESSORS)

2.2 Activity sequencing and dependencies

| NO | ACTIVITY | DURATION (DAYS) | PREDECESSOR |
| --- | --- | --- | --- |
| A1 | Project kick-off and scope confirmation | 2 | _____ |
| A2 | Topographical survey | 3 | A1 |
| A3 | Ground investigation | 5 | A1 |
| A4 | Design coordination (architecture/structure) | 10 | A2, A3 |
| A5 | Planning approval allowance | 20 | A4 |
| A6 | Procurement & window/façade order | 11 | A4 |

2. SITE SETUP AND ENABLING WORKS

| NO | ACTIVITY | DURATION | PREDECESSOR |
| --- | --- | --- | --- |
| B1 | Mobilisation and temporary services | 3 | A5, A6 |
| B2 | Hoarding, Welfare and health & safety setup | 3 | B1 |
| B3 | Site clearance and setting out | 4 | B2 |

3. SUBSTRUCTURE

| NO | ACTIVITY | DURATION | PREDECESSOR |
| --- | --- | --- | --- |
| C1 | Excavation & temp dewatering | 10 | B3 |
| C2 | Foundation reinforcement and formwork | 6 | C1 |
| C3 | Foundation concrete pour/inspection | 3 | C2 |
| C4 | Foundation curing/early strength | 4 | C3 |
| C5 | Below-ground drainage | 5 | C1 |
| C6 | Backfill and compaction | 4 | C4, C5 |
| C7 | Ground floor slab pre/pour/cure | 9 | B3, C6 |

4. EXTERNAL ENVELOPE AND WEATHER-TIGHT

| NO | ACTIVITY | DURATION | PREDECESSOR |
| --- | --- | --- | --- |
| E1 | External walls/façade/cladding | 15 | D1 |
| E2 | Windows and external doors installation | 8 | E1, A6 |
| E3 | Roof waterproofing | 5 | D4 |
| E4 | Seal penetrations and make weather tight | 3 | E2, E3 |

5. MECHANICAL, ELECTRICAL AND PLUMBING AND INTERNAL WORKS

| NO | ACTIVITY | DURATION | PREDECESSOR |
| --- | --- | --- | --- |
| F1 | Mechanical, electrical, plumbing, fire | 10 | E4 |
| G1 | Internal partition framing | 10 | F1 |
| G2 | Drylining/plasterboard installation | 10 | G1 |
| G3 | Plastering/finishing coats | 8 | G2 |
| G4 | Floor screed / levelling | 6 | G3 |

6. SECOND FIX, FINISHES AND CLOSEOUT

| NO | ACTIVITY | DURATION | PREDECESSOR |
| --- | --- | --- | --- |
| H1 | MEP second fix | 8 | G4 |
| H2 | Joinery (doors/ironmongery) | 6 | G3 |
| H3 | Painting and decorating | 10 | G3 |
| H4 | Flooring finishes | 8 | G4, H3 |
| H5 | Kitchen installation | 6 | H4 |
| H6 | Bathroom sanitary installation | 6 | H1, H4 |
| I1 | Testing and Commissioning | 6 | H1, H2, H3 |
| I2 | Final cleaning | 2 | H2, H4, H5, H6 |
| I3 | Snagging and defects | 6 | I1, I2 |
| I4 | Final inspection (building control) | 3 | I3 |
| I5 | Handover (key, certificates) | 0 | I4 |

# APPENDICES B

Early start = maximum EF of all Predecessors

Early finish = ES + duration            backward pass = LS - Duration

A1= 2 days                                       LF (late start) = minimum Ls of all successors &

IF Activity more than one = the smallest successor Ls

ES= 0              EF= 0 + 2 = 2

(A2= A1 so, ES = EF(A1) =2)

EF= 2+3=5

(A3=A1   ES=2     EF= 2+5=7)

For Backword

LF=minimum LS of successor activities

LS= LF- duration

For I5

LF=201    LS=201-0 = 201

For H4 = H5, H6

LF= min (LS, H5) (LS H6)    LS= LF- Duration

| NO | DURATION | PREDECESSOR | ES | EF | LS | LF | FLOAT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A1 | 2 | --- | 0 | 2 | 0 | 2 | 0 |
| A2 | 3 | A1 | 2 | 5 | 4 | 7 | 2 |
| A3 | 5 | A1 | 2 | 7 | 2 | 7 | 0 |
| A4 | 10 | A2, A3 | 7 | 17 | 7 | 17 | 0 |
| A5 | 20 | A4 | 17 | 37 | 17 | 37 | 0 |
| A6 | 11 | A4 | 17 | 28 | 26 | 37 | 9 |
| B1 | 3 | A5, A6 | 37 | 40 | 37 | 40 | 0 |
| B2 | 3 | B1 | 40 | 43 | 40 | 43 | 0 |
| B3 | 4 | B2 | 43 | 47 | 43 | 47 | 0 |
| C1 | 10 | B3 | 47 | 57 | 47 | 57 | 0 |
| C2 | 10 | C1 | 57 | 63 | 57 | 63 | 0 |
| C5 | 5 | C1 | 57 | 62 | 65 | 70 | 8 |
| C3 | 3 | C2 | 63 | 66 | 63 | 66 | 0 |
| C4 | 4 | C3 | 66 | 70 | 66 | 70 | 0 |
| C6 | 4 | C4, C5 | 70 | 74 | 70 | 74 | 0 |
| C7 | 9 | B3, C6 | 74 | 83 | 74 | 83 | 0 |
| D1 | 16 | C7 | 83 | 99 | 83 | 99 | 0 |
| D2 | 16 | D1 | 99 | 115 | 99 | 115 | 0 |
| D3 | 5 | D1 | 99 | 104 | 196 | 201 | 97 |
| E1 | 15 | D1 | 99 | 114 | 102 | 117 | 3 |
| D4 | 5 | D2 | 115 | 120 | 115 | 120 | 0 |
| E2 | 8 | E1, A6 | 114 | 122 | 117 | 125 | 3 |
| E3 | 5 | D4 | 120 | 125 | 120 | 125 | 0 |
| E4 | 3 | E2, E3 | 125 | 128 | 125 | 128 | 0 |
| F1 | 10 | E4 | 128 | 138 | 128 | 138 | 0 |
| G1 | 10 | F1 | 138 | 148 | 138 | 148 | 0 |
| G2 | 10 | G1 | 148 | 158 | 148 | 158 | 0 |
| G3 | 8 | G2 | 158 | 166 | 158 | 166 | 0 |
| G4 | 6 | G3 | 166 | 172 | 170 | 176 | 4 |
| H2 | 6 | G3 | 166 | 172 | 180 | 186 | 14 |
| H3 | 10 | G3 | 166 | 176 | 166 | 176 | 0 |
| H1 | 8 | G4 | 172 | 180 | 176 | 184 | 4 |
| H4 | 8 | G4, H3 | 176 | 184 | 176 | 184 | 0 |
| I1 | 6 | H1,2, 3 | 180 | 186 | 186 | 192 | 6 |
| H5 | 6 | H4 | 184 | 190 | 184 | 190 | 0 |
| H6 | 6 | H1,4 | 184 | 190 | 184 | 190 | 0 |
| I2 | 2 | H2, 4, 5 | 190 | 192 | 190 | 192 | 0 |
| I3 | 6 | I1, 2 | 192 | 198 | 192 | 198 | 0 |
| I4 | 3 | I3 | 198 | 201 | 198 | 201 | 0 |
| I5 | 0 | I4 | 201 | 201 | 201 | 201 | 0 |

# APPENDICES C:  COST SLOPE CALCULATION

To Determine the most cost-effective activities to crash, the cost slope is calculated for activity

cost slope =crash cost- normal costnortmal duration-crash duration

- Excavation

Normal Duration = 6 days    Crash Duration = 5 days    Normal Cost= 45,000   Crash cost=50,000

cost slope=50,000-45,0006-5

=5,000 £

- Foundation reinforcement & formwork

Normal Duration = 6 days    Crash Duration = 5 days    Normal Cost= 60,000   Crash cost=68,000

cost slope=68,000-60,0006-5

=8,000 £

| ACTIVITY | DAYS | ADDITIONAL COST £ | COST SLOPE £/DAY |
| --- | --- | --- | --- |
| Excavation | 1 | 5,000 | 5,000 |
| Foundation reinforcement & formwork | 1 | 8,000 | 8,000 |
| Drylining & plasterboard | 1 | 10,000 | 10,000 |
| Painting & decorating | 1 | 10,000 | 10,000 |
| Testing & commissioning | 1 | 10,000 | 10,000 |
| Window & external doors | 1 | 15,000 | 15,000 |
| Structure frame | 1 | 15,000 | 15,000 |