## DataCopy
Task Name | Start Date | End Date | Duration
Research presentation techniques | 2020-10-10 | 2020-10-17 | 1900-01-07
Analyse own weaknesses | 2020-10-17 | 2020-10-20 | 4
Write text for section 1 | 2020-10-20 | 2020-10-25 | 6
Perform additional self evaluation | 2020-10-25 | 2020-10-27 | 3
Compare contrast | 2020-10-27 | 2020-10-31 | 5
Write up section 2 | 2020-11-01 | 2020-11-09 | 9
Create 4 goals with SMART aims & objectives | 2020-11-09 | 2020-11-10 | 2
Create Gantt charts | 2020-11-10 | 2020-11-15 | 6
Format section 3 | 2020-11-18 | 2020-11-25 | 8
Research and set up google calendar | 2020-11-25 | 2020-11-27 | 3
Research and set up google keep | 2020-11-25 | 2020-11-27 | 3
Finish populating e-portfolio | 2020-11-27 | 2020-12-01 | 5
Write up section 3 | 2020-12-01 | 2020-12-09 | 9
Plan your steps productivity,organisation & reduce stress | 2020-12-09 | 2020-12-15 | 7
Pull screen grabs | 2020-12-15 | 2020-12-17 | 3
Write up section 4 | 2020-12-17 | 2020-12-24 | 8
Formulas:
Duration = DATEDIF([Start Date],[End Date],"D")+1

## Data
Task Name | Start Date | End Date | Duration |  | Income | Weekly avrage income | Outgoing | Weekly Avrage Outgoing | Avrage left over each week
Research presentation techniques | 2020-10-10 | 2020-10-17 | 8 |  | Affiliate marketing | 150 | Rent | 125
Analyse own weaknesses | 2020-10-17 | 2020-10-20 | 4 |  | Trading | 100 | Phone | 15
Write text for section 1 | 2020-10-20 | 2020-10-25 | 6 |  | Paid Work | 250 | Internet | 15
Perform additional self evaluation | 2020-10-25 | 2020-10-27 | 3 |  | Freelancing online | 75 | Food | 50
Compare contrast | 2020-10-27 | 2020-10-31 | 5 |  | Dropshipping | 450 | Other Expence | 300
Write up section 2 | 2020-11-01 | 2020-11-09 | 9 | Totals |  | 1025 |  | 505 | 520
Create 4 goals with SMART aims & objectives | 2020-11-09 | 2020-11-10 | 2
Create Gantt charts | 2020-11-10 | 2020-11-15 | 6
Format section 3 | 2020-11-18 | 2020-11-25 | 8
Research and set up google calendar | 2020-11-25 | 2020-11-27 | 3
Research and set up google keep | 2020-11-25 | 2020-11-27 | 3
Finish populating e-portfolio | 2020-11-27 | 2020-12-01 | 5 | Total income | 1025
Write up section 3 | 2020-12-01 | 2020-12-09 | 9 | Total Outgoing | 505
Plan your step you take or intend totake to enhance your productivity, improve your organisation and/or reduce stress levels. | 2020-12-09 | 2020-12-15 | 7 | Total Left After Outgoing | 520
Pull screen grabs/pictures showing e.g. your electronic calendar/diary, your organised e-portfolio directory structure etc. | 2020-12-15 | 2020-12-17 | 3
Write up section 4 | 2020-12-17 | 2020-12-24 | 8
Formulas:
Duration = DATEDIF([Start Date],[End Date],"D")+1

## Gannt Bar Pie
Spendings charts and Gannt for activity schedueling Iskander Abd-Al-Kerim 0250002