Author

SHAMIM 2118790

Mental Health in the Workplace CONFERENCE A Feasibility Study
for an International Meeting

Module: International Meetings Management (BMIH6007)

AI Acknowledgment:

I acknowledge the use of CHATGPT, Quill Bot and Grammarly to check my work below for grammatical mistakes and simplify the text.  I also used AI to find and research on mental health in workplace. I confirm that I have not presented any AI generated text as my own work. I confirm I have copies of my drafts, notes, and other resources I used before, and after the use of AI tools which I may be asked to provide in evidence.

1. INTRODUCTION

The Mental Health in the Workplace Conference is designed to address the growing need for corporate well-being initiatives, aiming to provide HR professionals, business leaders, and mental health advocates with the tools and strategies to foster a healthier workplace. According to the Mental Health Foundation (2023), poor mental health costs UK businesses an estimated £45 billion annually. The event aligns with global discussions on employee well-being, recognising the impact of mental health on productivity, staff retention, and overall corporate performance. The conference follows key event management principles, incorporating the Event Cycle transfer and workplace impact.

As mental health in professional settings gains recognition, organisations are under increasing pressure to implement sustainable well-being policies (CIPD, 2024). Research suggests that companies with strong mental health support structures experience increased employee engagement and reduced absenteeism (Deloitte, 2023). However, barriers such as stigma, lack of organisational commitment, and resource constraints continue to hinder progress (McKinsey & Company, 2024). This conference aims to bridge that gap by providing evidence-based solutions, case studies, and networking opportunities for attendees.

The event will be held at the Scottish Event Campus (SEC) in Glasgow, a venue chosen for its hybrid event capabilities, accessibility, and alignment with sustainable event practices (VisitScotland, 2023). The conference itinerary includes keynote speeches, interactive workshops, networking sessions, and expert panels, offering a well-rounded experience for participants.

This report provides a structured approach to planning and delivering the conference, covering key aspects such as event concept, marketing strategies, financial planning, industry trends, and cultural considerations. The event’s success will be evaluated using feedback mechanisms, engagement metrics, and financial performance indicators.

2. THE EVENT CYCLE

Bowdin et al. (2011) describe event planning as a continuous process where phases like pre-event strategy, execution, and post-event evaluation determine success. It ensures that all key stages are properly managed to create a successful and impactful experience. A structured event cycle ensures that all key stages of planning, delivery, and evaluation are executed efficiently (Bladen et al., 2012).

The model consists of three main phases:

- Planning Phase

This is the most critical stage, as it lays the foundation for the event. Key activities include:

- Defining the event’s objectives: The goal of the Mental Health in the Workplace Conference is to provide practical strategies for improving employee well-being.

- Venue selection: The Scottish Event Campus (SEC) in Glasgow was chosen for its accessibility and hybrid event facilities (VisitScotland, 2023).

- Budgeting and sponsorship: Funding is secured through ticket sales, sponsorships, and exhibitor fees (Drucker, 1954).

- Marketing and audience engagement: social media, email campaigns, and partnerships will be used to attract attendees (Eventbrite, 2023).

- Risk assessment and logistics: Health and safety measures will be put in place to comply with UK regulations (HSE, 2024).

- Delivery Phase

This phase focuses on the actual execution of the event. Key elements include:

- Managing guest experience: Attendees will be welcomed and guided through registration, sessions, and networking opportunities.

- Speaker and session coordination: Experts in workplace mental health will deliver keynote speeches and lead workshops.

- Technology support: Hybrid participation will be enabled through live streaming and interactive online sessions

- Catering and accessibility: Food options will be available, and accessibility features such as sign language interpreters will be provided.

- Evaluation Phase

Once the event is completed, it is important to measure its success. Kirkpatrick (1994) outlines a four-level framework to assess training effectiveness, which will be adapted to measure attendee engagement, knowledge retention, and the event’s long-term impact.

- Attendee satisfaction: Surveys will be conducted to gather feedback.

- Knowledge gained: Tests and assessments will check whether attendees learned valuable strategies.

- Workplace impact: Companies will be followed up to see if they have applied new mental health initiatives.

- Financial review: Income and expenses will be analysed to assess profitability.

By following the Event Cycle Model, the conference will be well-organised, engaging, and valuable to attendees.

3. EVENT CONCEPT & ITINERARY

The Mental Health in the Workplace Conference is designed to provide practical solutions for improving employee well-being. The event will bring together HR professionals, business leaders, and mental health advocates to discuss strategies for creating healthier work environments. The conference follows the Experience Economy Model (Pine & Gilmore, 1999), which emphasises creating meaningful and interactive experiences rather than just delivering information.

A. Event Concept

The conference will focus on three key areas:

- Education: Experts will share insights on mental health policies and best practices.

- Engagement: Attendees will participate in interactive workshops and discussions.

- Networking: Business professionals will have the opportunity to connect and collaborate.

A hybrid format will be used, allowing both in-person and online participation (Skift Meetings, 2024). This ensures accessibility for attendees from different locations.

B. Event Objectives

Doran (1981) introduced the SMART model, emphasizing goal-setting principles that enhance the accuracy and achievability of event objectives below:

- Specific: Provide three actionable strategies for improving mental health at work.

- Measurable: Ensure at least 80% of attendees engage in workshops.

- Achievable: Structure sessions with expert speakers and real-world case studies.

- Relevant: Address the growing need for workplace well-being initiatives.

- Time-bound: Conduct all activities within a single-day conference.

C. Event Itinerary

A well-structured schedule is essential for keeping attendees engaged.

| Time | Activity | Details |
| --- | --- | --- |
| 09:00 AM | Registration & Networking | Attendees’ check-in and receive event materials. |
| 10:00 AM | Opening Keynote | Expert talk on the importance of mental health in the workplace. |
| 11:00 AM | Panel Discussion | Industry professionals discuss effective well-being policies. |
| 12:00 PM | Coffee Break | Refreshments and informal networking. |
| 12:30 PM | Interactive Workshop | Attendees participate in case studies and group activities. |
| 01:30 PM | Lunch Break | Healthy catering options provided. |
| 02:30 PM | Fireside Chat | Q&A with leaders who have successfully implemented mental health initiatives. |
| 03:30 PM | Mindfulness Session | Guided meditation and relaxation techniques. |
| 04:00 PM | Closing Keynote | Future trends in workplace mental health. |
| 05:00 PM | Networking Reception | Final networking opportunity before event concludes. |

By structuring the event in this way, attendees will benefit from a mix of learning, discussion, and practical application.

4. AIMS & SMART OBJECTIVES

The Mental Health in the Workplace Conference aims to help businesses create a supportive and inclusive work environment where employees feel mentally and emotionally well. The event provides practical solutions, expert insights, and networking opportunities to promote corporate well-being strategies.

To ensure the event is well-structured and its success can be measured, the SMART Goal Framework (Doran, 1981) is used to set clear and achievable objectives.

- Event Aim

To equip HR professionals, business leaders, and mental health advocates with knowledge and tools to improve workplace mental health, leading to better employee well-being, productivity, and job satisfaction.

- SMART Objectives

- Specific: Provide attendees with three key mental health strategies that can be applied in their organisations.

- Measurable: Ensure at least 80% of attendees participate in interactive sessions and panel discussions.

- Achievable: Feature expert-led workshops and real-world case studies to give practical solutions.

- Relevant: Address current workplace mental health challenges and industry needs (CIPD, 2023).

- Time-bound: Deliver all content and engagement activities within a one-day conference.

- Key Outcomes

By the end of the conference, attendees will:

- Gain practical knowledge on how to implement workplace well-being programs.

- Learn from case studies about companies that have successfully improved mental health policies.

- Network with industry experts and HR professionals leading mental health initiatives.

- Understand how to create effective policies that support a healthy work culture.

- Access post-event resources to continue their learning and implementation journey.

Using the SMART framework, the event ensures measurable success and long-term impact on workplace mental health.

5. MARKETING STRATEGIES & PROMOTION

A strong marketing strategy is essential to attract attendees, sponsors, and industry partners to the Mental Health in the Workplace Conference. The 7Ps Marketing Framework (Kotler, 2016) is used to guide the event’s promotional efforts.

- Target Audience

The marketing strategy is designed to engage key stakeholders who have a role in workplace mental health:

- HR professionals: Responsible for employee well-being policies.

- Business leaders & executives: Interested in improving company culture and productivity.

- Corporate wellness advocates: Promoting mental health programs within organisations.

- Researchers & academics: Studying trends in workplace mental health.

- Marketing Channels

To maximise outreach and engagement, the event will be promoted through multiple channels:

- Social Media Marketing

- LinkedIn: Posts and discussions targeting HR professionals.

- Twitter/Event hashtag for real-time engagement.

- Facebook & Instagram: Sponsored ads and behind-the-scenes content.

- YouTube & TikTok: Short video clips featuring keynote speakers and testimonials (Eventbrite, 2023).

- Email Campaigns & Newsletters

- Personalised invitations to corporate leaders and wellness professionals.

- Weekly newsletters with speaker announcements and exclusive content.

- Event Website & Registration Platform

- A dedicated website will provide details on the agenda, speakers, venue, and ticketing options.

- Online registration for both in-person and virtual attendees.

- Corporate & Industry Partnerships

- Collaboration with CIPD, Deloitte, and MHFA England to increase credibility and sponsorships.

- Featured content on HR industry blogs and business news websites.

- Influencer & Thought Leadership Marketing

- Engaging HR and mental health experts to promote the event.

- Guest blogs, interviews, and video testimonials.

- Press & Media Coverage

- Press releases to major HR and business publications such as Forbes and McKinsey Reports (Forbes, 2024).

- Industry news coverage to attract corporate sponsorships.

- Ticket Pricing Strategy

To ensure accessibility while generating revenue, a tiered pricing model is used:

| Ticket Type | Price (£) | Inclusions |
| --- | --- | --- |
| Early Bird Ticket | 150 | Full access, networking, digital resources |
| Standard Ticket | 200 | Full access + bonus workshop |
| VIP Ticket | 350 | Priority seating, exclusive Q&A with speakers |
| Virtual Ticket | 100 | Live-stream access + recordings |

A strong early bird pricing strategy encourages early registrations and helps with budgeting.

- Sponsorship & Revenue Opportunities

Sponsorship packages allow companies to gain visibility while funding key aspects of the event.

| Sponsorship Tier | Cost (£) | Benefits |
| --- | --- | --- |
| Gold Sponsor | 20,000 | Logo on materials, keynote slot, exhibition space |
| Silver Sponsor | 10,000 | Logo on website, panel mention, networking access |
| Bronze Sponsor | 5,000 | Social media recognition, free event passes |

The marketing strategy ensures that the event attracts the right audience, secures sponsors, and maximises attendance.

6. EVENT MANAGEMENT CONSIDERATIONS

Successful event planning requires a feasibility assessment, ensuring that logistical and financial constraints are managed effectively (O’Toole, 2011). Managing an event effectively requires careful planning and coordination to ensure a smooth and engaging experience for attendees. The EMBOK Model (Silvers, 2008) is used to guide the management of the Mental Health in the Workplace Conference, covering administration, operations, risk management, and logistics.

A. Venue Selection & Logistics

The Scottish Event Campus (SEC) in Glasgow was selected due to its dedicated hybrid conferencing facilities, allowing seamless interaction between virtual and in-person attendees. Additionally, its corporate-friendly infrastructure, including executive boardrooms and networking lounges, makes it an ideal location for HR professionals and business leaders to discuss workplace well-being. SEC’s sustainability initiatives, such as energy-efficient spaces and waste reduction programs, also align with the conference’s commitment to ethical business practices (VisitScotland, 2023). Key venue considerations include:

- Capacity: SEC provides ample space for keynotes, workshops, and networking sessions.

- Technology: Equipped with live-streaming and digital engagement tools for hybrid attendees (Skift Meetings, 2024).

- Sustainability: The venue supports eco-friendly event planning, reducing environmental impact.

B. Scheduling & Time Management

To prevent delays and ensure efficiency, the event follows a structured timeline:

- Clear session timings to keep the conference organised.

- Time buffers between sessions for networking and movement.

- Digital time-tracking tools to send alerts for upcoming sessions.

C. Stakeholder Coordination

The success of the event relies on the collaboration of various stakeholders, including:

- Speakers & Panellists: Experts in mental health and corporate well-being.

- Sponsors & Partners: Companies supporting mental health initiatives.

- Attendees: Business leaders, HR professionals, and wellness advocates.

- Suppliers: Catering, security, and tech support teams.

Regular meetings and communication plans will ensure all stakeholders are aligned on event goals.

D. Technology & Hybrid Event Setup

A hybrid format is implemented to increase accessibility and engagement:

- Live streaming for remote attendees.

- AI-powered event app for schedules, networking, and Q&A.

- Digital ticketing and registration for a paperless experience.

Using technology ensures a seamless experience for both in-person and virtual participants.

E. Risk & Crisis Management

A well-defined risk management plan ensures the event runs smoothly. Strategies include:

- Health & Safety Compliance: Trained staff and emergency response measures (HSE, 2024).

- Cybersecurity: Secure platforms to protect attendee data (UK Government, 2024).

- Backup Plans: Alternative speakers and venue options in case of disruptions.

By applying strong management principles, the event will be well-organised, engaging, and efficient.

F. Sustainable & Inclusive Event Planning

- Environmental Responsibility

- Paperless registration and digital materials to reduce waste.

- Sustainable catering options, promoting mental and physical well-being.

- Eco-friendly transport options for attendees.

7. BUDGET & FINANCIAL STRATEGY

A strong financial plan ensures that the Mental Health in the Workplace Conference remains financially viable while offering value to attendees and sponsors. The Break-Even Analysis (Drucker, 1954) helps determine whether revenue will cover costs and ensure long-term sustainability.

A. Estimated Budget Breakdown

The event’s budget is structured to cover all necessary expenses while maintaining financial efficiency.

| Expense Category | Estimated Cost (£) |
| --- | --- |
| Venue Hire (SEC, Glasgow) | 55,000 |
| Speaker Fees & Travel | 22,500 |
| Catering & Hospitality | 18,000 |
| Marketing & Promotion | 12,500 |
| Event Technology (Live Streaming, App, IT Support) | 10,000 |
| Staffing & Logistics | 6,500 |
| Security & Insurance | 8,000 |
| Miscellaneous Expenses | 7,500 |
| Total Estimated Cost | 140,000 |

A 10% contingency fund is allocated to cover any unexpected expenses.

B. Revenue Streams

Multiple revenue sources are used to cover costs and generate profit.

| Revenue Source | Estimated Income (£) |
| --- | --- |
| Ticket Sales (500 attendees at avg. £240 per ticket) | 120,000 |
| Corporate Sponsorships | 40,000 |
| Exhibitor Fees (11 companies at £2,000 each) | 22,000 |
| Workshop & Certification Fees | 12,500 |
| Total Estimated Revenue | 194,000 |

Revenue is projected to exceed expenses, ensuring the event is financially successful.

C. Ticket Pricing Strategy

A tiered ticket model ensures affordability while maintaining revenue targets.

| Ticket Type | Price (£) | Inclusions |
| --- | --- | --- |
| Early Bird Ticket | 175 | Full access, networking, digital resources |
| Standard Ticket | 225 | Full access + bonus workshop |
| VIP Ticket | 400 | Priority seating, exclusive Q&A with speakers |
| Virtual Ticket | 125 | Live-stream access + recordings |

An early bird pricing model encourages early sign-ups, improving cash flow before the event.

D. Sponsorship & Partnership Strategy

Sponsorships help offset costs while providing companies with branding opportunities.

| Sponsorship Tier | Cost (£) | Benefits |
| --- | --- | --- |
| Platinum Sponsor | 25,000 | Logo on all event materials, keynote speaker slot, VIP access |
| Gold Sponsor | 15,000 | Panel discussion feature, logo placement, marketing mention |
| Silver Sponsor | 7,500 | Social media promotion, networking sponsorship |
| Exhibitor Package | 3,000 | Booth space at SEC, company feature in event app |

Corporate sponsorships from HR-focused organisations will enhance financial security (Deloitte, 2023).

E. Financial Risk Management

To minimise financial risks, the following strategies will be applied:

- Break-even analysis to ensure revenue covers operational costs.

- Cost control measures such as negotiated speaker fees and digital marketing over print media.

- Flexible sponsorship options to attract corporate backing.

This financial plan ensures long-term event sustainability and profitability.

8. INDUSTRY TRENDS & CHALLENGES

The Mental Health in the Workplace Conference aligns with current trends in corporate well-being, technology, and sustainability. However, challenges such as financial uncertainty and engagement issues must be addressed. Recent UK Government initiatives have emphasised the importance of workplace mental health programs in promoting employee well-being (GOV.UK, 2023).

A PESTLE Analysis (Kotler, 2016) helps evaluate external factors affecting the event.

A. Emerging Trends in Workplace Mental Health

Increased Corporate Investment in Employee Well-Being

- Many companies are prioritising mental health due to its impact on productivity and staff retention (CIPD, 2023).

- Businesses that invest in well-being programs experience higher employee engagement and lower turnover (Deloitte, 2023).

Growth of Hybrid & Digital Events

- Virtual participation is becoming standard, allowing global access to events.

- AI-driven engagement tools enhance interactivity for both in-person and remote attendees.

Personalised Event Experiences

- Attendees expect tailored sessions, networking opportunities, and personalised content.

- AI-powered apps and event platforms help create a customised attendee journey (Eventbrite, 2023).

Sustainable Event Planning

- More businesses prefer eco-friendly events, reducing waste through paperless registration, digital resources, and sustainable catering (VisitScotland, 2023).

B. Key Challenges in the Events Industry

Despite growth opportunities, several challenges impact the success of corporate events.

Financial Constraints

- Rising event costs (venue, speaker fees) require careful budgeting (Drucker, 1954).

- Economic uncertainty may limit ticket sales and sponsorship funding (Forbes, 2024).

Digital Fatigue & Low Engagement

- Virtual attendees may struggle to stay engaged due to “Zoom fatigue.”

- The event will incorporate interactive Q&A sessions, gamification, and networking features to maintain interest.

Accessibility & Inclusivity Issues

- Mental health discussions vary across cultures, requiring sensitivity to different workplace norms.

- The conference will provide multilingual support and sign language interpreters (UK Government, 2024).

Cybersecurity & Data Privacy Risks

- Virtual events pose risks related to data security and GDPR compliance (HSE, 2024).

- Secure registration systems and encrypted communication channels will be used.

By addressing these trends and challenges, the event will remain relevant, accessible, and impactful for businesses.

9. SITUATIONAL & CULTURAL CONSIDERATIONS

The Mental Health in the Workplace Conference must consider situational and cultural factors to ensure it is inclusive, accessible, and well-received by attendees from diverse backgrounds. Employers must ensure that workplace mental health policies align with anti-discrimination laws under the Equality Act 2010 (Equality and Human Rights Commission, 2021). A diverse and inclusive workplace fosters better employee engagement and well-being (Achievers, 2023). A SWOT Analysis (Gürel & Tat, 2017) and PESTLE Analysis (Kotler, 2016) help evaluate these factors.

A. SWOT Analysis of Event Planning & Location

| Factor | Analysis |
| --- | --- |
| Strengths | High demand for workplace mental health solutions; strong industry partnerships; SEC Glasgow’s reputation as a premier event venue (VisitScotland, 2023). |
| Weaknesses | Mental health stigma in some industries may limit open discussions. |
| Opportunities | Growth in hybrid events enables global participation and accessibility (Skift Meetings, 2024). |
| Threats | Economic challenges may impact attendance and sponsorships (Forbes, 2024). |

By leveraging its strengths and opportunities, the event will remain impactful while addressing potential challenges.

B. PESTLE Analysis of External Influences

| Factor | Impact on the Event |
| --- | --- |
| Political | Government initiatives supporting mental health in workplaces influence corporate strategies (UK Government, 2024). |
| Economic | Budget constraints may limit ticket sales, requiring competitive pricing and sponsorship strategies (Drucker, 1954). |
| Social | Mental health awareness is rising, but cultural differences impact how businesses address well-being (CIPD, 2023). |
| Technological | AI-driven event apps improve engagement and networking opportunities (Eventbrite, 2023). |
| Legal | GDPR compliance ensures secure handling of attendee data (HSE, 2024). |
| Environmental | Sustainable event practices, such as paperless registration and eco-friendly catering, enhance event reputation (VisitScotland, 2023). |

C. Cultural Sensitivity & Global Accessibility

To accommodate attendees from different cultures and industries, the following measures will be implemented:

Multilingual Support

- Live translations for keynote sessions.

- Event materials available in multiple languages.

Cultural Awareness in Mental Health Discussions

- Recognising differences in mental health perceptions across industries and regions.

- Tailoring discussions to be inclusive and respectful.

Ensuring Inclusivity & Accessibility

- Sign language interpreters for key sessions.

- Quiet zones for attendees needing breaks.

- Hybrid access for those unable to attend in person.

By focusing on cultural inclusivity and accessibility, the event ensures a diverse and welcoming experience for all attendees.

10. POST-EVENT EVALUATION

Evaluating the success of the Mental Health in the Workplace Conference is essential to measure its impact and identify areas for improvement. The Kirkpatrick Model (Kirkpatrick, 1994) is used to assess the event on four levels:

- Reaction: Attendee feedback on the event experience.

- Learning: Measuring the knowledge gained by participants.

- Behaviour: Evaluating how attendees apply insights in their workplaces.

- Results: Assessing the long-term impact on workplace mental health initiatives.

A. Methods of Evaluation

Attendee Surveys & Feedback Forms

- Post-event surveys will measure satisfaction levels, content relevance, and speaker effectiveness.

- Live polling during sessions will gather real-time feedback.

Engagement & Participation Metrics

- Website analytics will track session attendance, app engagement, and networking activity.

- Social media performance (event hashtags, shares, and interactions) will be monitored (Eventbrite, 2023).

Financial Performance & ROI Analysis

- Break-even analysis will compare revenue from ticket sales, sponsorships, and exhibitor fees against total costs (Drucker, 1954).

- Sponsor & exhibitor feedback will measure partnership satisfaction.

Post-Event Media & Content Distribution

- Event highlights will be shared via social media, press releases, and corporate blogs (Forbes, 2024).

- Video recordings and key takeaways will be provided to attendees.

B. Continuous Improvement Strategy

- Refining future event themes based on attendee demand.

- Enhancing logistics & hybrid accessibility for a better user experience.

- Strengthening sponsorships by showcasing event impact.

By implementing a data-driven evaluation process, the event will ensure continuous growth and long-term impact.

11. CONCLUSION:

The Mental Health in the Workplace Conference is designed to provide businesses with practical strategies, expert insights, and actionable solutions for improving workplace mental health. By integrating structured event management models, such as the Event Cycle Model (Bowdin et al., 2011) and the EMBOK Model (Silvers, 2008), the event ensures a well-planned, engaging, and impactful experience.

The report has outlined key aspects of the event, including:

- A clear event concept that aligns with corporate mental health needs.

- Structured marketing and sponsorship strategies to maximise outreach and financial sustainability.

- Event logistics and risk management measures for smooth execution.

- A comprehensive budget and financial strategy to ensure long-term viability.

- Industry trends and cultural considerations that shape the event’s impact.

- Post-event evaluation methods to measure effectiveness and guide future improvements.

As mental health awareness continues to grow, companies must take proactive steps to support employee well-being. This conference provides an opportunity for business leaders, HR professionals, and industry experts to come together, share knowledge, and implement meaningful workplace changes. By combining expert-led discussions, interactive workshops, and networking opportunities, the event will create a lasting impact on corporate mental health initiatives.

12. REFERENCES

Achievers (2023) ‘Benefits and Challenges of Diversity & Inclusion in the Workplace’. Available at: https://www.achievers.com/blog/diversity-and-inclusion/

Bladen, C., Kennell, J., Abson, E., & Wilde, N. (2012) Events Management: An Introduction. Routledge. Available at: https://www.taylorfrancis.com/books/mono/10.4324/9781003102878/events-management-charles-bladen-nick-wilde-james-kennell-emma-abson

Bowdin, G., Allen, J., O’Toole, W., Harris, R., & McDonnell, I. (2011). Events Management. Oxford: Elsevier. Available at: https://www.taylorfrancis.com/books/mono/10.4324/9780080964317/events-management-johnny-allen-ian-mcdonnell-rob-harris-glenn-bowdin-william-toole

CIPD (2023) ‘Workplace Well-being: Policy and Strategy’. Available at: https://www.cipd.org/uk/knowledge/reports/health-well-being-work/

Deloitte (2023) ‘Mental Health and Well-being in the Workplace’. Available at: https://www2.deloitte.com/content/dam/Deloitte/global/Documents/Life-Sciences-Health-Care/gx-mental-health-2022-report-noexp.pdf

Doran, G. T. (1981) ‘There’s a S.M.A.R.T. Way to Write Management’s Goals and Objectives.’ Management Review, 70(11), pp. 35-36. Available at: https://community.mis.temple.edu/mis0855002fall2015/files/2015/10/S.M.A.R.T-Way-Management-Review.pdf

Drucker, P. (1954) The Practice of Management. New York: Harper & Brothers. Available at: https://www.scirp.org/reference/referencespapers?referenceid=1197362

Equality and Human Rights Commission (2021) The Equality Act 2010: Key Provisions. Available at: https://www.equalityhumanrights.com/equality/equality-act-2010

Eventbrite (2023) The Future of Business Events: Trends and Insights. Available at: https://www.eventbrite.com/blog/press/newsroom/eventbrite-trends-report-2023-predictions/

Forbes (2024) The Future of Business Events & Corporate Well-Being. Available at: https://www.forbes.com/sites/rhettpower/2024/12/29/transforming-work-culture-through-employee-wellness/

Glasgow Chamber of Commerce (2023) ‘Why Glasgow is a top business destination’. Available at: https://www.glasgowchamberofcommerce.com

GOV.UK (2023) ‘Workplace Mental Health Initiatives’. Available at: https://www.gov.uk

Gürel, E., & Tat, M. (2017) ‘SWOT Analysis: A Theoretical Review.’ Journal of International Social Research, 10(51), pp. 994-1006. Available at: https://www.scirp.org/reference/referencespapers?referenceid=3040380

HSE (2024) Health and Safety Guidelines for UK Events. Available at: https://www.hse.gov.uk/event-safety/

Kirkpatrick, D. (1994) Evaluating Training Programs: The Four Levels. Berrett-Koehler Publishers. Available at : https://www.researchgate.net/publication/257496612_Evaluating_Training_Programs_The_Four_Levels_Donald_L_Kirkpatrick_Berrett-Koehler_Publishers_San_Francisco_CA_1996_229_pp

Kotler, P., Keller, K.L., Brady, M., Goodman, M., & Hansen, T. (2008). Marketing Management. Harlow: Pearson Education.

McKinsey & Company (2024) The State of Workplace Well-being: Strategies for Corporate Mental Health Support. Available at: https://www.mckinsey.com/featured-insights/well-being-in-the-workplace

Mental Health Foundation (2023) ‘Mental health at work: statistics. Available at: https://www.mentalhealth.org.uk/explore-mental-health/statistics/mental-health-work-statistics

MHFA England (2023) ‘Ten workplace mental health statistics for 2023’. Available at: https://mhfaengland.org/mhfa-centre/blog/ten-workplace-mental-health-statistics-for-2023/

O’Toole, W. (2011). Events Feasibility and Development. Routledge. Available at: https://www.routledge.com/Events-Feasibility-and-Development-From-Strategy-to-Operations/OToole/p/book/9781032000879?srsltid=AfmBOooOIdIo2VglkGKNKfaeoOqjibz1UL9_PyO82_z-zVe_nEQykpib

Pine, B. & Gilmore, J. (1999) The Experience Economy: Work is Theatre & Every Business a Stage. Harvard Business Review Press.

SEC (2023) ‘Why Choose SEC for Events?’. Available at: https://www.sec.co.uk

Silvers, J.R. (2008). EMBOK Model for Event Management. Routledge. Available at: https://www.embok.org/juliasilvers/embok.html

UK Government (2024) Mental Health and Well-being at Work: Policy & Compliance Guide. Available at: https://www.gov.uk/government/publications/mental-health-and-work

VisitScotland (2023) ‘Business Tourism & Economic Impact’. Available at: https://www.visitscotland.org/research-insights/about-our-industry/tourism-employment

World Health Organization (2023) ‘Mental health at work’. Available at: https://www.who.int/news-room/fact-sheets/detail/mental-health-at-work