Project Planning and Management in Workplace

Lecturer’s name: DR Paul.

BMSW 5104

BA Leadership and Management

Ridwan Dahir                                  1714111

1) Introduction:

Vinter’s is a company that collects and sells antique items through its store. The company has a warehouse also situated in Sparkhill. The shop is not generating enough revenues and hence the company also a proposal from Tesco where Tesco can buy the shop of Vinter’s. The company can focus on switching to warehouse where the antiques can then be sold through warehouse directly. Warehouse can be renovated and the antiques can be sold directly by attracting customers or even listing the products on website. This report focuses on the scope, cost and time duration of the project and provides reasoning as to why the appropriate cost or timeline has been chosen.  Also the report focuses on the iron triangle and how the constraints of iron triangle can have associated risks. In the preparation of the project it has been assumed that the workers will work for 10 hours continually for seven days without any break for weekend.

2) Scope:

According to Fageha & Aibinu (2013), project scope definition is a critical aspect before starting any project as this helps in defining the project for execution. Gibson et al. (2006) defined project scope as project definition which is required to provide all the information to project workers so that the work can be performed without any major changes which can impact the performance of the project and have associated impact on cost and quality of the project. Therefore having a well-designed project scope is crucial for project of Vinter’s so that a satisfactory project outcome can be received for renovation of the warehouse. Sharma & Lutchmann (2006) defined that the project scope definition can be highly incomplete and project may fail if the inputs are not taken from all the stakeholders. The scope definition of the Vinter’s project should ideally take input from Vinter’s family and associated employees such as Suha Madani, Omar King & even Paul Ranson. The initial requirement of the project is that the warehouse of Vinter’s in Sparkhill should be renovated so that the customers can be attracted and even proper storage space should be ensured so that the items can even be shipped through orders received from website. The scope of the project hence includes:

- Tidying the warehouse and creating a dedicated layout for the existing concrete warehouse. Designing an attractive warehouse will help in attracting the customers and even retaining customers. In terms of tidying work it is important that warehouse is properly painted, tiling or attractive wallpapers are done on the welcome areas and proper lighting is done.

- Creating a reception area for guests that can also function as billing area for customers that want to buy directly from warehouse. This will also help in area saving with both reception and billing area attached.

- Creation of a dedicated office so that the workers can track orders and even implement functions such as accounting, website updating and even regular meetings.

- Creation of a separate room for cleaning, restoring and photographing the antique elements which can be later updated on website and be also put on display to attract customers.

- A dedicated area where incoming antiques can be stored and packaged when ordered is also needed. After initial storing the antiques can be taken to a separate room where the remaining operations can be done.

- A dedicated small area for quick breaks is needed that can have attached restrooms for all the employees.

- The warehouse has to be connected with internet and phone lines so that the website can be maintained and any queries can be answered on phones to the customers.

- A dedicated website hosting that can attract online sales.

A work breakdown structure is decomposition of the project scope which can easily help in easier identification of deliverables and objectives. (Globerson, 1994) The project scope definition has been done according to the project needs and a work breakdown structure has been created (Dg. 1).

Work-Breakdown for Vinter’s

Area for Quick Breaks

1.3) Final Phase

1.1) Project Start Phase

1.2) Construction

Painting

1.1.1) Creating attractive Layout

Lighting

Area for initial storage and packaging

Wallpaper or Tiles use on walls

Layout Design

Internet and Phone Connection

Cleaning, Restoring and photographing Room

Buying Resources

Website Hosting

Dedicated office and Reception

Contracting workers

Dg.1 Work Breakdown Structure: Vinter’s

3) Time:

The time management is the component of the project management in which an overall timeline for any project is created so that the project can be successfully executed ( Solis, Corona-Suárez & García-Ibarra, 2015). Ensuring time management processes are important so that the project is not delayed and hence cost and scope of the project is not compromised. The time management aspect of project should include activity definition, duration estimating of the activity and even schedule monitoring. It has been also proved that the organisations which focus on time management aspect have higher completion rate than organisations where time management aspect is not even considered.

The timeline of completion has been done through Gantt chart creation. According to Geraldi & Lechter (2012), Gantt chart is one of the most used project management tools that can be effectively used to develop critical tasks (Table 1) that are needed for completion of project and final delivery. The Gantt chart is shown in Dg. 2.

Dg.2 Vinter’s Gantt Chart

| TASK NAME | START DATE | DAY OF MONTH* | END DATE |
| --- | --- | --- | --- |
| Layout Design | 07/06/2021 | 7 | 10/06/2021 |
| Buying Resources | 11/06/2021 | 11 | 17/06/2021 |
| Contracting Workers | 18/06/2021 | 18 | 18/06/2021 |
| Construction Area for Breaks | 21/06/2021 | 21 | 24/06/2021 |
| Construction area for initial storage | 21/06/2021 | 21 | 24/06/2021 |
| Cleaning Room Construction | 21/06/2021 | 21 | 24/06/2021 |
| Construction of Reception and Office | 21/06/2021 | 21 | 27/06/2021 |
| Painting | 24/06/2021 | 24 | 12/07/2021 |
| Lighting | 13/07/2021 | 13 | 16/07/2021 |
| Wallpapers or Tiles on Walls | 17/07/2021 | 17 | 20/07/2021 |
| Internet and Phone connection | 20/07/2021 | 20 | 21/07/2021 |
| Website Hosting | 22/07/2021 | 22 | 22/07/2021 |

Table 1: Gantt Chart Activities

In the Gantt chart, it has been assumed that the work starts on 07/06/2021 and based on this the work is completed on 22/07/2021. For construction of timeline, the activity has been taken from scope statement and work breakdown structure. The estimation of individual activity and reasoning as follows:

- The layout design can be made in four days and it is due to the fact that appropriate recommendations have been taken from all the stakeholders of Vinter’s. Taking of recommendations and understanding of scope will take time.

- After properly understanding of scope and designing of layout, basic resources have to be bought which can be done in a week since different items would have to be sourced from different locations example – furniture.

- For contracting workers, the best agency in town will be selected for construction and this will take one day.

- The construction workers will be put in place for four different areas storage area, break area, cleaning area and reception and office. It would take between four to seven days for construction to finish when four workers are employed per construction area. This is due to the fact that, according to The Chartered Institute of Building (2016), the productivity levels of construction workers is extremely low when compared with other developed countries such as USA and France. This means that more workers (four per construction area) will be required to complete the process of construction between four to seven days.

- The paint work for Vinter’s warehouse will take most of the time. As Cladding spraying and even internal wall painting will have to be done. According to Diamond (2021), the warehouse can be made more attractive by using floor painting such as Decora Quartz System. This will overall add to the look of the warehouse albeit at certain cost. It is estimated that overall drying and painting work will be completed in 19 days with around 8 painters hired on contractual bases.

4) Cost:

Project cost management is an important process in realization of the project as the project has to be complemented with certain budget. Hence it is the duty of the managers to estimate the costs in a realistic manner (Anicic & Anicic, 2019). Also initial cost estimation can help the organisation in determining whether the project should go ahead or not. Vinter’s is suffering in terms of financial resources and the company has to see whether the selling of current shop to Tesco and renovating the warehouse can be overall profitable to the company. The overall cost analysis is as follows (Table 2):

| Component | Cost |
| --- | --- |
| Layout Design by Expert | £ 1000 |
| Buying Basic Resources | £ 5000 |
| Contracting Workers for construction | £ 7600 (16 workers – 4 days and 4 worker – 3 days – 10 hours per day) |
| Paint Work | £ 10,000 |
| Lighting | £ 5000 |
| Wallpaper or Tiles Pasting (in few places) | £ 6000 |
| Internet and Phone Connection | £ 50 monthly |
| Website Hosting | £ 60 payed annually |
| Total cost | £ 34710 |

Table 2: Costs Estimation

The website hosting can be done through Wix (2021), which will cost just £ 60 annualy and Vinter’s family can easily create a secure website according to needs and can control the layout through Wix application. According to PriceYourJob (2020), the cost in UK to wallpaper a room can be £ 300 and hence for the whole warehouse the cost can be approximately £ 6000. The installation of lights can be £ 60 for a single light and hence for all the warehouse (around 80 lights), the costs can be £ 5000. For estimation of construction work, in 4 days, 16 workers will work for 10 hours and the cost of one hour work per worker is £ 10.87 (Indeed, 2021) and hence the approximate cost will be £ 7600. The cost of paint of walls and floors including labour will be £ 10,000 as approximated from the home painting cost provided by Home Advice Guide (2021). Various resources will be bought by the organisation including lights, attractive wallpapers and office supplies this can cost to be £ 5000. Internet and phone connectivity can be taken from any organisation such as BT and Virgin and this will approximately cost £ 50.

5) Iron Triangle:

Iron Triangle can be described as a ‘long-standing’ model that can help any organisation in a dynamic way particularly in relation to achieving priorities for completion of project. According to Pollack, Helm & Adler (2018), iron triangle is also known as Triple constraint and it is a concept that is central to management of projects in practice. The iron triangle represents the performance criteria’s of the project that should be met. Even when the project managers don’t acknowledge the use of iron triangle in any managed project, it is confirmed that managers would have worked through the project using triple constraints. The three constraints that any project managers work with are scope, budget and schedule. Depending on the project that has been undertaken, the three constraints can have varying importance level.  As demonstrated by Pollack, Helm & Adler (2018), the links of time, cost and quality were found to be more significantly stronger and more effective than link to alternative such as performance, scope or requirements. The quality component is at the middle of triangle and to achieve success in delivering any project the managers have to balance all the trade-offs considering these three elements.

5.1) Budget and Risks to the Project:

Considering the budget and costs of the project, it can be pointed out that the Vinter’s family will have a limited budget to redesign the warehouse properly so that people can be attracted to warehouse for direct selling. According to National Research Council (2005) one of the main risk for any project is the fact that project costs can be more than what has been budgeted. This can be true for warehouse of Vinter’s too as some of the work will be done by contractual workers and the cost will increase with delay in completion of work by contractual workers. The cost of interior furniture can increase depending on the quality of furniture of so purchased. Similarly any wastage particularly in relation to breakage or wastage of materials such as tiles or any glass materials during renovation can further increase the costs. There is also risk in digitalising of the warehouse as the costs for running a website and even tools for bill generation can be greater in comparison to the estimated costs. Cost risk for Vinter’s can directly lead to risk of performance where the family may think to reduce the quality or scope of work so that the budgeted cost can be achieved.

The costs risk can be managed by proper planning project costs involving all stakeholders of Vinter’s. Also the risks should be categorised and well planned for. The risk identification and mitigation plan for risks associated with cost is given in Table 3.

| Risk Cost | Probability | Mitigate |
| --- | --- | --- |
| Wastage of materials | High | Due diligence to be given in transportation and placing of materials |
| Delay in completion by workers | High | Initially fix cost with workers & specify amount of time |
| High Furniture costs | Low | Collecting furniture from various sources |
| High cost for technological changes | Medium | Comparing technological plans for all tools |

Table 3: Risks associated with Cost

5.2) Schedule and Risks to the Project:

According to Hulett (2016), is also a main project risk that can have significant impact on cost and even quality of the project. In case of any project there is a risk that project can take longer than expected especially during the implementation phase. There is a direct impact on costs risks with delay in schedule, as the projects that are delayed cost more for the company. Similarly there is a threat to performance risk as well where delays in schedule can force the organisation to create a project that even doesn’t fulfil its desired mission fully.  Also there can be a case that the costs increase are not too much with delays but the value of the project is definitely reduced with the delays.

For Vinter’s warehouse the major schedule risks are namely re-estimation of scope, inability to collect resources, basing schedule on workers without booking and optimistic schedule creation. The same has been highlighted in Table 4 and even a mitigation plan has been shown for successfully dealing with associated risks.

| Risk Schedule | Probability | Mitigate |
| --- | --- | --- |
| Schedule based on contract workers who are not available | Low | Finding contract workers early and booking them for certain dates. |
| Re-estimation of scope (New Requirements) | Medium | Using all stakeholders and defining requirements all at once |
| Tough to collect resources | Low | Proper planning of resources before starting implementation |
| Schedule created is optimistic | Low | Need for creation of realistic schedule |
| No budget for implementation | Low | Initially budget has to be calculated and passed before starting the project |

Table 4: Risks associated with Schedule

5.3) Scope and Risks to the Project:

Product scope includes the various functions and features of the products and it is useful in documenting the set goals of the project. In any project, scope creep can occur. This generally includes the risks where any project fails to meet the requirements that are set. If the scope is not defined carefully and is regularly changed by the stakeholders then there can be associated risks to costs and duration of the project.

The major risk in development of warehouse (Table 5) is no prioritization of requirements, which can lead to large delays in projects and can even built up costs. Similarly Vinter’s family can add features to the project at a later stage for example – including implementation of solar energy source in the warehouse. Also during the implementation of project, there can be failure to identify general requirements for successful project such as correct amount of furniture, number of tiles, amount of paint to name a few.

| Risk Scope | Probability | Mitigate |
| --- | --- | --- |
| Vinter’s family may add more features to the project | Low | Finding contract workers early and booking them for certain dates. |
| Failure to identify project requirements | Low | Using all stakeholders and defining requirements all at once |
| No prioritization of requirements | High | Proper planning of resources before starting implementation |

Table 5: Risks associated with Scope

6) Conclusion:

In conclusion, the project can be completed in 46 days and the cost for the project will be £ 34, 710, this is depending on the scope as defined in the report. The report has also highlighted how the costs, time and scope of the project has been estimated from different sources. The iron triangle has been used to highlight the risks associated with budget, time and scope constraints.

7) References:

- Anicic, D. J. & Anicic, J. (2019) ‘Cost management concept and project evaluation methods’, Journal of Process Management New Technologies, 7(4), pp. 54-59.

- Chartered Institute of Building (2016) Productivity in Construction. Available at: https://www.ciob.org/industry/research/Productivity-Construction-Creating-framework-industry-thrive (Accessed: 01/April/2021).

- Diamond (2021) Floor Painting. Available at: https://diamonddecorators.co.uk/floor-painting-2/ (Accessed: 01/April/2021).

- Fageha, M. K. & Aibinu, A. A. (2013) ‘Managing Project Scope Definition to Improve Stakeholders’ Participation and Enhance Project Outcome’, Procedia – Social & Behavioural Sciences, 74, pp. 154-164.

- Geraldi, J. & Lechter, T. (2012) ‘Gantt charts revisited: A critical analysis of its roots and implications to the management of projects today’, International Journal of Managing Projects in Business, 5(4), pp. 578-594.

- Globerson, S. (1994) ‘Impact of various work-breakdown structures on project conceptualization’, International Journal of Project Management, 12(3), pp. 165-171.

- Home Advice Guide (2021) A Guide To Painting Your Home: Paint Types, Prices & Painters’ Charges. Available at: https://www.homeadviceguide.com/how-much-does-paint-cost/ (Accessed: 01/April/2021).

- Hulett, D. (2016) Practical Schedule Risk Analysis. New York: Gower Publishing.

- Indeed (2021) How much does a Construction Worker make in United Kingdom? Available at: https://uk.indeed.com/career/construction-worker/salaries (Accessed: 01/April/2021).

- National Research Council (2005) The Owner’s Role in Project Risk Management. Washington: The National Academia Press.

- Pollack, J., Helm, J. & Adler, D. (2018) What is the Iron Triangle, and how has it changed?, International Journal of Managing Projects in Business, 11(4), pp. 527-547.

- PriceYourJob (2020) The Cost To Wallpaper a Room. Available at: https://www.priceyourjob.co.uk/wallpaper-room-cost/ (Accessed: 01/April/2021).

- Solis, R., Corona-Suárez, G. A. & García-Ibarra, A. J. (2015) ‘The Use of Project Time Management Processes and the Schedule Performance of Construction Projects in Mexico’, Journal of Construction Engineering, 2015(1), pp. 1-9.

- Wix (2021) The Leader in Website Creation. Available at: https://www.wix.com/html5uk/leader?utm_source=google&utm_medium=cpc&utm_campaign=1652383858%5E65123661082&experiment_id=%2Bweb%20%2Bsite%5Eb%5E338733948418%5E&cq_src=google_ads&cq_cmp=1652383858&cq_con=65123661082&cq_term=%2Bweb%20%2Bsite&cq_med=&cq_plac=&cq_net=g&cq_pos=&cq_plt=gp&gclid=EAIaIQobChMIxZfB5Jfx7wIVkDMrCh2KPwT3EAAYAiAAEgLj1fD_BwE (Accessed: 01/April/2021).