## Budget
Glengarnock Castle - Community Archaeology Project
BUDGET
Resource | Rate | Days | Sub total | Total
Project Team
Project Executive | 250 | 5.5 | 1375
Project Assurance Officer | 250 | 5.5 | 1375
Project Manager | 200 | 36 | 7200
Expert Team Leader | 170 | 9 | 1530
Expert - Fieldwork Strategy | 140 | 11 | 1540
Expert - On site and online communication | 120 | 11 | 1320
Expert - Geophysical and Topographical Survey and reporting | 180 | 10 | 1800
Expert - Fieldwork Supervisor, Post excavation processes, assessment/analysis reporting | 130 | 27.5 | 3575
Expert - Fieldwork Supervisor | 120 | 8.5 | 1020
Expert - Historic Building recording Fieldwork, pottery and small finds specialist assessment reporting and analysis | 180 | 14 | 2520
Expert - Historic Building recording Fieldwork and specialist reporting and analysis | 180 | 10 | 1800
Expert - Specialist zooarchaeological assessment reporting and analysis | 200 | 10 | 2000
Expert - Specialist Paleoenvironmental assessment reporting and analysis | 200 | 12 | 2400
29455
Other costs
Travel / expenses |  |  | 1500
Accommodation |  |  | 2000
Van Hire |  |  | 300
Site Consumables (Finds Bags, sample bags, labels, records sheets etc) |  |  | 200
Site Welfare |  |  | 1800
Archive Deposition Fees |  |  | 1200
7000
| SUB-TOTAL | 170 |  | 36455
Overheads (10% of sub total) |  |  |  | 3645.5
| TOTAL |  |  | 40100.5
(Please note: For the purposes of this assignment, all budgeted rates and costs are fictional)

## GANTT
Product No./Name
| 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
1 - Finalised PD & Risk Log | 2021-06-01: 13
2 - Permissions | bar: 2021-06-01
3 - RAMS/H&S Plan | bar: 2021-06-01
4 - Field Archive | 2021-07-01: 20.5
5 - Social Timeline/Dig Broadcast | 2021-07-01: 4
6 - Stratigraphic Assessment | 2021-08-01: 2.5
7 - Specialist Finds Assessment | 2021-09-01: 0.5; 2021-10-01: 2.5; 2021-11-01: 1.5; 2021-12-01: 0.5; 2022-01-01: 5.5
8 - Integrated Assessment Report | 2022-02-01: 0.5; 2022-03-01: 3
9 - Updated Project Design | 2022-03-01: 12
10 - Finalised UPD & Risk Log | 2022-04-01: 2.5; 2022-05-01: 4.5
11 - Permissions | bar: 2022-05-01
12 - RAMS/H&S Plan | bar: 2022-05-01
13 - Field Archive | 2022-05-01: 21
14 - Social Timeline/Dig Broadcast | 2022-05-01: 4
15 - Stratigraphic Assessment | 2022-06-01: 2.5
16 - Specialist Finds Assessment | 2022-07-01: 0.5; 2022-08-01: 2; 2022-09-01: 1; 2022-10-01: 2; 2022-11-01: 2
17 - Integrated Assessment Report | 2022-11-01: 0.5; 2022-12-01: 3
18 - Post Excavation Research Design | 2022-08-01: 2; 2022-09-01: 1; 2022-10-01: 3; 2022-11-01: 6; 2022-12-01: 3
19 - Draft Analysis Report | 2022-08-01: 3; 2022-09-01: 2; 2022-10-01: 3; 2022-11-01: 6; 2022-12-01: 7.5
20 - Approval of Final Analysis Report | 2022-12-01: 7
21 - Full Dissemination of Results | 2023-03-01: 2
22 - Project Archive Deposition | 2022-12-01: 1; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 1
23 - End of Project Report | 2023-03-01: 3
Total Person Days | 15 | 24.5 | 2.5 | 0.5 | 2.5 | 1.5 | 0.5 | 5.5 | 0.5 | 15 | 2.5 | 31.5 | 2.5 | 0.5 | 7 | 4 | 8 | 14.5 | 21.5 | 2 | 2 | 6
Staff Cost Per Month | 2820 | 3560 | 360 | 100 | 460 | 280 | 100 | 1150 | 100 | 2610 | 490 | 4955 | 360 | 100 | 1340 | 740 | 1570 | 2530 | 3730 | 400 | 400 | 1300 |  | 29455
Travel / expenses | 2021-07-01: 750; 2022-05-01: 750 |  | 1500
Accommodation | 2021-07-01: 1000; 2022-05-01: 1000 |  | 2000
Van Hire | 2021-07-01: 150; 2022-05-01: 150 |  | 300
Site Consumables (Finds Bags, sample bags, labels, records sheets etc) | 2021-07-01: 100; 2022-05-01: 100 |  | 200
Site Welfare | 2021-07-01: 900; 2022-05-01: 900 |  | 1800
Archive Deposition Fees | 2023-03-01: 1200 |  | 1200
TOTAL COST PER MONTH (Less overheads) | 2820 | 6460 | 360 | 100 | 460 | 280 | 100 | 1150 | 100 | 2610 | 490 | 7855 | 360 | 100 | 1340 | 740 | 1570 | 2530 | 3730 | 400 | 400 | 2500 |  | 36455
(Please note: For the purposes of this assignment all resources, rates and costs are fictional) | [23 empty] | 0 | Check Sum
Person Days by Team Role
Project Executive | 2021-06-01: 0.5; 2022-01-01: 0.5; 2022-03-01: 0.5; 2022-05-01: 1; 2022-11-01: 1; 2022-12-01: 1; 2023-03-01: 1 | 5.5
Project Assurance Officer | 2021-06-01: 0.5; 2022-01-01: 0.5; 2022-03-01: 0.5; 2022-05-01: 1; 2022-11-01: 1; 2022-12-01: 1; 2023-03-01: 1 | 5.5
Project Manager | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 1 | 3 | 0.5 | 0.5 | 1 | 1 | 2 | 2.5 | 3.5 | 2 | 2 | 4 | 36
Expert Team Leader | 2021-06-01: 1; 2021-07-01: 2; 2022-03-01: 1; 2022-05-01: 2.5; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 0.5 | 9
Expert - Fieldwork Strategy | 2021-06-01: 1; 2021-07-01: 4; 2022-03-01: 1; 2022-05-01: 4.5; 2022-12-01: 0.5 | 11
Expert - On site and online communication | 2021-06-01: 1; 2021-07-01: 4; 2022-03-01: 1; 2022-05-01: 4.5; 2022-12-01: 0.5 | 11
Expert - Geophysical and Topographical Survey and reporting | 2021-06-01: 1; 2021-07-01: 2; 2022-03-01: 1; 2022-05-01: 2.5; 2022-11-01: 1; 2022-12-01: 2.5 | 10
Expert - Fieldwork Supervisor, Post excavation processes, assessment/analysis reporting | 2021-07-01: 4; 2021-08-01: 2; 2022-03-01: 3; 2022-05-01: 4; 2022-06-01: 2; 2022-11-01: 6; 2022-12-01: 6.5 | 27.5
Expert - Fieldwork Supervisor | 2021-07-01: 4; 2022-05-01: 4; 2022-12-01: 0.5 | 8.5
Expert - Historic Building recording Fieldwork, pottery and small finds specialist assessment reporting and analysis | 2021-06-01: 1; 2021-07-01: 2; 2021-10-01: 2; 2022-03-01: 1; 2022-05-01: 2.5; 2022-08-01: 2; 2022-09-01: 2; 2022-12-01: 1.5 | 14
Expert - Historic Building recording Fieldwork and specialist reporting and analysis | 2021-06-01: 1; 2021-07-01: 2; 2021-11-01: 1; 2022-03-01: 1; 2022-04-01: 0.5; 2022-05-01: 2; 2022-08-01: 1; 2022-09-01: 1; 2022-12-01: 0.5 | 10
Expert - Specialist zooarchaeological assessment reporting and analysis | 2021-06-01: 1; 2022-01-01: 2; 2022-03-01: 1; 2022-04-01: 0.5; 2022-08-01: 2; 2022-10-01: 2; 2022-12-01: 1.5 | 10
Expert - Specialist Paleoenvironmental assessment reporting and analysis | 2021-06-01: 1; 2022-01-01: 2; 2022-03-01: 1; 2022-04-01: 0.5; 2022-08-01: 1; 2022-10-01: 3; 2022-11-01: 2; 2022-12-01: 1.5 | 12
Total Person Days | 15 | 24.5 | 2.5 | 0.5 | 2.5 | 1.5 | 0.5 | 5.5 | 0.5 | 15 | 2.5 | 31.5 | 2.5 | 0.5 | 7 | 4 | 8 | 14.5 | 21.5 | 2 | 2 | 6 | 170
Check Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0