## Data Entry
FAILURE MODE AND EFFECTS ANALYSIS
Trial: | X0001 |  |  | Responsibility: |  | Trials Manager |  |  |  | FMEA number: | 1
Version: | 1 |  |  | Prepared by: |  | Thomas Clayton |  |  |  | Page : | 1
Core Team: | T Clayton, I Marrs, Harry McAuliffe | [8 empty] | FMEA Date (Orig): | 2017-04-24 | Rev: |  | N/A
Process Function | Potential Failure Mode | Potential Effect(s) of Failure | Sev | Potential Cause(s)/ Mechanism(s) of Failure | Occur | Current Process Controls | Detec | RPN | Recommended Action(s) | Responsibility and Target Completion Date | Action Results
[11 empty] | Actions Taken | Sev | Occ | Det | RPN
Hazardous Activity Risk Assessment Construction/Failure mode Analysis for Trial X0001 Plate Proof | Insufficient control measures to prevent harm/damage | Multiple Fatalities | 10 | Failure to Establish suitable control measures | 6 | Constructed by a single individual with nearly 10 years trials experience | 6 | 360 | Follow the safety management structure set out by QQ internal documentation. | Immediate-Thomas Clayton | Reviewed HARA/FMEA with a team of technical experts | 10 | 2 | 2 | 40
Preparation/Delivery/Post Preparation of the Trial | Slips Trips and Falls | Single Person, Serious Injury (broken bones) | 7 | Human Error | 5 | Individual awareness | 8 | 280 | All persons to be briefed on the battery layout. All persons to be made aware of cabling and ducting, high visibility tape to be applied to raised edges. Trauma trained first aiders to be available at all times on the battery' | Immediate-Thomas Clayton | Safety brief before activity start, listed PPE requirements for staff (Steel toe cap boots minimum) | 7 | 3 | 9 | 189
Preparation/Delivery/Post Preparation of the Trial | Dropped target plate during setup | Crush injury+ Potential material damage | 7 | Human Error | 4 | Yearly manual handling training | 8 | 224 | Two man lift under supervision. | Immediate-Thomas Clayton | Leather protective gloves and steel toe caps to be worn. Supervised two man lift. | 5 | 2 | 5 | 50
Ammunition Preparation | Unintended initiation of propellant during round construction | Single person, serious burns (insufficient propellant mass to cause death)' | 7 | Static discharge, Impact Friction, Human Error | 4 | Ammunition is only to be prepared in a suitably licenced building | 5 | 140 | Anti Static precautions to be applied | Immediate- Ammo technical lead | Complete antistatic clothing and fire retardant to be worn throughout round makeup, only tools of a non-ferrous nature to be used | 4 | 2 | 5 | 40
Preparation/Delivery/Post Preparation of the Trial | Lifting Tackle failure | Multiple Fatalities | 10 | Lifting tackle which is damaged or has insufficient capacity used. | 6 | Lifting operations and lifting equipment regulations 1998 to be followed | 6 | 360 | Staff Training, Lifting plans, Supervision | Immediate-Training manager | All persons to be appropriately qualified slingers under the direct supervision of a SME. A lifting plan must be constructed prior to any operations | 10 | 3 | 3 | 90
Delivery | Unintended initiation of a loaded weapon system | Multiple Fatalities | 10 | Human Error, Communications breakdown | 4 | Training/Competence of Gun foreman on the weapon system | 8 | 320 | Gun foreman to have his competence extensively tested. Regular Health checks. Weapon system not be loaded until all personnel are reported undercover. Loading of the weapon system is only to commence on the order of Trials manager | Immediate, Trials manager/Process controller | All recommended actions | 10 | 1 | 3 | 30
Delivery | Ricochet of the projectile | Projectile ricochets back towards weapon system | 5 | Projectile fails to penetrate armoured plate | 7 | Shore 1 Battery is designed to contain small arms firings | 7 | 245 | All battery personnel to be undercover during firing, Weapon system is to be placed 100m from target to prevent ricochet returning to the firing position. | Immediate-Trials Manager- Trials Design | All recommended actions | 2 | 5 | 7 | 70
Delivery | Failure to fire/Miss fire of the weapon system | Unauthorised discharge of the weapon, Multiple Fatalities | 10 | Weapon firing pin failure, Slow burning propellant etc. | 4 | Rugged and proven weapon system | 4 | 160 | Construction of a failure to fire misfire procedure | QQ OME manager | Misfire drills produced in SAF\158\MS\2.0 | 5 | 4 | 4 | 80
Ammunition Preparation | Round initiation when crimped | Discharge of projectile resulting in death | 7 | Compression of propellant grains causing adiabatic heating. | 5 | Staff suitably trained and competent for activity | 10 | 350 | Ensure that staff keep up competency, regular training. | Ammunition lead/manager on site | PPE and suitable checks on staff competency/facilities. | 7 | 2 | 5 | 70
Ammunition Preparation | Incorrect propellant type supplied | Single Fatality | 7 | Overpressure of the weapon system resulting in low order detonation | 5 | Propellant is commercially available and therefore subject to manufacturer controls | 4 | 140 | Gun foreman to ensure weapon system shows no signs of over pressure between each firing, through visual inspection. Ammo to ensure correct propellant by cross referencing with issue voucher. | Trials manager, During Delivery | Propellant pressure response modelled by technical lead at Fort Halstead. This sets pre-determined limits on prop mass. | 7 | 2 | 2 | 28
Delivery | Sky screen instrument failure | Loss of customer data | 3 | Power Cut, Pre/Post triggering, | 6 | PAT testing. | 7 | 126 | Regular inspection of equipment (yearly), Regular Calibration and electrical testing. | Immediate, Instrumentation Officer | All recommended actions | 3 | 4 | 4 | 48

## About This Template
This template was written for the American Society for Quality by
Stat Aids
Your feedback is welcome and encouraged. Please e-mail to:
Stat_Aids@yahoo.com