## Sheet1
Dissertation
|  |  | Block 1 |  |  |  |  | Block 2 |  |  |  |  | Block 3 |  |  |  | XMAS | XMAS |  | Block 4 |  |  |  |  | Block 5 |  |  |  |  | Easter | Easter | Block 6 |  |  |  |  | Block 7
Deliverables | Owner | Duration | W1 - 14/9 | W2 - 21/9 | W3 - 28/9 | W4 - 5/10 | Prep Week | W1 -19/10 | W2 - 26/10 | W3 - 2/11 | W4 - 9/11 | Prep Week | W1 - 23/11 | W2 - 30/11 | W3 - 7/12 | W4 - 14/12 | W1 - 21/12 | W2 - 28/12 | Prep Week | W1 - 11/1 | W2 - 18/1 | W3 - 25/1 | W4 - 01/2 | Prep Week | W1 - 15/2 | W2 - 22/2 | W3 - 01/3 | W4 - 08/3 | Prep Week | W1 - 22/3 | W2 - 29/3 | W1 - 05/4 | W2 - 12/4 | W3 - 19/4 | W4 - 26/4 | Prep Week | W1 - 10/5 | W2 - 17/5 | W3 - 24/5 | W4 - 31/5
Research | J.S | 24 WEEKS | 6HR | 6HR | 6HR | 6HR | 6HR | 2HR | 2HR | 2HR | 2HR | 6HR | 2HR | 2HR | 2HR | 2HR | HOLIDAY | 3HR | 3HR | 3HR | 3HR | 3HR | 3HR | 3HR | 3HR | 3HR | 3HR |  | HOLIDAY | HOLIDAY
Reading | J.S | 24 WEEKS | 9HR | 9HR | 9HR | 9HR | 2HR | 4HR | 4HR | 4HR | 4HR | 9HR | 4HR | 4HR | 4HR | 4HR | HOLIDAY | 7HR | 7HR | 7HR | 7HR | 7HR | 7HR | 7HR | 7HR | 7HR | 7HR |  | HOLIDAY | HOLIDAY
Planning | J.S | 2 WEEKS |  |  |  |  | 6HR |  |  |  |  | 3HR |  |  |  |  | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY
Introduction | J.S | 2 WEEKS | [9 empty] | 5HR | 2HR |  |  |  | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY
Chapter 1 | J.S | 2 WEEKS | [14 empty] | HOLIDAY | 5HR | 5HR | [9 empty] | HOLIDAY | HOLIDAY
Chapter 2 | J.S | 2 WEEKS | [14 empty] | HOLIDAY |  |  | 5HR | 5HR | [7 empty] | HOLIDAY | HOLIDAY
Chapter 3 | J.S | 2 WEEKS | [14 empty] | HOLIDAY |  |  |  |  | 5HR | 5HR | [5 empty] | HOLIDAY | HOLIDAY
Chapter 4 | J.S | 2 WEEKS | [14 empty] | HOLIDAY | [6 empty] | 5HR | 5HR |  |  |  | HOLIDAY | HOLIDAY
Conclusion | J.S | 2 WEEKS | [14 empty] | HOLIDAY | [8 empty] | 5HR | 5HR |  | HOLIDAY | HOLIDAY
Assesments | J.S | UNKNOWN |  |  |  | JOURNAL 5% | [10 empty] | HOLIDAY |  |  |  | T.B.C - 5% | [7 empty] | HOLIDAY | HOLIDAY | [6 empty] | T.B.C - 90%
Drafts | H.W | 4 WEEKS | [14 empty] | HOLIDAY | [9 empty] | SEND DRAFT |  | HOLIDAY | HOLIDAY | SEND DRAFT |  | SEND DRAFT |  | SEND DRAFT
Revising Drafts | J.S | 4 WEEKS | [14 empty] | HOLIDAY | [10 empty] | 4HR | HOLIDAY | HOLIDAY |  | 4HR |  | 4HR |  | FINISH DISS
Lectures | J.S | 16 WEEKS | [5 empty] | 12HR | 12HR | 12HR | 12HR |  | 12HR | 12HR | 12HR | 12HR | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY |  | 12HR | 12HR | 12HR | 12HR |  | 12HR | 12HR | 12HR | 12HR
Reading |  | 20 WEEKS |  |  |  |  | 5HR | 5HR | 5HR | 5HR | 5HR | 2HR | 5HR | 5HR | 5HR | 5HR | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY | 6HR | 6HR | 6HR | 6HR | 6HR | 6HR | 6HR | 6HR | 6HR | 6HR
Assesments | J.S | UNKNOWN | [7 empty] | PRESENTATION | ESSAY |  |  |  | T.B.C | T.B.C | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY |  |  |  | T.B.C | T.B.C |  |  |  | T.B.C | T.B.C
Supervison Meetings | J.S | UNKNOWN | [14 empty] | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY
Meetings | J.S | UNKNOWN |  | CAREERS | [12 empty] | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY
[17 empty] | HOLIDAY | [11 empty] | HOLIDAY | HOLIDAY