Applied Leadership and Management in the Workplace
Module Assignment Submission

| Student Name: | Jodie Loosmore |
| --- | --- |
| Student Number: | 2320605 |
| Module No: | BMSK5014 |
| Module Title: | Project Management |

Statement of Confirmation of Authenticity

By the act of making this submission, the student declares that this is the work of the student named above. The work has not, in whole or in part, been knowingly presented elsewhere for assessment, or where assessment has been built on a previous assessment, this has been identified. Where materials have been used from other sources it has been properly acknowledged. If this statement is untrue, the student acknowledges that an assessment offence has been committed. Attention is drawn to the plagiarism and unfair practice policies of both the University and of ILM.

Table of Contents

Introduction	2

Business Case Objectives and Rationale	3

Project Management Methodologies and Application	4

Agile	4

V-Model	4

Risk Assessment and Constraints	4

Iron Triangle (Project Management Triangle)	5

Scope, Theme and Target Audience	6

Scope	6

In-Scope	6

Out-of-Scope	6

Theme: Loyalty Program/ Immersive Experience	7

Primary Segment: Experience Seekers	8

Secondary Segment: CRM-Engaged Guests	8

Stakeholder Communication Plan	8

Cost Benefit Analysis and ROI Calculation	10

CBA - “Loyal by Taste – A Culinary Celebration of Connection”	11

Project Organisation/Work Breakdown Structure	12

Critical Path Analysis	13

Task Durations and Dependencies	13

Implementing Kanban Method	13

Team Roles/Responsibilities	14

Control & Monitoring Framework: Time, Budget, Quality and Scope	15

Time	15

Budget	16

Quality	17

Scope	17

Change Management Process	17

Log the change Request	17

Authorisation	17

Change to Project Plan	18

Risk Management Risk	18

Implement the Change	18

Close	18

Project Manager Skills, Self-Assessment and PDP	19

References	20

# Introduction

“Loyal by Taste: A Culinary Celebration of Connection” is an event designed to bring people together through great food and strong relationships. Held in Swansea, this event celebrates loyal customers and shows how hospitality can create lasting emotional bonds. Guests will enjoy a carefully prepared tasting menu, each dish telling a story about the brand’s values, warmth, creativity and care. The event space, music, and service are all designed to make people feel connected and appreciated. It’s not just about eating, it’s about feeling a part of something meaningful (Pine & Gilmore, 1999). As digital touchpoints multiply and customer expectations rise, restaurants need to move beyond transactional encounters to develop more meaningful connections. Using strategies such as an experiential event, improves brand reputation and provides platforms for data-driven customer relationship management (CRM) (Kotler et al., 2017). Following the structured Project Management Process from concept to completion and integrating academic theories/models, ensures methodological accuracy and practical relevance (Verhoef et al., 2009). The main objectives of the event are to thank and keep loyal customers by giving them a memorable experience and to show what the brand stands for through food, design, and storytelling. The restaurant can learn from guests by collecting feedback and using it to improve loyalty programs and future event ideas. By combining great food, thoughtful design and smart customer insights, “Loyal by Taste” shows how restaurants can build deeper relationships and long-term loyalty.

# Business Case Objectives and Rationale

The main objectives for this event are as follows:

- Increase customer engagement and loyalty

- Generate revenue through ticketed experience and upselling

- Enhance customer satisfaction and brand perception.

- Collect actionable customer data for CRM optimisation.

Keeping existing customers is cheaper and more profitable than finding new ones. Reichheld and Sasser (1990) showed that improving customer retention by just 5% can increase profits by 25% to 85%. Loyal customers spend more, return often and recommend the brand to others. Hosting events like “Loyal by Taste” helps build strong emotional connections with customers. These experiences make the brand more memorable, encourage repeat visits and create chances to offer upgrades and collect useful customer data.

Garvin’s Eight Dimensions of Quality (1987) explains how customers judge quality. Hosting this event can improve:

Performance: Great food and service.

Features: Special touches like wine pairings or chef talks.

Aesthetics: Beautiful presentation and atmosphere.

Perceived Quality: How customers feel about the brand after the event.

By focusing on these areas, restaurants can make customers feel valued and more likely to return.

# Project Management Methodologies and Application

### Agile

Agile is an iterative and flexible project management approach that emphasises customer collaboration, rapid feedback and adaptive planning. It breaks work into short cycles (sprints) and encourages continuous improvement. Key traits of this approach are flexibility, responsiveness and team collaboration. This is best used for dynamic environments where customer needs evolve quickly. Agile is particularly effective in hospitality settings where customer preferences and operational variables shift rapidly (Highsmith, 2009). Agile supports flexible guest engagement by adjusting seating or menu based on live feedback.

### V-Model

The V-Model is a framework for verification and validation that assigns a testing phase to each stage of development. It guarantees the methodical testing and validation of each requirement. Crucial attributes include structured testing, traceability, and thoroughness. This model is ideal for systems that need precise validation, such as CRM data workflows. The V-Model is especially useful in structured environments where data integrity and traceability are critical (Forsberg et al., 2005). V-Model ensures CRM data integrity by validating that guest preferences and feedback are accurately captured and useable.

How each methodology process will be used in the event:

| Methodology | Application in Event | Justification |
| --- | --- | --- |
| Agile | Iterative planning of event features, menu tweaks and guest experience enhancements | Allows real-time adaptation based on guest feedback and operational observations |
| V-Model | Designing and validating CRM data collection and feedback systems | Ensures structured testing of data capture tools and feedback loops for accuracy |

# Risk Assessment and Constraints

Risk assessment is the process of identifying, analysing and managing potential threats that could impact a project’s success. It helps project teams anticipate problems and develop mitigation strategies to reduce uncertainty and protects the outcomes (Hillson & Simon, 2020). In hospitality, risk assessment is essential for managing operational, financial and reputational risks during events (Lock, 2020).

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Low Guest Turnout | Medium | High | Use targeted CRM campaigns and early RSVP tracking |
| Staff Shortages | Medium | Medium | Schedule backups and offer incentives for attendance |
| Supply Chain Delays | Low | Medium | Source ingredients locally and confirm delivery timelines |
| CRM System Failure | Low | High | Test systems in advance and have manual data collection forms |
| Negative Guest Feedback | Medium | Medium | Collect feedback live and respond promptly |
| Budget Overrun | Medium | High | Monitor spending weekly and set contingency funds |
| Health & Safety Incident | Low | High | Conduct pre-event safety checks and staff briefings |

This table helps prioritise risks based on their likelihood and impact, ensuring proactive management throughout the event lifecycle.

### Iron Triangle (Project Management Triangle)

The Triple Constraint Triangle also known as the iron triangle, is a basic project management tool that shows how time, cost, and scope are connected. It was introduced by Barnes, (1969) and is now a standard part of project planning

For this event the constraints are as follows:

Time - refers to the fixed date and schedule for planning, setup and execution.

Cost - includes the budget for food, staff, marketing and CRM tools.

Scope - covers the event goals, creating a personalised loyalty experience without changing the regular menu or making long-term investments.

Changing one part (such as adding more features to the event) could affect the others, such as needing more time or money. Using this triangle helps keep the event focused and balanced (Atkinson, 1999). Below is a visual example of the iron triangle:

# Scope, Theme and Target Audience

### Scope

This project focuses on planning and delivering a one-time loyalty event. To keep the project clear and manageable, the scope includes only short-term activities directly related to the event.

### In-Scope

- Planning the Event: Organising the menu, staff and logistics.

- Marketing: Promoting the event through CRM tools and social media.

- Running the Event: Hosting the experience and managing operations.

- Collecting Feedback: Using surveys and CRM data to learn from guests.

These tasks follow standard project management guidelines to keep the project focused and efficient.

### Out-of-Scope

- Changing the Regular Menu: The event menu is temporary and won’t affect long-term offerings.

- Big Investments: No renovations or major purchases will be made.

Keeping the scope limited helps avoid delays and extra costs (Kerzner, 2017).

### Theme: Loyalty Program/ Immersive Experience

“Loyal by Taste: A Culinary Celebration of Connection”, is an all-day event in the restaurant catering for 100 guests. Transforming the loyalty event into an immersive experience, celebrating customer commitment while deepening emotional and behavioural engagement. It aligns with CRM strategies and quality models by offering personalised, high-value interactions by driving customer engagement, collecting CRM data and boosting repeat business. A table mapping the loyalty program is as follows:

| Theme Element | Loyalty Program Features | CRM Strategy | Quality Dimension (Garvin, 1987) |
| --- | --- | --- | --- |
| Ingredient Integrity Showcase | “Transparency Tier” rewards for choosing sustainable dishes | Data capture on ethical preferences | Conformance, Perceived Quality |
| Personalised Tasting Menus | “Flavour Match” points for trying recommended dishes | CRM-driven personalisation via taste profiles | Performance, Features |
| Interactive Quality Stations | “Quality Explorer” badges for engaging with stations | Behavioural tracking for segmentation | Reliability, Aesthetics |
| Feedback Loop Activation | “Voice of the Guest” bonus points for feedback submission | Real-time data enrichment and sentiment analysis | Serviceability, Durability |
| Chef Storytelling Sessions | “Insider Access” for loyalty members | Exclusive content for high-tier members | Perceived Quality, Features |
| Surprise & Delight Moments | Randomised rewards based on engagement | Predictive analytics for reward timing | Responsiveness (TQM), Empathy (SERVQUAL) |

### Primary Segment: Experience Seekers

- Demographics: Aged 25–45, urban professionals, mid-to-high income

- Psychographics: Food enthusiasts, value authenticity and aesthetics, active on social media

- Behaviours: Frequently dine out, attend culinary events, open to trying new experiences

- Motivations: Seeking memorable dining moments, social engagement, and brand connection

### Secondary Segment: CRM-Engaged Guests

- Demographics: Existing loyalty program members, aged 30–60

- Psychographics: Brand-loyal, responsive to personalised offers, value recognition

- Behaviours: Repeat visitors, high engagement with CRM communications

- Motivations: Appreciation for exclusive access, rewards and tailored experiences

# Stakeholder Communication Plan

A stakeholder communication plan is a structured approach to ensuring that everyone involved in a project, such as team members, managers and customers, receives the right information, at the right time, through the right channels. This keeps everyone aligned which helps avoid confusion by clearly defining who needs to know what, when, and how. This ensures that all stakeholders are working toward the same goals. It improves decision-making with timely and accurate communication which allows stakeholders to make informed decisions, reducing delays and misunderstandings. It builds trust and engagement, when stakeholders feel informed and involved, they’re more likely to support the project and contribute positively. It also reduces risk by proactively sharing updates and addressing concerns, the plan helps prevent issues from escalating.

Stakeholders are individuals or groups who influence or are affected by the project. This plan outlines key stakeholders, their roles, interests and engagement strategies using The Power-Interest Grid model Mendelow, (1991), who introduced it as a strategic tool for stakeholder analysis. Mendelow’s Matrix helps categorise stakeholders based on their level of power to influence a project and their interest in its outcomes, guiding how they should be engaged throughout the project lifecycle. This model is especially effective in hospitality and event settings, where stakeholder expectations can shift rapidly and collaboration is key to success (Bourne, 2016). Effective stakeholder management is essential for the success of this event, Turner, (2016) highlights that communication planning is essential for stakeholder engagement, which directly influences project success.

Below is a table depicting the Mendelow’s Matrix, this leads to executing a stakeholder communication plan:

| Quadrant | Stakeholders | Role/Interest | Engagement Strategy |
| --- | --- | --- | --- |
| Manage Closely | Restaurant Owner, CRM Manager | High influence, deeply invested in success | Regular updates, strategic meetings |
| Keep Satisfied | Investors, Local Authorities | High influence, moderate interest | Periodic briefings, compliance checks |
| Keep Informed | Frontline Staff, Loyalty Members | Low influence, high interest in experience | Training, newsletters, feedback loops |
| Monitor (Minimal Effort) | Media, General Public | Low influence, low interest | Occasional updates, press releases |

- Manage Closely: Engage the restaurant owner and CRM manager in planning and execution. Their decisions shape the event’s success.

- Keep Satisfied: Ensure investors and regulators are informed of ROI and compliance.

- Keep Informed: Empower staff with training and keep loyalty members engaged via CRM tools.

- Monitor: Share general updates with media and the public to maintain brand visibility.

The stakeholder communication plan for the event is as follows:

| Event Manager | Oversee planning and execution | Ensure alignment across all teams | Weekly team meetings, email updates | Weekly | Event Manager |
| --- | --- | --- | --- | --- | --- |
| Marketing Lead | Promote the event and manage public relations | Drive attendance and media coverage | Social media, press releases, newsletters | Bi-weekly | Marketing Lead |
| Chef Coordinator | Coordinate participating chefs and menus | Ensure culinary consistency and quality | Chef briefings, email | Weekly | Chef Coordinator |
| Sponsorship Manager | Manage sponsor relationships and deliverables | Fulfil sponsor expectations | Sponsor meetings, reports | Monthly | Sponsorship Manager |
| Logistics Coordinator | Handle venue, equipment, and scheduling | Ensure smooth operations | Daily check-ins, task tracker | Daily | Logistics Coordinator |
| Finance Officer | Manage budget and payments | Maintain financial control | Budget reports, email | Bi-weekly | Finance Officer |
| Volunteer Coordinator | Recruit and manage volunteers | Ensure adequate staffing | Volunteer briefings, messaging app | Weekly | Volunteer Coordinator |
| IT Support | Set up and maintain tech infrastructure | Ensure reliable tech support | Tech checklist, email | Weekly | IT Support |
| CRM Specialist | Manage customer data and loyalty integration | Align CRM strategy and data capture | CRM dashboard, internal meetings | Weekly | CRM Specialist |
| Customer Service Team | Handle guest interactions and feedback | Prepare for inquiries and post-event support | Training sessions, handbook, email | One-time + follow-up | CRM Specialist |

# Cost Benefit Analysis and ROI Calculation

Cost-Benefit Analysis (CBA) is a systematic decision-making tool used to evaluate the feasibility and desirability of a project by comparing its total expected costs against its anticipated benefits (Boardman et al., 2018). It helps organisations allocate resources efficiently by quantifying both tangible and intangible factors in monetary terms (Yates, 1985). CBA is widely applied in business, government, and healthcare to ensure that initiatives deliver maximum value and impact (Ashikuzzaman, 2024). Informed Decision-Making CBA helps decision-makers evaluate whether a project’s benefits outweigh its costs, enabling more rational and transparent choices (Boardman et al., 2018).

- Efficient Resource Allocation - By quantifying impacts in monetary terms, CBA ensures that limited resources are directed toward initiatives with the highest net value (Yates, 1985).

- Comparability Across Projects - CBA provides a common metric typically the benefit-cost ratio (BCR) to compare diverse projects, even across sectors.

- Inclusion of Intangible Impacts - While some benefits (e.g., brand equity or customer satisfaction) are hard to monetise, CBA encourages their consideration through supplementary techniques like multi-criteria analysis

- Strategic Planning Support - CBA supports long-term planning by forecasting future costs and benefits, helping organisations anticipate risks and returns (Boardman et al., 2018).

- Accountability and Justification CBA provides a defensible framework for stakeholders and funders to understand the rationale behind project choices (Hockley, 2014).

### CBA - “Loyal by Taste – A Culinary Celebration of Connection”

- Duration: One-day immersive dining experience

- Audience: 100 guests (loyalty members + prospects)

- Objectives: Strengthen emotional loyalty, collect CRM data, and showcase culinary excellence

Estimated Costs:

| Cost Category | Details | Estimated Cost (GBP) |
| --- | --- | --- |
| Venue & Ambience | Elegant setup, lighting, music, themed décor | £1,000–£1,500 |
| Staffing | Chef showcase, service staff, host training | £1,200–£1,800 |
| Marketing | Email campaigns, social media, influencer outreach | £600–£900 |
| Ingredients | Premium tasting menu (£20 per guest) | £2,000 |
| CRM Integration | Data capture tools, feedback forms, loyalty app sync | £400–£600 |
| Miscellaneous | Licenses, insurance, clean-up, contingency | £300–£500 |
| 🔹 Total Estimated Cost |  | £5,500–£7,300 |

Projected Benefits:

| Benefit | Details | Estimated Value (GBP) |
| --- | --- | --- |
| Ticket Revenue | £35 per guest × 100 guests | £3,500 |
| Upselling | Wine pairings, merchandise (£10 per guest avg.) | £1,000 |
| Repeat Visits | 25% return rate × £30 avg. spend | £750 |
| CRM Data Acquisition | 90+ enriched profiles for future campaigns | Strategic long-term value |
| Brand Equity | Social media buzz, influencer content, press mentions | Intangible but strategic |
| 🔹 Total Estimated Benefit |  | £5,250–£6,500+ |

Net Benefit = Total Benefits − Total Costs ROI (%) = (Net Benefit / Total Costs) × 100 (Harvard Business School, 2025)

Costs: £6,000

Benefits: £6,500

Net Benefit: £500

ROI: (500 / 6,000) × 100 = 8.3%

This ROI is strategically valuable due to enhanced emotional loyalty and brand connection, rich CRM data for segmentation and personalisation, £500 made for the company proving success and becoming the foundation for future loyalty campaigns.

# Project Organisation/Work Breakdown Structure

The Work Breakdown Structure (WBS) was first formally introduced by the United States Department of Defence, (1962) as part of its aerospace project management practices. It was later adopted and standardised by the Project Management Institute (2017). The WBS breaks down a project into more manageable, smaller parts in a hierarchical manner. Its purpose is to organise work into clear deliverables and tasks, improves planning by identifying all required activities, supports scheduling, budgeting and clarifies responsibilities.

A Work Breakdown Structure designed for the event is shown below, dividing tasks into clear sections:

### Critical Path Analysis

Critical Path Analysis was created by (Kelley & Walker, 1959). It is a project scheduling method used to identify the longest sequence of dependent tasks that determines the shortest time to complete a project. It helps project managers prioritise tasks that cannot be delayed, allocates resources efficiently, tracks progress and adjusts timelines.

Planning → Marketing → Event Execution → Post-Event Review (Alternate paths include Culinary Prep and Guest Setup feeding into Event Execution)

### Task Durations and Dependencies

| Task | Duration | Dependencies |
| --- | --- | --- |
| Planning | 5 days | — |
| Marketing | 3 days | Planning |
| Culinary Preparation | 4 days | Planning |
| Guest Experience Setup | 2 days | Planning |
| Event Execution | 1 day | Marketing, Culinary Prep, Guest Setup |
| Post-Event Review | 2 days | Event Execution |

### Implementing Kanban Method

“Kanban” means “signboard” or “billboard” in Japanese, symbolising visual cues for workflow. Kanban is a visual workflow management method developed by Ohno (1940) at Toyota to improve manufacturing efficiency. It uses cards and boards to visualise tasks, limit work in progress and to optimise flow. In project management, Kanban helps teams track progress, prioritise tasks and reduce bottlenecks, by organising work into columns like To Do, In Progress, and Done.

Kanban Board for “Loyal by Taste” Event in clear sections:

| To Do | In Progress | Done |
| --- | --- | --- |
| Finalise event concept | Marketing campaign | Planning complete |
| Confirm chef lineup | Culinary prep | Guest list finalised |
| Design loyalty experience | Guest experience setup | Venue booked |
| Prepare post-event survey |  |  |

Tasks can move across columns as they progress. This keeps the team aligned and responsive.

# Team Roles/Responsibilities

The RACI Matrix introduced by Sheehan, (1950) is a tool used in project management to define roles and responsibilities across tasks. RACI stands for:

R – Responsible: Who does the work

A – Accountable: Who owns the outcome

C – Consulted: Who gives input

I – Informed: Who needs updates

It was popularised by Ernst & Young, (1970) as a way to improve clarity in decision-making and task ownership (Responsible, Accountable, Consulted, Informed)

Below is a visual representation of the RACI Matrix applied to the event:

Using the RACI Matrix the event now has defined clear roles for team members across marketing, culinary, logistics, and CRM. Confusion is avoided by showing who is responsible for each task and who needs to be consulted. The matrix streamlines communication, so updates and decisions reach the right people and improves efficiency by preventing overlap and missed responsibilities. This approach is especially useful for hospitality events, where multiple departments must work together under tight timelines and high customer expectations (Eventbrite, 2024). This matrix helped the project team stay organised, reduced miscommunication and ensured that every part of the event, from menu planning to guest engagement, was executed smoothly and with accountability.

# Control & Monitoring Framework: Time, Budget, Quality and Scope

Effective control and monitoring ensure the event stays on track, within budget and delivers high-quality experiences.

### Time

The Gantt chart was developed by Gantt (1910), introducing a visual scheduling tool to improve production efficiency and project planning. A Gantt chart is a bar chart that illustrates a project schedule. It shows: Tasks or activities on the vertical axis

Time intervals on the horizontal axis

Start and end dates of tasks

Task dependencies and progress tracking

It’s widely used in project management to plan, monitor and control project timelines and resource allocation (Geraldi, 2012). To monitor and control the timing of the event, a Gantt chart has been created to plan pre-event tasks and a run sheet for the event day. Monitoring progress in real time will be done using checklists and team updates. A visual representation of the Gantt chart depicts each task with its start and end dates, showing how they overlap or depend on each other. This chart helps monitor progress, allocate resources and to adjust timelines if needed.

### Budget

Budget control is the methodical process of controlling project expenses to guarantee that funds are spent effectively, and the project stays within the allocated budget. It contains:

Estimating costs and allocating them to various job bundles

Monitoring actual spending against budgeted amounts

Identifying excessive or insufficient spending

Corrective actions to realign financial results

Providing stakeholders with reports to ensure accountability and transparency

This procedure is crucial for upholding financial restraint and ensuring that strategic goals are fulfilled without compromising scope or quality (Fleming & Koppelman, 2016).

For the “Loyal by Taste” launch event, budget control can be applied across key cost categories:

| Cost Category | Control Technique |
| --- | --- |
| Venue & Setup | Compare actual rental and decorating costs to planned values |
| Culinary & Staffing | Track catering invoices and labour hours against forecasts |
| Marketing & Promotion | Monitor ads spend, printing and digital campaign costs |
| CRM & Technology | Log software subscriptions and hardware rentals |
| Contingency Reserve | Allocate 10–15% buffer for unforeseen expenses |

Use tools such as Gantt charts, cost tracking spreadsheets, or project management software to visualise budget adherence and flag irregularities early.

### Quality

Using Garvin’s 8 Dimensions of Quality: evaluate performance, aesthetics, reliability, and guest satisfaction, will keep track of quality control as well as using feedback forms and live observations to assess service quality.

### Scope

Use WBS to define deliverables such as loyalty program setup, CRM integration, culinary showcase, guest experience design and post-event feedback. Track completion and conduct milestone reviews with stakeholders to confirm alignment (Turner, 2016). Scope is reviewed through the Work Breakdown Structure (WBS) and validated via stakeholder feedback to prevent scope creep and ensure expectations are met.

# Change Management Process

When managing an event, it is important to be prepared and to go through the proper channels to execute the change correctly and effectively.

### Log the change Request

The operations team submits a request to add QR code-based feedback surveys at each table to collect real-time guest impressions during the event. This supports continuous quality improvement and guest engagement. Change requests should be formally documented and evaluated to maintain control over scope and quality and ensures alignment with project goals (Meredith et al., 2021).

### Authorisation

The event manager and CRM coordinator review the request. It is approved due to its strategic alignment and low implementation risk. Authorisation is a critical control point to prevent scope creep and maintain project integrity (Turner, 2020).

### Change to Project Plan

Update guest flow to include survey prompts. Allocate staff to monitor responses and escalate urgent feedback. Approved changes must be reflected in the project starting point and communicated to all stakeholders. Integrating approved changes into the project starting point ensures transparency and accountability (Schwalbe, 2022).

### Risk Management Risk

Low participation or technical issues with QR codes. Mitigation: Staff reminders, visible signage and pre-event testing. Risk analysis is essential to anticipate and mitigate negative impacts of changes (Hillson & Simon, 2020).

### Implement the Change

QR codes are placed on tables and menus. Guests are encouraged to submit feedback during the event. Responses are monitored live and used to adjust service delivery in real time. Implementation should be tracked and evaluated to ensure the change achieves its intended benefits (Kerzner, 2022).

# Close

At the close of the “Loyal by Taste” event project, formal sign-off and hand-off procedures are essential, to confirm that all deliverables have been accepted by stakeholders and that operational responsibilities are transitioned appropriately. Any outstanding changes, or unresolved issues, should be documented and agreed upon to ensure transparency and closure. A structured evaluation of the project’s performance, comparing planned outcomes to actual results, supports accountability and continuous improvement. Capturing lessons learned through team debriefs and stakeholder feedback helps refine future event planning and strengthens organisational knowledge (Wysoki, 2019).

Event got signed off by Event Project Manager with acceptance of all stakeholders.in conclusion of the event project, all agreed changes, such as revised guest flow and adjusted vendor timelines, were documented alongside minor unresolved issues, including delayed feedback from external partners. A structured evaluation was conducted, comparing planned objectives with actual outcomes in areas like customer engagement and operational efficiency. Key lessons learnt included the importance of early stakeholder alignment and contingency planning for last-minute adjustments, which will inform future event strategies and improve project execution.

# Project Manager Skills, Self-Assessment and PDP

| Skill Area | Self-Assessment |
| --- | --- |
| Leadership | I organise people well and give clear roles. I want to improve how I motivate my team. |
| Communication | I write clearly and share updates well, but I need to speak more confidently in meetings. |
| Time Management | I plan tasks well using charts and boards, though I sometimes take on too much at once. |
| Problem-Solving | I use tools and logic to fix issues. I want to respond faster when problems come up. |
| Adaptability | I adjust plans when needed, but I hesitate with last-minute changes. |
| Conflict Resolution | I stay calm and fair in disagreements. I need to be more assertive when needed. |
| Decision-Making | I make careful choices using data. I sometimes wait too long to decide. |
| Emotional Intelligence | I understand how people feel and support them. I’m learning to manage my own stress better. |
| Risk Management | I’m good at spotting risks and planning for them, but I want to be more proactive. |
| Strategic Thinking | I link my projects to business goals well, and I’m working on seeing the bigger picture more clearly. |

| Skills to Improve | What I Will Do | When I Will Do It | How I Will Know I Improved |
| --- | --- | --- | --- |
| Leadership | Join a leadership workshop and ask for feedback from my team | Within 3 months | Team feels more motivated and gives positive feedback |
| Speaking in Meetings | Practice speaking with confidence and join a speaking group like Toastmasters | Over the next 2 months | I feel more confident and get good feedback from others |
| Making Faster Decisions | Use decision tools and set time limits for choices | Starting now | I make quicker decisions and avoid delays |
| Handling Conflict | Learn simple negotiation skills and practice with role-play | Within 1 month | I solve problems faster and reduce tension in the team |
| Thinking Strategically | Read articles about hospitality trends and apply ideas to my projects | Over the next 6 months | My plans match business goals and get stakeholder support |

# References

Ashikuzzaman, M. (2024). What is cost benefit analysis? Definition, steps, and examples. Library & Information Science Education Network. Retrieved from https://www.lisedunetwork.com/what-is-cost-benefit-analysis/

Atkinson, R. (1999). Project management: cost, time and quality, two best guesses and a phenomenon. International Journal of Project Management, 17(6), 337–342.

Barnes, M. (1969). Time and cost in contract control [PhD thesis]. University of Manchester Institute of Science and Technology

Boardman, A. E., Greenberg, D. H., Vining, A. R., & Weimer, D. L. (2018). Cost–benefit analysis: Concepts and practice (5th ed.). Cambridge University Press.

Bourne, L. (2016). Stakeholder relationship management: A maturity model for organisational implementation (2nd ed.). Routledge.

Ernst & Young (1970). Understanding responsibility assignment matrix (RACI matrix). [online] Project Management. Available at: https://project-management.com/understanding-responsibility-assignment-matrix-raci-matrix/.

Eventbrite. (2024). How to use the RACI matrix for event management. https://www.eventbrite.com/blog/academy/free-event-planning-template/

Fleming, Q. W., & Koppelman, J. M. (2016). Earned value project management (4th ed.). Project Management Institute.

Forsberg, K., Mooz, H., & Cotterman, H. (2005). Visualising project management (3rd ed.). Wiley.

Gantt, H. L. (1910). Work, wages, and profits: Their influence on the cost of living. The Engineering Magazine Company

Garvin, D. A. (1987). Competing on the eight dimensions of quality. Harvard Business Review, 65(6), 101–109.

Geraldi, J., & Lechter, T. (2012). Gantt charts revisited: A critical analysis of its roots and implications to the management of projects today. International Journal of Managing Projects in Business, 5(4), 578–594

Harvard Business School. (2025). What is cost-benefit analysis? https://online.hbs.edu/blog/post/cost-benefit-analysis

Highsmith, J. (2002). Agile software development ecosystems. Addison-Wesley.

Hillson, D., & Simon, P. (2020). Practical project risk management: The ATOM methodology (3rd ed.). Berrett-Koehler Publishers.

Hockley, N. (2014). Cost–benefit analysis: A decision-support tool or a venue for contesting ecosystem knowledge? Environment and Planning C: Government and Policy, 32(2), 283–300. https://doi.org/10.1068/c1384j

Kelley, J. E., & Walker, M. R. (1959). Critical-path planning and scheduling. Proceedings of the Eastern Joint Computer Conference, 160–173.

Kerzner, H. (2017). Project management: A systems approach to planning, scheduling, and controlling (12th ed.). Wiley.

Kotler, P., Bowen, J. T., & Makens, J. C. (2017). Marketing for hospitality and tourism (7th ed.). Pearson.

Lock, D. (2020). Project management (11th ed.). Routledge.

Mendelow, A. L. (1991). Environmental scanning: The impact of the stakeholder concept. In Proceedings of the International Conference on Information Systems (ICIS), 407–417

Meredith, J. R., Shafer, S. M., & Mantel, S. J. (2021). Project management: A managerial approach (10th ed.). Wiley.

Pine, B. J., & Gilmore, J. H. (1999). The experience economy: Work is theatre & every business a stage. Harvard Business Press.

Project Management Institute. (2017). A Guide to the Project Management Body of Knowledge  (6th ed.).

Pyzdek, T., & Keller, P. A. (2018). The Six Sigma handbook (5th ed.).

Reichheld, F. F., & Sasser, W. E. (1990). Zero defections: Quality comes to services.

Sheehan, E.F. (1950). Understanding responsibility assignment matrix (RACI matrix). [online] Project Management. Available at: https://project-management.com/understanding-responsibility-assignment-matrix-raci-matrix/.

Schwalbe, K. (2022). Information technology project management (9th ed.). Cengage Learning.

Turner, J. R. (2020). Handbook of project-based management: Leading strategic change in organizations (4th ed.). McGraw-Hill Education

Ohno, T. (1988). Toyota production system: Beyond large-scale production. Productivity Press.

United States Department of Defence. (1962).  Annual Report of the Secretary of Defence

Wysocki, R. K. (2019). Effective project management: Traditional, agile, extreme (8th ed.). Wiley.

Yates, B. T. (1985). Cost-effectiveness analysis and cost-benefit analysis: An introduction. Behavioural Assessment, 7(3), 207–234.