Event Plan Report

1. Event Overview

Event Name: The Sovereign Masquerade

Event Type: Charity Ball

Concept & Theme: The event has a black and gold theme, with attendees required to attend wearing masks.

Target Audience: Students and young people

2. Timing, Location & Programme

Date & Time: 25th March 2026 – 7pm-11pm

Venue: Dylan Thomas Centre, 6 Somerset Pl, Swansea SA1 1RR ·

Event Programme:

Doors open/Guest arrival – 7pm

Roaming Canapes – 7.15pm-8.30pm

Live singer (first act) - 7.30pm-8.15pm

Welcome speech and thank you – 8.15pm-8.30pm

Raffle draw and awards – 8.30pm-9pm

Live Singer (second act) - 9pm-9.45pm

Last orders – 10.45pm

Guest departure and set down – 11pm

Afterparty: Peppermint, Wind St. - 11pm-late

3. Aim and Objectives

Overall Aim: To organise a memorable and entertaining masquerade party in order to raise a substantial amount of money and awareness for cancer research.

Objectives:

Objective 1: To raise at least £300 during the event through donations, ticket sales, and fundraising initiatives.

Objective 2: To enhance awareness and fundraising possibilities by drawing at least 30 people to attend the event.

Objective 3: Throughout the event, information, speeches, and promotional materials will be shared to raise awareness of cancer research.

4. Project Planning Techniques (Including EMBOK Framework)

Work Breakdown Structure (WBS):

I managed both the finances and the decorations for my event, so I had to be both creative and well-organised. As the financial manager, it was my job to prepare and oversee the budget, ensuring that we didn't overspend while still producing a quality event. I made sure that all expenditures were both necessary and within our budget by keeping track of all the money received from ticket sales and any fundraising. I also searched for methods to save costs, like locating less expensive suppliers. As the manager of decorations, I paid close attention to the event's appearance and atmosphere, particularly ensuring that it complemented the masquerade theme.

I helped set everything up at the location, organised the decorations, and selected the colours and patterns. I ensured that the space had a pleasing appearance and the ideal ambiance for visitors. It was difficult to juggle both responsibilities because I had to make sure the decorations looked nice without going over budget, but doing so improved my time management, teamwork, and decision-making abilities and helped the event succeed overall.

Gantt Chart:

Running Order:

| Time | Timetabled event sector |
| --- | --- |
| 7pm | Doors Open & guest arrival – guests arrive, tickets scanned, welcome drink provided by volunteers (bucks fizz will |
| 7.15pm-8.30pm | Roaming canapes – served throughout the room (this format is a stop start service) |
| 7.30pm-8:15pm | Live singer (first act) |
| 8.15pm-8.30pm | Welcome speech and thank you |
| 8.30pm-9pm | Raffle draw and awards |
| 9pm-9.45pm | Live singer (second act) |
| 10.45pm | Last call on bar service |
| 11pm | Guest’s departure |
| 11pm-late | Afterparty – Peppermint, Wind St. |