## Slide 1
Start recruitment 2/11/20
End recruitment (18/12/20
Arrange interview dates with agents
Conduct weekly interviews (4 weeks)
Communicate results with registry and students
Publicise recruitment with current students ( re introduce Amazon voucher scheme)
Arrange interviews for referred students (over 5 weeks)
Inform registry and successful participants
1 week
4 weeks
1 week
1 week
5 week
1 week
Self referrals
Hold interviews
Communicate through registry

## Slide 2: Risk Analysis
Product
- Participants not engaging
Not getting enough responses back
Covid : stops project activity physically (open days/ physical meetings)
Not getting true feelings and engagement from participants due to physical constraint
People not wanting to join an organisation where they are put in the front line and at risk
Lack of engagement from the police with the community
Reputation of police through social media
Resource
Technology (Internet)
Team members
Schedule
Responses not getting back in time
Availability of police to engage
Identify :
Priority H M L
Likelihood H M L
Risk
Actions to mitigate
PESTLE / SWOT