## NRM 1 Layout
NRM 1: Order of Cost Estimating and Cost Planning for Capital Building Works
2.4 Constituents of an Order of Cost Estimate
2.1 The Key Constituents of an order of cost estimate are as follows.
Constituent
Facilitating works estimate (1) | 15178
Building works estimate (2) | 2470710.5
Main contractor's preliminaries estimate (3) | 175323
Sub-total (4) [(4) = (1) + (2) + (3)] | 2661211.5
Main contractor's overheads and profit estimate (5) | 0
Works cost estimate (6) [(4) + (5)] | 2661211.5
Project/design team fees estimate (7) | 10000
Sub-total (8) [(8) = (6) + (7)] | 2671211.5
Other developments/project costs estimate (9) | 56521
Base cost estimate (10) [(10) = (8) + (9)] | 2727732.5
Risk allowances estimate (11) [(11) = (11(a)) + (11(b)) + (11(c)) + (11(d))] | 0
(a) Design development risks estimate (11(a)) | 0
(b) Construction risks estimate (11(b)) | 0
(C) Employer change risks estimate (11(c)) | 0
(D) Employer other risks estimate (11(d)) | 0
Cost limit (excluding inflation) (12) [(12) = (10) + (11)] | 2727732.5
Tender inflation estimate (13) | 3399490.4
Cost limit (excluding construction inflation) (14) [(14) = (12) + (11)] | 2727732.5
Construction inflation estimate (15) | 3915643.39
Cost limit (including inflation) (16) [(16) = (14) + (15)] | 6643375.89
Vat assessment at Standard Rate (17.5%) | 1162590.7807

## Elemental Sheet
BCIS Online -
Building function: | 713.8 - Secondary Schools - mixed facilities
Type of work: | New build
Gross floor area: | 688 m2
Job title: | Teaching Block, Beauchamps High School
Location: | Wickford, Essex | (Orignal Prices based on this location)
District: | Basildon
Grid reference: | TQ7693
Postcode: | SS11 8LY
Dates: | Receipt: | 2023-11-14 | (Original Prices based on this date)
| Base: | 2023-11-14
Project details: | 2 storey 1Nr form entry secondary school teaching block together with external works comprising site preparation, paving, fencing, gates, drainage, services and lighting. Demolition.
Site conditions: | Level operational infill school site with restricted working space and site access.
Client: | Essex County Council
Tender documentation: | Activity schedule
Contract: | NEC4 priced contract 2017 (option A or B)
Cost fluctuations: | Fixed
Basis of cost: | Contract
Contract breakdown
Measured work:
Provisional sums: | 0
Prime cost sums: | 0
Preliminaries: | 175323
Contractor design fees:
Contract sum:
Accommodation and design features: | 2 storey 1FE secondary school teaching block providing 150Nr pupil places comprising, 2Nr music rooms, music resource store, nurture room, office, plant room, lobby and WCs to ground floor; and 2Nr general science laboratories, chemical store, science prep room, general classroom, group room, office, WCs and link corridor to existing school to first floor. Concrete strip foundations. Steel frame. Facing brick and insulated rendered external walls. Aluminium double glazed windows and doors. Wall, floor and ceiling finishes. Fittings and furnishings. Sanitaryware. Air source heat pumps. Power and light including PV. BMS, data, public address, TV, CCTV, fire, intruder and panic alarms.
Basement: | 0 | m2
Ground floor: | 326.5 | m2
First floor: | 361.5 | m2
Gross floor area: | 688 | m2 | 688m2 gross floor area (I've measured ASSUMPTION)
Functional unit: | 150 | No places
Storeys as % of gross floor area: | 2 storey | 100%
Elements | [6 empty] | Example on Teams - Interim Valuation (%) |  | Interim Valuations Calculations (£)
Element | Total cost (£) | Cost per m² (£) | Element unit quantity | Element unit rate | Percentage (%) |  | 5th Month(Previous Month) (%) | 6th Month (Current Month)(%) | 5th Month (Previous Month) (£) | 6th Month (Current Month) (£) | Difference between 5th and 6th Month (£)
01 Substructure | 66932.5 | 205 | 326.5 |  |  |  | 100 | 100 | 66932.5 | 66932.5 | 0
02.01 Frame | 383822 | 548 |  |  | 10 | % | 80 | 85 | 307057.6 | 326248.7 | 19191.1
02.02 Upper Floors | 83581 | 119 |  |  | 2 | % | 45 | 52 | 37611.45 | 43462.12 | 5850.67
02.03 Roof | 155948 | 223 |  |  | 4 | % | 0 | 0 | 0 | 0 | 0
02.04 Stairs | 14389 | 21
02.05 External Walls | 295298 | 422 |  |  | 8 | % | 0 | 0 | 0 | 0 | 0
02.06 External Windows and Doors | 78238 | 112 |  |  | 2 | % | 0 | 0 | 0 | 0 | 0
02.07 Internal Walls and Partitions | 124055 | 177 |  |  | 3 | % | 0 | 0 | 0 | 0 | 0
02.08 Internal Doors | 10920 | 420 | 26
02 Superstructure | 1146251 | 2042
03.01 Wall Finishes | 28943 | 41 |  |  | 1 | %
03.02 Floor Finishes | 14448 | 21 | 688
03.03 Ceiling Finishes | 87935 | 126 |  |  | 2 | %
03 Finishes | 131326 | 188 |  |  |  |  | 0 | 0 | 0 | 0 | 0
04 Fittings, Furnishings and Equipment | 90458 | 129 |  |  | 2 | %
05.01 Sanitary Installations | 11353 | 16
05.02 Services Equipment | 0 | 0 | 0
05.03 Disposal Installations | 28883 | 41 |  |  | 1 | %
05.04 Water Installations | 100617 | 144 |  |  | 3 | %
05.05 Heat Source (Costs included elsewhere) | 0 | 0
05.06 Space Heating and Air Conditioning (Costs include other elements) | 200458 | 286 |  |  | 5 | %
05.07 Ventilating Systems | 168173 | 240 |  |  | 4 | %
05.08 Electrical Installations | 196734 | 281 |  |  | 5 | %
05.09 Fuel Installations | 21474 | 31 |  |  | 1 | %
05.10 Lift and Conveyor Installations | 30190 | 43 |  |  | 1 | %
05.11 Fire and Lightning Protection | 2950 | 4
05.12 Communications and Security Installations | 158882 | 227 |  |  | 4 | %
05.13 Special Installations | 52961 | 76 |  |  | 1 | %
05.14 Builder's Work in Connection with Services (BWIC) | 63068 | 90 |  |  | 2 | %
05 Services | 1035743 | 1479 |  |  |  |  | 0 | 0 | 0 | 0 | 0
06 Prefabricated Buildings and Building Units | 0 | 0
07 Work to Existing Building | 0 | 0
Building Sub-total | 2470710.5 |  |  |  | 61 | %
08.01 Site Preparation Works | 58453 | 84 |  |  | 3 | % | 100 | 100 | 58453 | 58453 | 0
08.02 Roads, Paths, Pavings and Surfacings | 40131 | 57 |  |  | 2 | % | 12 | 15 | 4815.72 | 6019.65 | 1203.93
08.03 Soft Landscaping, Planting and Irrigation Systems | 0 | 0
08.04 Fencing, Railings and Walls | 8874 | 13 |  |  |  |  | 0 | 0 | 0 | 0 | 0
08.05 External Fixtures | 0 | 0
08.06 External Drainage | 108328 | 155 |  |  | 4 | % | 0 | 0 | 0 | 0 | 0
08.07 External Services (Costs include other elements) | 180233 | 257 |  |  | 8 | % | 0 | 0 | 0 | 0 | 0
08.08 Minor Building Works and Ancillary Buildings | 159207 | 227 |  |  | 6 | % | 0 | 0 | 0 | 0 | 0
08 External Works | 555226 | 793 |  |  | 23 | %
00.01 Toxic/Hazardous/Contaminated Material Treatment | 0 | 0
00.02 Major Demolition Works | 15178 | 22 |  |  |  |  | 100 | 100 | 15178 | 15178 | 0
00.03 Temporary Support to Adjacent Structures | 0 | 0
00.04 Specialist Groundworks | 0 | 0
00.05 Temporary Diversion Works (Costs included elsewhere) | 0 | 0
00.06 Extraordinary Site Investigation | 0 | 0
00 Facilitating Works | 15178 | 22 |  |  |  |  | 100 | 100 | 15178 | 15178 | 0
09 Preliminaries | 175323 | 250 |  |  | 10 | %
10 Main Contractor's Overheads and Profit | 0 | 0
Total (less Design Fees) | 3216437.5 | 5100 |  |  | 94 | %
11 Project/Design Team Fees | 10000 | 0 |  |  | 5 | %
12 Other Development/Project Costs | 56521 | 81 |  |  | 1 | %
13 Risk (Clients Contingencies) | 0
Total Contract sum | 3282958.5 |  |  |  | 100 | %
[9 empty] | 349484.77 | 375730.47 | 26245.7
Credits:
Submitted by | Essex County Council
Client | Essex County Council
Architect | Concertus
General Contractor | Barnes Construction

## Payment Certificate
Interim Payment
Contract: | 07796 835604
Employer: | Mr. John George
Address: | tostconstruction@outlook.com
Contractor: | Mr. Sam Williams
Address: | 43, Elkingkton Road, Swansea
Payment Nr: | 110 |  |  |  | Period Ending : | 2025-07-05
Assessment Date: | 2024-11-10 |  |  |  | Date of Issue: | 2024-10-02
Our assessment of the above Contract indicates that the following payment is due from the Employer to
the Contractor.
1 | General Items |  |  |  | £ | 0
2 | Work |  |  |  | £ | 375730.47
3 | Disallowed Costs |  |  |  | £ | 0
[5 empty] | £ | 375730.47
4 | Management Fee @ 0% |  |  |  | £ | 0
5 | Gross Valuation |  |  |  | £ | 375730.47
6 | Less Retention @ 0% |  |  |  | £ | 0
375730.47
8 | Net Valuation |  |  |  | £ | 375730.47
9 | Less Previously Certified |  |  |  | £ | 349484.77
10 | Balance Due - |  |  |  | £ | 26245.7
|  | Payment To Be Received By: | Andrew Hughes
11 | Value Added Tax
£ | 26245.7 | at Standard Rate (17.5%) |  |  | 4592.9975
£ | 0 | at Zero Rate |  |  | 0
|  |  |  | Total VAT Payable £ | 4592.9975
| Signed by Project Manager: | Ioan Phillip |  | Date: | 2025-10-02

## Summary Sheet
Adjusting Rates for the Project in February 2025
Proposed 2 Storey 1FE Secondary School Teaching Block
Total Contract Sum Prior to Adjustment: |  |  | 3282958.5
Budget Calculation
Example from the Elemental Sheet |  |  |  | Proposed Project in February 2025
Location: | Essex |  |  | Location: | Swansea
Date | 14th Novemeber 2023 |  |  | Date: | 1st February 2025
Tender Price Index: | 388 | (provisional) |  | Tender Price Index: | 403 | (forecasted)
Location Factor: | 191 | (assumed) |  | Location Factor: | 220 | (assumed)
Pricing Adjustments (£)
Tender Price Index Adjustment: | 3409876.9987
Location Factor Adjustment: | 3927607.0142
Indicative Total Construction Works Cost: | 3927607.0142
Summary Sheet
Element Ref | Element | Cost Summary (Prior to Indicies Adjustment) | Cost Summary (Updated for Inflation) | Cost Sumarry (Updated for Location and Inflation)
0 | Facilitating Works | 15178 | 15764.7784 | 18158.3834
1 | Subcstructure | 66932.5 | 69520.0966 | 80075.504
2 | Superstructure | 1146251 | 1190564.8273 | 1371331.2147
3 | Finishes | 131326 | 136403.0361 | 157113.4447
4 | Fittings, Furnishings and Equipment | 90458 | 93955.0876 | 108220.5198
5 | Services | 1035743 | 1075784.6108 | 1239123.6355
6 | Prefabricated Buildings and Building Units | 0 | 0 | 0
7 | Work to Existing Building | 0 | 0 | 0
8 | External Works | 555226 | 576690.9227 | 664251.3246
9 | Preliminaries | 175323 | 182100.951 | 209749.7865
10 | Main Contractor's Overheads and Profit | 0 | 0 | 0
11 | Project/Design Team Fees | 10000 | 10386.5979 | 11963.6207
12 | Other Development/Project Costs | 56521 | 58706.0902 | 67619.5803
13 | Risk (Client Contigencies) | 0 | 0 | 0
Total: |  | 3282958.5 | 3409876.9987 | 3927607.0142
Personal Note: Adjusting for inflation and market conditions first, then refining for location cost differences.

## Query Sheet and General Info.
Queuery Sheet (Addressed through in class discussions)
Name: Toby George
Lecturer: Dr. Deborah Hughes
Project: Two Storey School
Student Email: 2204590@student.uwtsd.ac.uk
Query Number | Query | Response
1 | Can I confirm that the Retention and Management Fee is set at 0%? | Yes, Retention and Management can be assumed as 0%.
2 | Can I confirm with you whether the 688m2 GIFA is acceptable? | Yes, 688m2 GIFA can be assumed.
3 | Are there any additional allowances or fees required for the budget? | No, but can add risk, fees and OH/P if wanted.
4 | Can I confirm the Interim Valuation value is acceptable? | Yes, the value seems reasonable.
5 | Can I keep the highlighted elements on the Elemental sheet | Yes please.
to emphasise which costs have been requested?
6 | Are you satisified with the selected specifications for substructure, | Yes, these specifications can be used.
internal doors and flooring?
7 | Would you like me to include a price for Services Equipment? | No, keep it at £0.
8 | Can I confirm the Swansea LF is 220 and Essex LF is 119. | Yes, this can be used.
General Information
Elements are based on NRM:1 Rules of Measurement for Elemental Method of Estimating.
All rates are based on Spon's Architects and Builder's Price Book 2020.
The indicies have been adjusted for the Proposed Project in February 2025., following clarification on the indices provided.
Cubilce doors are not included as internal door.
Double doors have been counted as a single door.
Doors in the coriddor and the single doorway leading to the store room have been included in the budget.
Due to certain elements being estimated rather than precisely defined, all costs are based on higher end rates.
A simple reinforced concrete raft foundation is used for development, up to two storey high.
Standard internal doors with a single leaf and saple veneered finish are used.
Floor finish; Sheet/board flooring, chipboard 18mm to 22mm thick cardboard flooring t&g joints is used.

## Elemental Calculations
NRM 1 Procedures |  | Calculations |  | Spons Rates
1.1.1 Substructure
1.1.1 Substructure
| 326.5 | m2 | <--GF (m2)
| 205 | £/m2 | <--Spons Rate (£/m2)
| 66932.5 | £ | <--GF x Spons Rate
02.08 Internal Doors
02.08 Internal Doors
| 26 | nr | <--Internal Doors (nr)
| 420 | £/nr | <--Spons Rate (£/m2)
| 10920 | £ | <--Internal Doors x Spons Rate
3.02 Floor Finishes | 03.02 Floor FInishes
| 688 | m2 | <-- Floor Finishes (m2)
| 21 | £/m2 | <--Spons Rate (£/m2)
| 14448 | £ | <-- Floor Finishes x Spons Rate
05.02 Services Equipment
05.02 Services Equipment
| 0 | nr | <--Services Equipment (nr)
| 0 | £/nr | <--Spons Rate (£/nr)
| 0 | £ | <-- Services Equipment x Spons Rate
Clarified with lecturer, Services Equipment as £0 for Elemental Sheet

## BoQ
Bill of Quantity (BoQ)
| Code | Item No. | Description | Quantity | Unit | Unit Rate (£) | Total (£)
| 1.1.1 | A | Raft foundations, simple reinforced concrete raft on | 326.5 | m^2 | 205 | 66932.5
poorer ground for development up to two storey high
| 2.08 | B | Standard doors, cellular core; softwood; softwood | 26 | nr | 420 | 10920
architrave; aluminium ironmongery (latch only),
single leaf; Sapele veneered finish
| 3.02 | C | Sheet/board flooring, chipboard, 18mm to 22m thick | 688 | m^2 | 21 | 14448
chipboard flooring; t&g joints
|  |  |  | Total carried forward to main summary (£) |  |  | 92300.5
Note: Please refer to the Calculations for reference.

## Cashflow Exercise
Summary = Value of work + profit (%) - (%) retention
Value add 8% then ddt 5%
[13 empty] | S1: | 28.0522 | (Nett Rate) |  |  | S1: | 26.8833 | (Nett Rate)
84.99
[13 empty] | S2: | Labour | 39.444 | % | say 40% | S2: | Labour | 84.9866 | % | Say 84.99 | 12.33
[14 empty] | Material | 60.556 | % | say 60% |  | Material | 12.3324 | % | Say 12.33 | 2.68 | 100
[19 empty] | Plant | 2.681 | % | Say 2.68
[13 empty] | S2.2: | Labour | 11.22 | £
[14 empty] | Material | 16.83 | £ |  | S2.2: | Labour | 22.8481 | £
[19 empty] | Material | 3.3147 | £
[13 empty] | S3: | Labour | 15.708 | £ |  |  | Plant | 0.72047 | £
[14 empty] | Material | 23.562 | £ |  |  |  | 26.8833 | £
[15 empty] | 39.27 | £ | [6 empty] | S1: Ddt OH/P % from material
[18 empty] | S3: | Labour | 30.0633 | £ | S3 might be wrong | S2: Spons % breakdown
|  |  | This is better but can do (-) for cash out | [9 empty] | S4: | 45.1605 | (Gross Rate) |  |  |  | Material | 4.3615 | £ |  | S2.2: % breakdown to Nett Rate
[19 empty] | Plant | 0.94799 | £ |  | S3: Difference in material volume
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | [7 empty] | 35.3728 | £ |  | S4: Add OH/P % from material
Cost | 20000 | 50000 | 100000 | 130000 | 150000 | 180000 | 140000 | 130000 | 120000 | 100000 | 50000 | 30000
Profit | 0 | 21600 | 54000 | 108000 | 140400 | 162000 | 194400 | 151200 | 140400 | 129600 | 108000 | 54000 | [5 empty] | S4: | 42.4474 | (Gross Rate)
Retention | 0 | 20736 | 51840 | 103680 | 134784 | 155520 | 186624 | 145152 | 134784 | 124416 | 103680 | 51840
Cash in | 0 | 20736 | 51840 | 103680 | 134784 | 155520 | 186624 | 145152 | 134784 | 124416 | 103680 | 51840
Cash out | 0 | 50000 | 100000 | 130000 | 150000 | 180000 | 140000 | 130000 | 120000 | 100000 | 50000 | 30000
Cash flow | -20000 | -49264 | -97424 | -123744 | -138960 | -163440 | -116816 | -101664 | -86880 | -62464 | -8784 | 13056
No cost or retention for the first month, as just cash coming out of the bank. Cash flow would be -cost (1st month)
Cost = to pay (leaving bank account at the end of the month)
Profit = Profit on last months cost (add)
Retention = ddt on the profit
Cash in = Total from the cost, profit and retention
Cash out = From the current month
Cash flow = Previous cash flow + cash in - cash out
Total Project Cost - is a negative value
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project 1 | 10000 | 30000 | 50000 | 50000 | 50000 | 10000 | 5000
Project 2 | 5000 | 20000 | 60000 | 80000 | 80000 | 60000 | 20000 | 10000
Project 3 | 20000 | 40000 | 70000 | 20000 | 10000
Total Project Cost | 35000 | 90000 | 180000 | 150000 | 140000 | 70000 | 25000 | 10000
Profit | 0 | 37800 | 97200 | 194400 | 162000 | 151200 | 75600 | 27000
Retention | 0 | 35910 | -92340 | -184680 | -153900 | -143640 | -71820 | -25650
Cash in | 0 | 35910 | -92340 | -184680 | -153900 | -143640 | -71820 | -25650
Cash out | 0 | -90000 | -180000 | -150000 | -140000 | -70000 | -25000 | -10000
Cash flow | -35000 | -89090 | -361430 | -696110 | -990010 | -1203650 | -1300470 | -1336120
Exam marks
|  | 67.3333 | 6 MODULES
|  | 68.6 | 5 MODULES

## Student Halls of Residence - CF
Student Halls of Residence Cash Flow Forecast
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Cost (£) | 650000 | 845000 | 1645000 | 960000 | 2450000 | 4100000 | 1890000 | 1500000 | 760000 | 300000 | 560000 | 340000 | 0
Profit (£) | 0 | 708500 | 921050 | 1793050 | 1046400 | 2670500 | 4469000 | 2060100 | 1635000 | 828400 | 327000 | 610400 | 0
Retention (£) | 0 | 680160 | 884208 | 1721328 | 1004544 | 2563680 | 4290240 | 1977696 | 1569600 | 795264 | 313920 | 585984 | 0
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Cash in (£) | 0 | 680160 | 884208 | 1721328 | 1004544 | 2563680 | 4290240 | 1977696 | 1569600 | 795264 | 313920 | 585984 | 740633.6
Cash out (£) | 0 | 845000 | 1645000 | 960000 | 2450000 | 4100000 | 1890000 | 1500000 | 760000 | 300000 | 560000 | 340000 | 0
Cash flow (£) | -650000 | -814840 | -1575632 | -814304 | -2259760 | -3796080 | -1395840 | -918144 | -108544 | 386720 | 140640 | 386624 | 1127257.6
Retention
12 Month Project Completion |  |  |  | 1127257.6
12 Month Project Completion: 40% Retention Return |  |  |  | 0
6 Months After Project Completion: 60% Retention Return |  |  |  | 0
Forecasting the Cash Flow for the Student Halls of Residence with the Following Economic Conditions:
Estimated cost of works: £16 million
Duration: 12 months
Profit: 9%
Retention: 4% with 40% returned at the end of the project and the rest after 6 months.
Please Note that for some reason the two figures in the Retention table have gone blank but the table above is what the figures should be.
1. Calculate the cash-flow for the Student Halls of Residence.
The Cash Flow following the 12 month project completion is £1,127,257.60. After, 40% retention return is £450,903.04.
The remaining retention after 6 months is £721,444.86.
2. When does the project become profitable?
The project becomes profitable at month 10 with a cash flow of £386,720.00.

## Whole Life Costing
Whole Life Cycle with Potential Future Expansion in Year 5
[6 empty] | Whole Life Costing Over 30 Years | Services
Recurring Costs | Cost (£) | Frequency | Total Per Year (£) |  |  | Pumps | Without Service | With Service Level 1 | With Service Level 2 | With Service Level 3
Service Charge | 3000 | Twice a Year | 6000 |  |  | Small Pump | 1500000 | 1755000 | 1845000 | 1650000
Service Report | 500 | Twice a Year | 1000 |  |  | Large Pump | 2250000 | 2469000 | 2550000 | 2340000
Standard Call Out Charge | 500 | Assumption Twice a Year | 1000
Priority Call Out Charge | 2000 | Assumption 0 a Year | 0
Pump Replacement | 10000 | Every 8 Years | 1250
Average Parts Cost | 3000 | Two Parts a Year | 6000
|  | Total Accumulated (£) | 15250
Fixed Costs (£)
Small Pump | 1050000
Large Pump | 1800000
Whole Life Costing Without Service over 30 Years |  |  |  | Whole Life Costing With Service over 30 Years
30 Years Whole Life Costing WITHOUT Service |  |  |  | 30 Years Whole Life Costing WITH Service (Levels)
Service Charge | 180000 |  |  | Service Level 1 (£12,000 per year)
Service Report | 30000 |  |  | Small Pump | 1755000
Standard Call Out | 30000 |  |  | Large Pump (with 10% discount) | 2469000
Pump Replacement | 30000 |  |  | Service Level 2 (£15,000 per year)
Parts Replacement | 180000 |  |  | Small Pump | 1845000
Total (£) | 450000 |  |  | Large Pump (with 10% discount) | 2550000
Service Level 3 (£20,000 per year)
Total WITHOUT Service per Pump |  |  |  | Small Pump | 1650000
Small Pump | 1500000 |  |  | Large Pump (with 10% discount) | 2340000
Large Pump | 2250000
Recommendations over 30 Years (screenshot), Please see the Full Report.
Note: Please see the full report
This chart isn't available in your version of Excel. Editing this shape or saving this workbook in a different file format will permanently break the chart.

## Whole Life Costing (T&G Only)
Whole Life Cycle with Potential Future Expansion in Year 5
[6 empty] | Whole Life Costing Over 30 Years | Services
Recurring Costs | Cost (£) | Frequency | Total Per Year (£) |  |  | Pumps | Without Service | With Service Level 1 | With Service Level 2 | With Service Level 3
Service Charge | 3000 | Twice a Year | 6000 |  |  | Small Pump | 1500000 | 1755000 | 1845000 | 1650000
Service Report | 500 | Twice a Year | 1000 |  |  | Large Pump | 2250000 | 2469000 | 2550000 | 2340000
Standard Call Out Charge | 500 | Assumption Twice a Year | 1000
Priority Call Out Charge | 2000 | Assumption 0 a Year | 0
Pump Replacement | 10000 | Every 8 Years | 1250
Average Parts Cost | 3000 | Two Parts a Year | 6000
|  | Total Accumulated (£) | 15250
Fixed Costs (£)
Small Pump | 1050000
Large Pump | 1800000
Whole Life Costing Without Service over 30 Years |  |  |  | Whole Life Costing With Service over 30 Years
30 Years Whole Life Costing WITHOUT Service |  |  |  | 30 Years Whole Life Costing WITH Service (Levels)
Service Charge | 180000 |  |  | Service Level 1 (£12,000 per year)
Service Report | 30000 |  |  | Small Pump | 1755000
Standard Call Out | 30000 |  |  | Large Pump (with 10% discount) | 2469000
Pump Replacement | 30000 |  |  | Service Level 2 (£15,000 per year)
Parts Replacement | 180000 |  |  | Small Pump | 1845000
Total (£) | 450000 |  |  | Large Pump (with 10% discount) | 2550000
Service Level 3 (£20,000 per year)
Total WITHOUT Service per Pump |  |  |  | Small Pump | 1650000
Small Pump | 1500000 |  |  | Large Pump (with 10% discount) | 2340000
Large Pump | 2250000