|  | Negligible | Minor | Moderate | Major | Cat |
| --- | --- | --- | --- | --- | --- |
| Rare |  |  |  |  |  |
| Unlikely |  |  |  | Sens Calibration | Interlock system |
| possible | Document error |  | Mechanical alignment | Power supply instability/ Overheat control cabinet |  |
| likely |  | Training delay | Network communication |  | Soft Int Failure |
| Almost certain | Delay in Delivery |  |  |  |  |

Ranking

Document error – 3

Calibration issue – 8

Training delay – 8

Alignment error – 9

Interlock system – 10

Power instability – 12

Network failure – 12

Overheating – 12

Delay component – 15

Soft Int Fail – 20

RE = 150k * 0.02 = 3000

RE after mitigation = 150k * 0.005 = 750

Risk reduction = 2250

2250/1500 = 1.5

2250-1500 = +750

Yes, risk mitigation is worth it

Expected time 12.66 days

Standard deviation = 2

Z value = 20 days

So unlikely to achieve within 15 days

2 suitable risk response

- System integration

Risk transfer, outsource to a specialist

Have a contingency plan, maintain system backups and prepare a rollback plan, allocate extra time and budget

- Delay in component delivery

Use multiple different suppliers

Or identify alternative components that can be used for the same task