## Front
NRM1 Substructure Cost Plan for Student Accomodation
IP Construction
Sean Hazelby
05/04/2023

## Status
NRM1 Elemental Cost Plan Template
2022-11-02
Document Status
Revision | Date | Status | Prepared by | Checked by | Authorised by
DISCLAIMER
This document and its contents have been prepared and are intended solely for [name of client] information and use in relation to [name of project]
Faithful+Gould assumes no responsibility to any other party in respect of or arising out of or in connection with this document and/or its contents.
COPYRIGHT
The copyright of this document is vested in Faithful+Gould. This document may not be reproduced in whole or in part without their express written permission.

## Information Used
Information Used & Assumptions
1 | Information Used
Concept design
Structural drawings
No Finnsihed design was used for this take off
2 | General Assumptions;
Measurements have been assumed for time being as there is no scaled drawing available at this time
No premlims added along with no overheads - this will be added to the main cost plan
Risk allowance of 10%
Plant, labour and materials allowed into all rates
3 | General Notes and Exclusions;
Rates build up from sponds along with labour and materials prices
All included costs are subject to variation following design development.
Land Costs
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Local Authority Fees
Building Regulation fees
Party Wall Awards
Acquisition & associated legals

## Summary Original
Project details: House Type - H1
Description: Two 3 Bedroom Semi-Detached Houses
Building Works Estimate
Based on GIA of: 193m2 |  |  |  |  | 2417.95
| Group Element | Element Type | Total | £/m2
| Group element 1 | Site Prep | 228514.8 | 94.5077
| Group element 2 | North Building Radon | 13652 | 5.6461
| Group element 3 | North Building Substructure | 521085.94 | 215.5073 | 768.0662
| Group element 4 | South Building Radon | 10894 | 4.5055
| Group element 5 | South Building Substructure | 1082998.843 | 447.8996
Works cost estimate (sub total A) |  |  | 1857145.583 | 9826.1671
Project design team fees and other development costs (sub total B)
Base cost estimate A + B (sub total C) |  |  | 1857145.583 | 9826.1671
Group element 13
| Design Contingency | Risk allowance @ 5% | 92857.2792 | 38.4033
| Construction Risk | Risk allowance @ 2.50% | 46428.6396 | 19.2017
| Employers Change Risk | Risk allowance @ 2.50% | 46428.6396 | 19.2017
| Other Mis. Risk | Risk allowance @ 0% | 0 | 0
Total Risk allowances (sub total D) |  |  | 185714.5583 | 76.8066
Total Construction Cost (C + D) |  |  | 2042860.1413 | 844.8728

## NRM1 CP template
Cost Plan for Student Accomodation
NRM 1 phaseologies
Elemental Cost Plan
Ref. | Element | Timesing | Quantity |  | Unit | Rate | Sub-Total | Group-Total | Notes
[6 empty] | £ | £ | £
1 | Site Prep | [6 empty] | 228514.8
| Site cearance including excavation, muck away, redcuced levels, |  | 1 |  |  | 22000 | 22000 |  | Rate buildup from machine rates and labour cost with time factored in.
| Knotweed Removal |  | 50
|  |  | 80 | 4000 | m2 | 50 | 200000 |  | Assumed rate to cover worst case scenario
| Knotweed transporty to landfill and tpiing on 20t lorry over 40 miles trasnport |  | 5 |  |  | 1302.96 | 6514.8 |  | Japanese Knotweed contaminated
waste removal; PBA Solutions Ltd
(see note above)
Removal off site to a licensed landfill
site using 20 tonne gross vehicle
weight lorries; price is for haulage
and tipping only; the mileage stated
below is the distance from point of
collection to licensed landfill site;
price excludes landfill tax and
loading of material into lorries; rates
will fluctuate between landfill
operators and the figures given are
for initial guidance only
2 | NORTH BUILDING
| Radon management | [6 empty] | 13652
| Radon Sumps |  | 6 |  |  | 150 | 900
| Supporting Ductwork |  | 120 |  |  | 2 | 240
| Juta GP3 Radon DPM |  | 250 |  |  | 3 | 750
| Double sided joining tape |  | 8 |  |  | 10 | 80
| Foil Tape gas tape single sided |  | 8 |  |  | 34 | 272
| Keytec Tophats |  | 8 |  |  | 8 | 64
| Juta VOID VENT 25mm |  | 6 |  |  | 500 | 3000
| Slotted T Connector to 110mm pipe |  | 6 |  |  | 120 | 720
| Delivery |  | 4 |  |  | 300 | 1200
| Labour Allowance |  | 1 |  |  | 6426 | 6426 |  | 6 men @ £17/h 9 hour days - for 7 days work
3 | Substructure Construction | [6 empty] | 521085.94
| Excavation |  | 15
|  |  | 56.5 | 847.5 | m2 |  |  |  | Rate included
847.5
|  |  | 0.4 | 339 | m3 | 28.85 | 9780.15 |  | 6 men @ £17/h for 9 hour days - 10 days
| Concrete slab pour RC35 300mm |  | 847.5
|  |  | 0.3 | 254.25 | m3 | 375 | 95343.75 |  | Rate includes labour with steel mesh, DPM, 150mm PIR and RC35 Concrete
| Concrete Piles Driven 20m |  | 98 |  | no | 3337.47 | 327072.06 |  | Rate buildup
| Pile Caps 900mm× 900mm× 1000 mm; 1–2 piles |  | 10 |  | no | 1081.8 | 10818 |  | Rate buildup
| Pile Caps 2100mm× 2100mm× 1000 mm; 2–3 piles |  | 26 |  | no | 2041.23 | 53071.98 |  | Rate buildup
| Extra for reinforcement at 100 kg/m³ concrete |  | 250 |  | no | 100 | 25000 |  | Spons Page
4 | SOUTH BUILDING
| Radon management | [6 empty] | 10894
| Radon Sumps |  | 9 |  |  | 150 | 1350
| Supporting Ductwork |  | 160 |  |  | 2 | 320
| Juta GP3 Radon DPM |  | 300 |  |  | 3 | 900
| Double sided joining tape |  | 12 |  |  | 10 | 120
| Foil Tape gas tape single sided |  | 12 |  |  | 34 | 408
| Keytec Tophats |  | 12 |  |  | 8 | 96
| Juta VOID VENT 25mm |  | 10 |  |  | 500 | 5000
| Slotted T Connector to 110mm pipe |  | 10 |  |  | 120 | 1200
| Delivery |  | 5 |  |  | 300 | 1500
| Labour Allowance |  |  |  |  | 6426 | 0 |  | 6 men @ £17/h 9 hour days - for 7 days work
5 | Substructure Construction | [6 empty] | 1082998.843
Excavation
57
|  |  | 18.5 | 1054.5 | m2
10.5
|  |  | -10.5 | -110.25 | m2
50.5
|  |  | 12.4 | 626.2 | m2 |  |  |  | Rate included
|  |  |  | 1570.45 | m2
1570.45
| Total excavation |  | 0.4 | 628.18 | m3 | 28.85 | 18122.993 |  | 6 men @ £17/h for 9 hour days - 10 days
1570.45
|  |  | 0.3 | 471.135
| Concrete slab pour RC35 300mm |  | 1570.45
|  |  | 0.3 | 471.135 | m3 | 390 | 183742.65 |  | Rate includes labour with steel mesh, DPM, 150mm PIR and RC35 Concrete
| Concrete Piles Driven 20m |  | 184 |  | no | 3939.93 | 724947.12 |  | rates Buildup from labour and material costs
| Pile Caps 900mm× 900mm× 1000 mm; 1–2 piles |  | 23 |  | no | 1229.48 | 28278.04 |  | Internal walls
| Pile Caps 2100mm× 2100mm× 1000 mm; 2–3 piles |  | 46 |  | no | 2019.74 | 92908.04 |  | External walls
| Extra for reinforcement at 100 kg/m³ concrete |  | 350 |  | no | 100 | 35000
| Total | [6 empty] | 1857145.583
| 10% Risk Allowance | [6 empty] | 185714.5583 | 10% Allowance
| Main Total | [6 empty] | 2042860.1413