System Improvement Programme

Introduction

This section outlines the organisational context and the problem that has been identified.  In 2009, the National Assembly for Wales commissioned a report to look at how NHS Services in Wales could be run more efficiently (NWSSP, 2022b).  This was undertaken by Bath University and the report was published in October 2009 (Lewis M et al, 2009).  The report recommended the introduction of a shared services approach to non-clinical services across NHS Wales to bring about economies of scale, efficiencies and consistency of services (Lewis M et al, 2009).  This included administrative, professional and technical services.  In April 2011, NHS Wales Shared Services Partnership (NWSSP) came into being (NWSSP, 2022b) with offices opened in Cardiff, Nantgarw, St Asaph, Swansea, Pontypool as well as staff who are based within Health Boards across Wales.

According to NWSSP 2022c, the aim of NWSSP is to support NHS Wales by creating a dedicated shared services organisation with a distinct identity, which:

- Shares common operating standards in line with best practice

- Has sufficient scale to optimise economies of scale and purchasing power and improving quality

- Has an excellent customer care ethos and focus on service quality

Thereby acting in support of the statutory Health Boards and NHS Trusts in Wales, so that they may in turn, focus on more effective local delivery of front-line services. In addition, the organisation will provide professional advice and support to Welsh Government.

It has the following strategic objectives:

- Value For Money

  - Highly efficient and effective organisation.

  - Deliver real term savings and service quality benefits to its customers.

- Excellence

  - An organisation that delivers process excellence.

  - Focus on continuous service improvement, automation and the use of technology

- Customers and Partners

  - Open and transparent customer-focused culture.

  - That supports the delivery of high quality services

- Service Development

  - Extend the range of high quality services provided to NHS Wales and Welsh public sector.

- Staff

  - Appropriately skilled, productive, engaged, and healthy workforce.

(NWSSP 2022c)

At it’s inception, the following services were all entirely transferred from within Health Boards and trusts to NWSSP, who now provide services to the NHS throughout Wales:

Audit and Assurance Services,

Employment Services,

Health Courier Services,

Legal & Risk Services,

Primary Care Services,

Procurement Services

Specialist Estates Services

Since it’s initial launch, additional services have been added to the NWSSP portfolio including Accounts Payable, Central Team eBusiness, Counter Fraud Service, Digital Workforce Solutions, Finance Academy, Laundry Services, Lead Employer, Medical Examiner Service, Student Awards Services, Surgical Materials Testing Laboratory and Wales Infected Blood Support Scheme (NWSSP, 2022b).  Each Service is managed by a Division, which are discrete and autonomous due to the diverse nature of the services provided.

This assignment focuses specifically on the digital needs of Legal & Risk Services (L&RS), who provide legal advice to Health Boards and GP’s throughout Wales (NWSSP, 2022a).  The areas of legal advice offered include:

Clinical Negligence eg defending Health Boards/Trusts against claims of clinical negligence such as delay in diagnosis

Commercial eg procuring medical equipment

Court of Protection eg advising on whether it is legal to give specified treatment a patient who lacks capacity to make the decision themselves

Employment eg representing Health Boards at employment tribunals

General Practitioner Indemnity eg defending GP’s against claims of clinical negligence

Inquests eg advising on evidence gathering and legal processes at inquests

Personal Injury eg defending Health Boards/Trust against claims of personal injury such as falls or needlesticks

Property eg buying or renting properties for healthcare such as mass vaccination centres

The functional organisational structure of L&RS is as follows:

Fig1 – Organisational Structure

Each legal Team is made up of a Team Leader, senior solicitors, solicitors, legal executives, trainees, paralegals, and secretaries.  The number of staff in each Team varies, with the smallest Team made up of 5 staff and the largest being 17.  The Business Support Team consists of administrators who process the mail and book travel, IT support who support the software used by L&RS  and media co-ordinators who publish newsletters and manage social media.  The Welsh Risk Pool (WRP) is somewhat different from the rest of L&RS.  Amongst other things, it manages reimbursements of compensation claims to Health Boards & Trusts, the Once for Wales DATIX Project and an initiative aimed at improving safety of maternity care known as PROMPT.  WRP is out of scope for the purposes of this assignment.  There are 166 staff in total.

Most legal matters begin with an enquiry.  Legal & Risk services will act on behalf of Health Boards or GP’s, corresponding with both the client and the person raising the legal issue (the other side).  Expert advice may be requested, and all parties may meet at a “round the table” meeting to negotiate the position.  If negotiations are unsuccessful, the case may progress to court for a judge to make a decision on the case.

The digital end user experience within Legal & Risk Services is made up of 4 components:

- A bespoke case management system, known as “the database”, which was built by an external contractor.  This holds all data relating to the legal matters.

- An of the shelf document management system called Virtual Cabinet (VC).  This holds all the documents relating the legal matters.  It has integrations with the database, such that users can retrieve documents directly from the database.

- Some smaller solutions that have been built by the Legal & Risk IT Team to meet additional needs of the Service, such as the Flexi App for managing flexible working.

- A Terminal Server to support home working.

The full infrastructure is illustrated in Fig 2.  Users do not see the VC file server but are able to retrieve documents from it using the VC Application.  With the exception of Office 365, users must use VPN to connect to the digital infrastructure when working remotely.  A terminal server is also available for staff whose broadband is slow.

Fig 2 Legal & Risk Digital infrastructure

Staff make use of Office 365 products such as Outlook and Word.  However, the licencing arrangements also include the Power Platform, which is not currently used.

The problem under consideration in this assignment pertains to the requirement of legal staff to undertake travel in order to perform their duties as a legal representative for NHS Wales.  They may visit clients, a witness, the other side or attend court.  This can take place throughout the UK and may require overnight stays.  Presently, when staff require travel and/or accommodation, this can be done in several ways and the process varies by Team.  Staff should obtain permission from their line manager and ask the Administration Team to book it in advance.  A budget holder should sign off the expense before it is purchased.  However, sometimes staff do not get line manager approval before approaching the Administration Team and sometimes staff book travel themselves and claim the journey on expenses after the event.  This makes it difficult for L&RS management to control the travel expenses budget and the organisation lacks data on staff travel.  Staff may book travel or accommodation that is outside the budget range, which is problematic.  For example, staff may book first class train travel but the NWSSP Travel and Subsistence Guidance (Lewis, P., Butler, A., 2014) only supports standard class travel.  The Finance Department is able to provide a total spend for expenses but cannot break that down reliably into travel expenses and other business expenses.  The organisation doesn’t know how much each member of staff is using of the travel budget, or why.  It doesn’t know if it’s getting value for money for travel and accommodation booked.  It doesn’t know cancellation rates.  There can be delays in staff’s travel being approved and the NWSSP Travel and Subsistence Guidance (Lewis, P., Butler, A., 2014) is not always followed.

Fig 3 Ishikawa’s Fishbone (Radziwill, N. 2017)

An information system would:

- Make it easier to ensure NWSSP guidance on travel expenses (Lewis and Butler 2014) and NHS Terms and Conditions (NHS Employers 2022, Section 17) are followed and that only approved journeys are reimbursed.

- Provide information about the total spend on travel and accommodation,

- Capture details of hotels used and prices, enabling discounts to be negotiated with those regularly used.

- Enable meetings to be planned around the most cost-effective times to travel.

- Give managers oversight of the journeys undertaken by their Teams.

- Simplify the booking process

- Ensure that staff have line management approval for their journey before it is booked.

- Enable the Administration Team to choose from a list of pre-approved providers.

- Provide reliable data on travel costs, supporting better budget planning and management.

- Enable the Director, Deputy Director, Head of Clinical Negligence, and other Team Leaders to see who is travelling where and for what, supporting future planning.

- Reduce Carbon Footprint by ensuring the most suitable method of transport was used and that travel was necessary.

Therefore, introducing a travel app would bring about considerable benefits to the organisation and the environment.

Justification

This assignment considers 4 options:

- Do nothing

This does not address any of the issues identified above.  There will be no opportunity to save money, reduce environmental impact or improve management information on travel.

- Buy an off the shelf solution

This would likely meet the needs of the Division.  However, there will be a cost attached.  There is no funding for the project, therefore, this option would require a business case and significant delays to secure the funding required.

- Utilize freeware

This may meet the needs of the Division.  However, it is unlikely to meet the security requirements of the NHS Wales network.  It will also be unsupported in the event of technical problems.

- Build an App in-house using the Power Platform

This would meet the exact needs of the Division.  It would utilise existing staff and licences, so would be cost neutral, apart from time.  The Legal & Risk IT Team have capacity and skills to take on this project.  It could be customised in the future, if needed and could be supported on an on-going basis.  This is the preferred option.

Option 4 involves the building of a Microsoft Power Platform solution utilizing Power Apps to be managing the requesting of travel/accommodation and Power Automate for notifications.

This assignment recommends Option 4, because the organisation has already invested in Microsoft products, meaning that there would be no additional software costs for the solution.  It would offer a cloud-based solution, which is in line with the Government Cloud First Policy (Gov.uk, 2022).  Microsoft Power Platform is a modern low code cloud solution (Microsoft, 2022a).  Staff could access the App remotely and on their smart devices, making it convenient and accessible.  It would not require VPN access, making it more convenient for staff and would integrate with existing software that is in use by the Division.  The in-house development Team already has the skills to build the solution and support users after go-live.

Costs Benefit Analysis

A costs-benefit analysis looks at the financial benefits of doing something compared to the financial costs (Shaffer, M., 2010).  If more money is saved than spent, the project is considered worth while.   The justification above is further supported by a cost-benefit analysis.  The project’s only costs relate to staff time.  These are for the duration of the project and ongoing support after go-live.  There are many benefits, which include:

- Data and therefore information on travel being captured which can provide intelligence to assist with travel, service and budgetary planning

- A simplified booking process, which is accessible and easy for staff to use.

- Improved Governance, offering assurance around travel expenditure and the appropriateness of travel undertaken.

- Improved value for bookings, ensuring that the most cost-effecting travel is arranged and preventing uncontrolled spending.

- Discounts can be secured with hotels that are frequently used or with hotel chains due to evidencing the volume of bookings.

- L&RS’s carbon footprint will be reduced as mode of travel will be managed and a clear justification for each journey will be captured.

Fig4 Costs Benefit Analysis Adapted From Krieshok, G. 2022

Whilst it is difficult to determine the actual monetary savings of the project due to lack of data captured in the existing process, given that there is no cost for delivery, the reduction in cost of a single journey would make the project financially viable.  It is anticipated that this project will lead to a reduction in travel expenditure by improving governance around the booking process, ensuring that only compliant travel is booked.  Many of the benefits are more than just financial, they improve operational efficiency and future planning.  On balance, this assignments recommends proceeding with the project.

Aims & Objectives

The aim of the project is to implement an in-house supported, Web based solution that enables complete management of travel requests including data to support efficiency savings.

The project itself is SMARTER (Shirley 2011, pp. 38-40)  as below:

| S | Specific | Improving the process for requesting and booking travel using Microsoft’s Power Platform to build a Travel Management App. |
| --- | --- | --- |
| M | Measurable | Data on travel booked will be captured by the new system. This can be compared to a manual audit of the existing process to demonstrate improvements in cost and timeliness. A user survey will be conducted as part of the project closure process to capture user satisfaction. |
| A | Achievable | Legal & Risk Services have a dedicated IT Team who have the necessary skills to carry out the design and build work. Legal & Risk Services staff have expressed a desire for the implementation. |
| R | Relevant | The proposal is consistent with NWSSP Travel and Subsistence Guidance (Lewis and Butler, 2014) and Sections 17 and 18 and Annex N of the NHS Terms and Conditions of Service handbook (NHS Employers, 2022, Sections 17, 18) |
| T | Timely | The project will be completed within 6 months. |
| ER | Environmentally Responsible | The project will reduce unnecessary travel and increase environmentally friendly methods of travel, enabling measurement of and reduction in the carbon footprint. |

Fig 5 SMARTER Objectives

4 key SMART objectives that fit with Leavitt’s Diamond model (Tahir, 2022) are as follows:

- Task: The project will deliver a Travel Requests App in order for staff to electronically request travel, for managers to approve the travel, Administration to identify travel options and book them and budget holders to approve spend on travel by May 2023.

- Structure:  A Project Management Team will be set up involving all key stakeholders to oversee the implementation, ensure engagement at all levels and delivery of the project by May 2023.

- Technology:  Microsoft’s Power Platform, Azure and Active Directory will be used to build the Travel Application ahead of the go-live so that all staff are comfortable using it.

- People:  The Legal & Risk IT Team will provide Training to all Legal & Risk staff on using the Travel Application.

The project also has the following goals:

- Legal &Risk Staff to be able to electronically submit requests for travel, including details of where, when, why and who in order for travel to be booked ahead of the journey.

- To enable line managers to electronically approve travel requests before the travel is booked.

- Administration Team to be able to electronically capture 3 quotes for every journey so that the most suitable journey can be booked.

- Budget Holder to be able to electronically record approval for each trip to be booked.

- A library of best value hotels to be captured through gathering of quotations and made available for future bookings.

- To be able to produce business management reports on travel undertaken to monitor and manage the travel expenses budget.

- Users to be able to electronically track the approval status of travel requests in real time.

- Users to be able to cancel travel requests ensuring refunds are sourced on travel booked.

- To be able to calculate the carbon footprint of each journey.

- To reduce the carbon footprint of L&R Services through the use of environmentally friendly travel options.

Introducing new technology to manage travel requests will make the task of managing travel requests easier, positively impacting staff, and supporting the structure of Legal & Risk Services.  Consultation with staff has also indicated that they are supportive of the proposal.  The project itself will lead to better information about travel undertaken and reduce inappropriate spend.  However, as current data is poor, it will be difficult to measure this improvement.  Once the solution is in place, L&RS will have accurate data and will be able to undertake more reliable travel budget forecasting and demonstrate improvements over time.  This can be measured as total cost savings, number of journeys undertaken, modes of transport used and average cost per journey.  This may enable diversion of funds to other areas.

Literature Review

Search Strategy:

ITIL Project Management

PRISMA was used to design the search strategy

Results: Emerging themes,  evidence how implementation and adoption of IS solved business problems and evidence of the use of different project management methodologies for IS implementation projects

Determining Methodology

Identify a suitable project management methodology and justification

In identifying a suitable methodology, the first thing considered is identifying the type of work to be carried out.  IT infrastructure Library (ITIL) is a methodology for managing IT Services comprising service strategy, service design, service transition, service operation and continuous improvement (IBM Cloud Education, 2019).  This assignment considers the onboarding of a new information solution, rather than routine operational management of IT services.  Therefore, ITIL was considered not suitable for managing the implementation.

Program management was also considered.  Didinsky, I., (2017) reports that there are several different definitions of program management and defines it as a group of projects, subprojects and operational management activities that are linked and managed in a co-ordinated way so as to reap benefits that would not be achieved managing them individually.  Using this definition, it is clear that the project is not a program as it only involves a single application development.

Both PRINCE2 and PMBOK are project management methodologies.  Kononenko, I. V. and Lutsenko, S. YU (2017) report that work experience, expert opinion, government regulation, preferences of stakeholders and the client and the client’s location should be considered when selecting a project methodology.  Within NWSSP, Prince2 is routinely used for project management.  It will therefore be used as the basis for this project.

The project has the following characteristics:

- Clearly defined start and end points

- Definitive milestones

- Short duration

- Understood by all stakeholders

It does not:

- Require iterative stages

- Development sprints

- A large number of developers

- Require constant feedback

- Require incremental releases

- Changing requirements

- Multiple Teams working in parallel

Comparing these attributes to the paradigms listed by Baseer K. K., Reddy, A. R. M. and Bindu, C. S. (2015)’s survey of various paradigms, the project will use waterfall.

|  |  | Waterfall | Prototype | Incremental | Iterative | V Model | Spiral | SCRUM | Clean Room | RAD | Dynamic System Development | Unified Process | XP | Agile | Lean | Dual Vee | Test Driven | Behavioural Driven | Feature Driven | Domain Driven | Model Driven |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HAS | Clearly defined start and end points | ü | û | û | û | ü | û | ü | ü | û | û | û | ü | û | ü | û | û | û | û | û | ü |
|  | Definitive milestones | ü | û | ü | ü | ü | û | ü | ü | û | û | û | ü | û | û | û | û | û | û | û | ü |
|  | Short duration | ü | û | ü | û | ü | û | û | û | ü | ü | û | ü | ü | û | û | ü | ü | ü | û | û |
|  | Stages that can overlap | ü | û | û | û | û | ü | ü | û | ü | ü | û | ü | ü | ü | ü | ü | ü | ü | û | ü |
|  | Understood by all stakeholders | ü | û | ü | û | ü | û | ü | û | ü | ü | ü | ü | û | ü | û | û | ü | ü | û | ü |
| DOES NOT | Require iterative stages | ü | û | û | û | ü | û | û | û | ü | û | û | û | û | û | û | ü | û | û | û | ü |
|  | Development sprints | ü | û | û | û | ü | ü | û | û | û | û | û | û | û | û | û | ü | û | û | û | ü |
|  | A large number of developers | ü | û | û | û | ü | û | ü | û | û | ü | ü | ü | ü | ü | û | ü | ü | ü | û | û |
|  | Require constant feedback | ü | û | ü | û | ü | ü | û | ü | ü | û | û | û | û | ü | û | û | û | û | û | ü |
|  | Require incremental releases | ü | û | û | û | ü | û | û | ü | ü | û | û | û | û | û | û | û | û | û | û | ü |
|  | Changing requirements | ü | û | û | û | ü | û | û | û | ü | û | û | û | û | û | û | û | û | û | û | ü |
|  | Multiple Teams working in parallel | ü | û | û | û | ü | û | û | û | ü | ü | û | û | û | ü | û | û | û | û | û | û |
|  | Require automated code generating tools | ü | ü | ü | ü | ü | ü | ü | ü | û | ü | ü | ü | ü | ü | ü | ü | ü | ü | û | ü |
|  | Require a pre-existing model | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | û |

Fig 7 Paradigm Suitability (Baseer K. K., Reddy, A. R. M. and Bindu, C. S. 2015)

Prince 2 Methodology

This method of project management requires completion of a Project Initiation Document that describes every element of the project, including the project definition, objectives, scope, roles/responsibilities, assumptions, constraints, interfaces, benefits, timescales, costs, risks, issues, change management, quality, communication, controls reports, plan and milestones.  It requires that there is a justifiable business case.  The completion of the Project Initiation Document triggers the launch of the project (Bentley, C 2005).

Considering each of these items separately, the project definition and objectives have been addressed earlier in this assignment.  The scope includes all travel requests for Legal & Risk Services legal staff.  It does not include WRP or other Divisions.  The project will be managed by a Project Board and the roles in the proposed project are as follows:

Fig 8 Project Board Membership

The Project Board includes representation from all stakeholders who have an interest in the project, and it will be accountable for the project delivery.

The assumptions are as follows:

- L&R IT have capacity to undertake the development and ongoing support

- Sufficient licences are available for all staff

- The product will be compliant with Information Governance and Cyber Security requirements of NWSSP

- The chosen product has all the functionality required to deliver the solution

- The project does not conflict with other projects within NWSSP

The constraints are as follows:

- The project must be delivered within 6 months in order to support the business annual review.

- Staff capacity – NWSSP IT Security staff availability is limited

The benefits have been addressed in the introduction to this assignment.  The timescales are as per Figure 9 below.

Fig 9 Project Plan/Gantt Chart

The project is cost neutral as there is no additional expenditure required.  However, staff time will be a soft expense as staff will be diverted away from other work to complete the project.

The risks to the project will be recorded in a risk register and updated at each Project Board meeting.  The initial risks are identified as follows:

Fig 10 Risk Register (Adapted from Duijm, N. J 2015)

The scores above are derived from the risk matrix below:

|  | Impact/Consequence |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Probablity/ Likelihood |  | Insignificant | Minor | Moderate | Major | Catastrophic |
|  | Rare | 1 | 2 | 3 | 4 | 5 |
|  | Unlikely | 2 | 4 | 6 | 8 | 10 |
|  | Possible | 3 | 6 | 9 | 12 | 15 |
|  | Likely | 4 | 8 | 12 | 16 | 20 |
|  | Almost Certain | 5 | 10 | 15 | 20 | 25 |

Fig 11 Risk Matrix (Adapted from Duijm, N. J 2015)

All issues will be recorded and reviewed at Project Board meetings in a similar format to the risk matrix.  There are no issues at the outset of this project.

A Change Control log will be kept to record any unexpected changes and all new changes will be signed off at each Project Board.  Quality will be managed through the sign off of key milestones at the end of each phase by the Project Board.

Discussion

The Travel Requests App will make data available about staff travel that is currently not captured.  L&R Services will have insight into the types of journeys undertaken by staff, the distance, the mode of transport, the frequency with which specific staff travel, the amount of travel for each matter and the cost of individual journeys.  Audit of this information will provide intelligence on the appropriateness of journeys undertaken.  This can be used to provide guidance on the mode of transport that should be used dependent on travel plan.  This will also reduce the carbon footprint of Legal & Risk Services and it’s impact on climate change.  According to Carbon Footprint (2022) the Carbon Footprint for the most commonly used modes of transport are:

| Mode of Transport | Tonnes of Co2 per 100 miles |
| --- | --- |
| Average Petrol Car | 0.03 |
| Average Diesel Car | 0.03 |
| Average Plug-in Hybrid | 0.01 |
| Bus | 0.02 |
| Coach | 0.004 |
| Rail | 0.01 |
| Taxi | 0.02 |

Therefore, coach is the most environmentally friendly mode of transport.  If the Travel App is used to book coaches rather than other modes of transport, this will reduce the carbon footprint and make progress towards Welsh Government’s pans towards net zero carbon emissions for public services (Welsh Government, 2022).

Digital nudging is the concept of using technology to influence decisions (Weinmann, M., Schneider, C. and Brocke, J. vom 2016).  It can be used to influence users to make more environmentally responsible travel choices and consider other options, such as virtual meetings, reducing costs and carbon footprint.

Further benefits of the intervention include being able to review the frequency with which Clients are visited in person to ensure that client relationships are developed across the whole portfolio.

The number of in person meetings can be compared to on-line meetings.  This data can be used to prepare a policy for meetings management.  This will drive down the cost of unnecessary journeys, releasing funds for service improvements elsewhere.

Although this essay considers the development of a travel application specifically for Legal & Risk Services, other Divisions within NWSSP also have travel requirements and there is potential for it to be rolled out across other Divisions in the future.  Further, the design could be shared with other NHS organisations to enable them to manage requests for travel more efficiently.  It could also be modified to accommodate other purchases such as office stationary or electronic devices.  Within the clinical environment, staff could use it to request uniforms or PPE.  This would provide more detailed information on where these items are being used and by whom.

The introduction of the Travel Requests App will be the first Power Platform application within L&R Services.  The division currently has 14 bespoke applications in use.  These use a SQL database with a MS Access 2007 user interface.  These include:

| Product | Purpose |
| --- | --- |
| Business Summary App | Produces an Excel report summarising activity by Client which is then shared with the Client. |
| Employment Block Report | A report summarising charges for employment law work provided for Clients |
| Clinical Negligence Dashboard | Produces an Excel report summarising Clinical Negligence activity by Team |
| CRU App | Provides information on Cost Recovery Unit (CRU) status to support updating of CRU data in the Legal & Risk Database |
| Daily Reporting App | Provides a summary of work recorded by legal staff each day |
| Error Reporting | Used to record mistakes made by staff and actions taken to mitigate the consequences. |
| Flexi App | Used by staff to manage their flexible working |
| GMPI App | Enables GMPI matters to be created in the Legal & Risk Database and produces a number of key performance indicator reports. |
| Property Reporting App | Produces a report on matters being managed by the Property Team |
| QBS | Enables billing of matters on a monthly basis. |
| Surveillance App | Records requests for surveillance of claimants and outcomes of requests. |
| Task Owners Report | Provides a report detailing the status of tasks by the creator of the task. |
| Template App | Enables staff to create template letters and automatically file them within VC |
| Training Record | Records training and development plans for staff |

Access 2007 is no longer supported by Microsoft (Microsoft 2022b) and presents a security risk to the NHS Wales network as it is no longer receiving security updates.  All of these applications would benefit from migrating to the Power Platform to address the security issues and modernise the interface for users.  The improved functionality would enable more complex reports to be produced and demand for information would increase.  This would enable further service delivery improvements over time as data quality and data monitoring would improve.  It will also introduce the opportunity for further developments for example the ability for Clients to complete an online referral form, which would automatically create a matter in the Legal & Risk database.

To conclude, this project innovation will save money, simplify the process for requesting travel, lower the carbon footprint, has potential for wider use and influence the upgrading of other aged products.

References

For Books: Author (Date) title of book. Edition. City of Publication: Publisher.

For Articles: Author, (date) ‘Title of article’.  Name of Journal. Volume No, pp pages.  Available at: DOI No or website

Cook, S. (2011) Essential Time Management and Organisation: A Pocket Guide.  Available at:http://www.jstor.org/stable/j.ctt5hh72n (Accessed: 1 Nov 2022)

Baseer, K.K., A Rama, M.R. and C, S.B., (2015) ‘A Systematic Survey on Waterfall Vs. Agile Vs. Lean Process Paradigms’. i-Manager's Journal on Software Engineering. 9(3), pp. 34-59.  Available at: DOI: 10.26634/jse.9.3.3471

Bentley, C. (2005) Prince 2 Revealed. 2nd Edition.  Available at https://r4.vlereader.com/Reader?ean=9780080458823 (Accessed: 13/12/22)

Didinsky, I., (2017) The practitioner's guide to program management.  1st Edition.  Available at: https://ebookcentral.proquest.com/lib/trinity/reader.action?docID=5301729 . (Accessed: 12 December 2022).

Carbon Footprint Ltd (2022) Carbon Calculator Available at: https://www.carbonfootprint.com/calculator.aspx  (Accessed: 14/12/2022)

Duijm, N. J. (2015) ‘Recommendations on the Use and Design of Ris Matrices’.  Safety Science. 75, pp21-31.  Available at: doi.org/10.1016/j.ssci.2015.02.014. (accessed 13/12/2022)

Gov.uk (2022) Guidance Government Cloud First Policy. Available at: https://www.gov.uk/guidance/government-cloud-first-policy (Accessed: 3 Nov 2022)

IBM Cloud Education (2019) IT Infrastructure Library.  Available at https://www.ibm.com/uk-en/cloud/learn/it-infrastructure-library#:~:text=What%20does%20ITIL%20mean%3F,and%20printed%20them%20for%20distribution. (Accessed: 12/12/2022)

Ishikawa, K and Loftus, J.H., (1990) Introduction to quality control. Tokyo: 3A Corporation.

Krieshok, G. (2022) Everyday Concepts Cost-Benefit Analysis.  Available at: https://everydayconcepts.io/cost-benefit-analysis/  (Accessed: 13/12/2022).

Kononenko, I. V., Lutsenko, S. YU., (2017) ‘Method for selection of Project Management Approach Based on Fuzzy Concepts’.  Вісник Національного Технічного Університету «ХПÌ». Серія: Стратегічне Управління, Управління Портфелями, Програмами Та Проектами,  7(2), pp 8–17. Available at: https://doaj.org/article/dc8a26aa08ef437a8e6ae58a8bc0e6c1

Lewis, P., Butler, A. (2014) ‘NWSSP Travel and Subsistence Guidance’. NWSSP. Unpublished. Available at https://nhswales365.sharepoint.com/sites/SSP_Intranet_POD/Policies%20Procedures%20and%20Forms/Forms/AllItems.aspx?id=%2Fsites%2FSSP%5FIntranet%5FPOD%2FPolicies%20Procedures%20and%20Forms%2FPolicies%2C%20Procedures%2C%20Guidelines%2FTravel%20and%20Subsistence%20Guidance%2Epdf&parent=%2Fsites%2FSSP%5FIntranet%5FPOD%2FPolicies%20Procedures%20and%20Forms%2FPolicies%2C%20Procedures%2C%20Guidelines  (Accessed 28 Oct, 2022)

Lewis, M., Carey, S., Phillips, W. (2009) ‘Taking Forward Shared Services in NHS Wales’ NWSSP.  Unpublished  at https://nhswales365.sharepoint.com/sites/SSP_Intranet/Corporate%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSSP%5FIntranet%2FCorporate%20Documents%2FBath%20University%20Study%2FTaking%20Forward%20Shared%20Services%20in%20NHS%20Wales%2Epdf&parent=%2Fsites%2FSSP%5FIntranet%2FCorporate%20Documents%2FBath%20University%20Study (Accessed 9/12/2022)

Microsoft (2022a) What is Microsoft Power Platform Available at: https://powerplatform.microsoft.com/en-gb/what-is-power-platform/ (Accessed: 3 Nov 2022)

Microsoft (2022b) Office 2007 end of support Available at: https://learn.microsoft.com/en-us/lifecycle/announcements/office-2007-end-of-support  (Accessed: 13 Dec 2022)

NHS Employers (2022) NHS Terms and Conditions of Service Handbook, Handbook amendment number 28 Pay Advisory Notice (02/2022) Available at https://www.nhsemployers.org/publications/tchandbook (Accessed 3 Nov 2022)

NWSSP (2022a) Legal and Risk Services. NWSSP.  Unpublished.  Available at: https://nwssp.nhs.wales/ourservices/legal-risk-services/  (Accessed: 1 Nov, 2022).

NWSSP (2022b) Our History.  Unpublished.  at https://nhswales365.sharepoint.com/sites/SSP_Intranet/SitePages/Our-History.aspx  (accessed 9/12/2022)

NWSSP (2022c) About Us.  Available at https://nwssp.nhs.wales/about-us/ (Accessed 14/12/2022)

Radziwill, N. (2017) ‘Creating Ishikawa (Fishbone) Diagrams With R’, Software quality professional, 20(1), pp. 47–48.

Creating Ishikawa (Fishbone) Diagrams With R - ProQuest

Shaffer, M. (2010) Multiple Account Benefit-Cost Analysis: A Practical Guide for the Systematic Evaluation of Project and Policy Alternatives.  Available at https://www-jstor-org.ezproxy.uwtsd.ac.uk/stable/10.3138/j.ctt2tv3p2 (Accessed: 12/12/2022)

Tahir, U. (2022) Change Management Insight.  Available at: https://changemanagementinsight.com/what-is-leavitts-diamond-model/ (Accessed: 2 Nov 2022)

Shirley, D., 2011. Project management for healthcare (1st ed.) London: CRC Press.

Weinmann, M., Schneider, C. and Brocke, J. vom (2016) ‘Digital Nudging’, Business & information systems engineering, 58(6), pp. 433–436. Available at: https://doi.org/10.1007/s12599-016-0453-1.

Welsh Government (2022) Net Zero Wales Available at: https://www.gov.wales/net-zero-wales (Accessed: 15/12/22)